## Con. Progress
CONSTRUCTION PROGRESS
Project: | Renovation Works of The Project for Building Capacity and Establishing Enabling Environment in ICT Majors of TVET in Cambodia
Subtitle: | Detailed Bill of Quantities of 40 Classrooms
Date: | 2026-04-27 | [7 empty] | Rev.01
ID | Scope of Works | Detail Description | Unit | Revise BOQ |  |  |  |  | Remark | THIS WEEK |  |  | NEXT WEEK |  |  | UP TO NEXT WEEK
|  |  |  | QTY | Material | Labor | Unit Rate | Amount |  | QTY | AMOUNT | % | QTY | AMOUNT | % | QTY | AMOUNT | %
I | Preliminary Works |  | Item | 1 |  |  |  | 63951.4
II | Renovation Works |  | Item | 1 |  |  |  | 850566.6
1 | Architectural Works |  | Item | 1 |  |  |  | 423137.8 | - Revise quantities based on the actual site condition. - Propose new skirting in all rooms where new floor tile (F2) is installed. - Propose new MC wood molding with laminate finish for the top trim of W5 and around WD1.. - Some existing windows, doors, and ceilings are in good condition and are proposed to be reused and repainted.
2 | Electrical Works |  | Item | 1 |  |  |  | 350611.8 | - Have no revise
3 | Miscellaneous and Common Work |  | Item | 1 |  |  |  | 76817 | - Revise quantities of window blind base on actual site - Revise quantities of ventilation block to improve airflow around the AC
III | Other Works |  | Item | 1 |  |  |  | 5000
A | Direct Cost | [6 empty] | 919518
B | Indirect Cost |  | Item | 1 |  |  |  | 64366
C | Construction Cost [A]+[B] | [6 empty] | 983884
D | HSE(Health, Safety, and Environment) | 0.6% of Construction Cost | Item | 1 |  |  |  | 5903
E | Contingency | 10% of Construction Cost | Item | 1 |  |  |  | 98388.4
F | Overhead & Profit | 5% of Construction Cost | Item | 1 |  |  |  | 49274.6
G | Bid Price [C]+[D]+[E]+[F] | [6 empty] | 1137450
I | Preliminary Works | [6 empty] | 63951.4
1 | Contractor temporary facilities | - Preparation and operation of contractor site office, meeting table, stock area for the construction period. | LS | 1 |  |  | 63951.4 | 63951.4
II | Renovation Works | [6 empty] | 850566.6 |  |  | 260698.203 | 30.65% |  | 29392.815 | 3.456% |  | 290091.018 | 34.11%
1 | Battambang Province | [6 empty] | 87288.92 |  |  | 16331.871 | 18.71% |  | 6064.04 | 6.947% |  | 22395.911 | 25.66%
1.1 | Battambang Institute of Technology (BIT) | [6 empty] | 40306.72 |  |  | 8106.805 | 20.11% |  | 2036.498 | 5.053% |  | 10143.303 | 25.17%
1.1.1 | A-TYPE | [6 empty] | 16664.86 |  |  | 2985.85 | 17.92% |  | 751.43 | 4.509% |  | 3737.28 | 22.43%
A | Architectural Works | [6 empty] | 7798.56 |  |  | 1114.2 | 14.29% |  | 252.24 | 3.234% |  | 1366.44 | 17.52%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 62 | 2.6 | 1.8 | 4.4 | 272.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 100%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 82.4043 | 1.8 | 2.8 | 4.6 | 379.06 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 53.9 | 5 | 4 | 9 | 485.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61.0567 | 41.8 | 12.9 | 54.7 | 3339.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 36 | 4.3 | 3.6 | 7.9 | 284.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 62 | 22.6 | 7.6 | 30.2 | 1872.4 |  | 31 | 936.2 | 50% | 6.2 | 187.24 | 10% | 37.2 | 1123.44 | 60%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0.6 | 93 | 60% | 0.2 | 31 | 20% | 0.8 | 124 | 80%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 10 | 11.3 | 5.7 | 17 | 170 | The existing security bars are in good condition, we propose repainting | 5 | 85 | 50% | 2 | 34 | 20% | 7 | 119 | 70%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 7327.7 |  |  | 1761.07 | 24.03% |  | 493.37 | 6.733% |  | 2254.44 | 30.77%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.3 | 383.28 | 30% | 0.1 | 127.76 | 10% | 0.4 | 511.04 | 40%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.35 | 592.55 | 35% | 0.1 | 169.3 | 10% | 0.45 | 761.85 | 45%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.4 | 785.24 | 40% | 0.1 | 196.31 | 10% | 0.5 | 981.55 | 50%
C | Miscellaneous and Common Work | [6 empty] | 1538.6 |  |  | 110.58 | 7.187% |  | 5.82 | 0.3783% |  | 116.4 | 7.565%
| Miscellaneous | [6 empty] | 913.6
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 11 | 44.2 | 19 | 63.2 | 695.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 6 | 12.1 | 7.3 | 19.4 | 116.4 | Revise quantities based on the actual site | 5.7 | 110.58 | 95% | 0.3 | 5.82 | 5% | 6 | 116.4 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| Common Works | [6 empty] | 625
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
1.1.2 | B-TYPE | [6 empty] | 23641.86 |  |  | 5120.955 | 21.66% |  | 1285.068 | 5.436% |  | 6406.023 | 27.1%
A | Architectural Works | [6 empty] | 10368.56 |  |  | 2410.5 | 23.25% |  | 540.498 | 5.213% |  | 2950.998 | 28.46%
| Floor Finish | [6 empty] | 541.2
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 123 | 2.6 | 1.8 | 4.4 | 541.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| Wall Finish | [6 empty] | 5496.76
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 110.6 | 1.8 | 2.8 | 4.6 | 508.76 |  | 0 | 0 | 0% | 5.53 | 25.438 | 5% | 5.53 | 25.438 | 5%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 77.7 | 5 | 4 | 9 | 699.3 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 36 | 183.6 | 90% | 4 | 20.4 | 10% | 40 | 204 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 51 | 41.8 | 12.9 | 54.7 | 2789.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 50 | 4.3 | 3.6 | 7.9 | 395 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| Ceiling Works | [6 empty] | 3714.6
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 123 | 22.6 | 7.6 | 30.2 | 3714.6 |  | 61.5 | 1857.3 | 50% | 12.3 | 371.46 | 10% | 73.8 | 2228.76 | 60%
| Door Works | [6 empty] | 310
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 2 | 120 | 35 | 155 | 310 |  | 1.2 | 186 | 60% | 0.4 | 62 | 20% | 1.6 | 248 | 80%
| Window Works | [6 empty] | 306
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 18 | 11.3 | 5.7 | 17 | 306 | The existing security bars are in good condition, we propose repainting | 10.8 | 183.6 | 60% | 3.6 | 61.2 | 20% | 14.4 | 244.8 | 80%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 2507.725 | 22.96% |  | 733.9 | 6.721% |  | 3241.625 | 29.68%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.25 | 517.025 | 25% | 0.1 | 206.81 | 10% | 0.35 | 723.835 | 35%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.35 | 823.62 | 35% | 0.1 | 235.32 | 10% | 0.45 | 1058.94 | 45%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.4 | 1167.08 | 40% | 0.1 | 291.77 | 10% | 0.5 | 1458.85 | 50%
C | Miscellaneous and Common Work | [6 empty] | 2353.2 |  |  | 202.73 | 8.615% |  | 10.67 | 0.4534% |  | 213.4 | 9.069%
| Miscellaneous | [6 empty] | 1642.6
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 21 | 44.2 | 19 | 63.2 | 1327.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 11 | 12.1 | 7.3 | 19.4 | 213.4 | Revise quantities based on the actual site | 10.45 | 202.73 | 95% | 0.55 | 10.67 | 5% | 11 | 213.4 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| Common Works | [6 empty] | 710.6
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
1.2 | Regional Polytechnic Institute Techo Sen Battambang (RPITSB) | [6 empty] | 46982.2 |  |  | 8225.066 | 17.51% |  | 4027.542 | 8.572% |  | 12252.608 | 26.08%
1.2.1 | A-TYPE | [6 empty] | 19084.76 |  |  | 2971.071 | 15.57% |  | 1699.262 | 8.904% |  | 4670.333 | 24.47%
A | Architectural Works | [6 empty] | 10218.46 |  |  | 1308.156 | 12.8% |  | 1176.792 | 11.52% |  | 2484.948 | 24.32%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 67 | 25.7 | 7.5 | 33.2 | 2224.4 |  | 29.48 | 978.736 | 44% | 13.4 | 444.88 | 20% | 42.88 | 1423.616 | 64%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 65.1 | 1.8 | 2.8 | 4.6 | 299.46 |  | 0 | 0 | 0% | 13.02 | 59.892 | 20% | 13.02 | 59.892 | 20%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 53.2 | 5 | 4 | 9 | 478.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 60 | 41.8 | 12.9 | 54.7 | 3282 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 26 | 4.3 | 3.6 | 7.9 | 205.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 60 | 7.5 | 4.5 | 12 | 720 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 67 | 22.6 | 7.6 | 30.2 | 2023.4 |  | 3.35 | 101.17 | 5% | 20.1 | 607.02 | 30% | 23.45 | 708.19 | 35%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse CPM Propose to paint on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0.65 | 100.75 | 65% | 0.2 | 31 | 20% | 0.85 | 131.75 | 85%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 10 | 11.3 | 5.7 | 17 | 170 | The existing security bars are in good condition, we propose repainting | 7.5 | 127.5 | 75% | 2 | 34 | 20% | 9.5 | 161.5 | 95%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 7327.7 |  |  | 1662.915 | 22.69% |  | 493.37 | 6.733% |  | 2156.285 | 29.43%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.3 | 383.28 | 30% | 0.1 | 127.76 | 10% | 0.4 | 511.04 | 40%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.35 | 592.55 | 35% | 0.1 | 169.3 | 10% | 0.45 | 761.85 | 45%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.35 | 687.085 | 35% | 0.1 | 196.31 | 10% | 0.45 | 883.395 | 45%
C | Miscellaneous and Common Work | [6 empty] | 1538.6 |  |  | 0 | 0% |  | 29.1 | 1.891% |  | 29.1 | 1.891%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 11 | 44.2 | 19 | 63.2 | 695.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 6 | 12.1 | 7.3 | 19.4 | 116.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 1.5 | 29.1 | 25% | 1.5 | 29.1 | 25%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
1.2.2 | B-TYPE | [6 empty] | 27897.44 |  |  | 5253.995 | 18.83% |  | 2328.28 | 8.346% |  | 7582.275 | 27.18%
A | Architectural Works | [6 empty] | 14813.74 |  |  | 3155.7 | 21.3% |  | 1551.7 | 10.47% |  | 4707.4 | 31.78%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 125 | 25.7 | 7.5 | 33.2 | 4150 |  | 68.75 | 2282.5 | 55% | 18.75 | 622.5 | 15% | 87.5 | 2905 | 70%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 81.9 | 1.8 | 2.8 | 4.6 | 376.74 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 67.9 | 5 | 4 | 9 | 611.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3' | - the brick counter and brick shelves shall be demolished and removed. - the existing grilled security bar shall be repaired by restoring it to its original design. - Any defective holes in the room shall also be repaired. | Sq.m | 1 | 0 | 400 | 400 | 400 |  | 0.95 | 380 | 95% | 0.05 | 20 | 5% | 1 | 400 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 47 | 41.8 | 12.9 | 54.7 | 2570.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 50 | 4.3 | 3.6 | 7.9 | 395 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 60 | 7.5 | 4.5 | 12 | 720 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 125 | 22.6 | 7.6 | 30.2 | 3775 |  | 0 | 0 | 0% | 25 | 755 | 20% | 25 | 755 | 20%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse CPM Propose to paint on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 3 | 120 | 35 | 155 | 465 |  | 1.8 | 279 | 60% | 0.6 | 93 | 20% | 2.4 | 372 | 80%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 18 | 11.3 | 5.7 | 17 | 306 | The existing security bars are in good condition, we propose repainting | 12.6 | 214.2 | 70% | 3.6 | 61.2 | 20% | 16.2 | 275.4 | 90%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 2098.295 | 19.21% |  | 733.9 | 6.721% |  | 2832.195 | 25.94%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.25 | 517.025 | 25% | 0.1 | 206.81 | 10% | 0.35 | 723.835 | 35%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.3 | 705.96 | 30% | 0.1 | 235.32 | 10% | 0.4 | 941.28 | 40%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.3 | 875.31 | 30% | 0.1 | 291.77 | 10% | 0.4 | 1167.08 | 40%
C | Miscellaneous and Common Work | [6 empty] | 2163.6 |  |  | 0 | 0% |  | 42.68 | 1.973% |  | 42.68 | 1.973%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 18 | 44.2 | 19 | 63.2 | 1137.6 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 11 | 12.1 | 7.3 | 19.4 | 213.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 2.2 | 42.68 | 20% | 2.2 | 42.68 | 20%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
2 | Banteay Meanchey Province | [6 empty] | 31930.6 |  |  | 16260.615 | 50.92% |  | 0 | 0% |  | 16260.615 | 50.92%
2.1 | Polytechnic Institute of Banteay Meanchey Province (PIBMC) | [6 empty] | 31930.6 |  |  | 16260.615 | 50.92% |  | 0 | 0% |  | 16260.615 | 50.92%
2.1.1 | A-TYPE | [6 empty] | 15110.9 |  |  | 6569.58 | 43.48% |  | 0 | 0% |  | 6569.58 | 43.48%
A | Architectural Works | [6 empty] | 6613.8 |  |  | 347.9 | 5.26% |  | 0 | 0% |  | 347.9 | 5.26%
Floor Finish
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 97 | 41.8 | 12.9 | 54.7 | 5305.9 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 80 | 7.5 | 4.5 | 12 | 960 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
Door Works
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 | Revise quantities based on the actual site | 7 | 347.9 | 100% | 0 | 0 | 0% | 7 | 347.9 | 100%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 5862.16 | 80% |  | 0 | 0% |  | 5862.16 | 80%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.8 | 1915.2 | 80% | 0 | 0 | 0% | 0.8 | 1915.2 | 80%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.8 | 1022.08 | 80% | 0 | 0 | 0% | 0.8 | 1022.08 | 80%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.8 | 1354.4 | 80% | 0 | 0 | 0% | 0.8 | 1354.4 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.8 | 1570.48 | 80% | 0 | 0 | 0% | 0.8 | 1570.48 | 80%
C | Miscellaneous and Common Work | [6 empty] | 1169.4 |  |  | 359.52 | 30.74% |  | 0 | 0% |  | 359.52 | 30.74%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 7 | 44.2 | 19 | 63.2 | 442.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0.8 | 359.52 | 80% | 0 | 0 | 0% | 0.8 | 359.52 | 80%
2.1.2 | B-TYPE | [6 empty] | 16819.7 |  |  | 9691.035 | 57.62% |  | 0 | 0% |  | 9691.035 | 57.62%
A | Architectural Works | [6 empty] | 4644.6 |  |  | 347.9 | 7.49% |  | 0 | 0% |  | 347.9 | 7.49%
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61 | 41.8 | 12.9 | 54.7 | 3336.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 80 | 7.5 | 4.5 | 12 | 960 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 | Revise quantities based on the actual site | 7 | 347.9 | 100% | 0 | 0 | 0% | 7 | 347.9 | 100%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 8915.135 | 81.64% |  | 0 | 0% |  | 8915.135 | 81.64%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.85 | 3043.935 | 85% | 0 | 0 | 0% | 0.85 | 3043.935 | 85%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.8 | 1654.48 | 80% | 0 | 0 | 0% | 0.8 | 1654.48 | 80%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.8 | 1882.56 | 80% | 0 | 0 | 0% | 0.8 | 1882.56 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.8 | 2334.16 | 80% | 0 | 0 | 0% | 0.8 | 2334.16 | 80%
C | Miscellaneous and Common Work | [6 empty] | 1255 |  |  | 428 | 34.1% |  | 0 | 0% |  | 428 | 34.1%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 7 | 44.2 | 19 | 63.2 | 442.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0.8 | 428 | 80% | 0 | 0 | 0% | 0.8 | 428 | 80%
3 | Pursat Province Province | [6 empty] | 33668.3 |  |  | 14751.769 | 43.82% |  | 0 | 0% |  | 14751.769 | 43.82%
3.1 | Polytechnic Institute of Pursat Province (PIPP) | [6 empty] | 33668.3 |  |  | 14751.769 | 43.82% |  | 0 | 0% |  | 14751.769 | 43.82%
3.1.1 | A-TYPE | [6 empty] | 15868.2 |  |  | 6032.714 | 38.02% |  | 0 | 0% |  | 6032.714 | 38.02%
A | Architectural Works | [6 empty] | 6739.1 |  |  | 347.9 | 5.162% |  | 0 | 0% |  | 347.9 | 5.162%
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 96 | 41.8 | 12.9 | 54.7 | 5251.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 95 | 7.5 | 4.5 | 12 | 1140 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 | Revise quantities based on the actual site | 7 | 347.9 | 100% | 0 | 0 | 0% | 7 | 347.9 | 100%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 5347.764 | 72.98% |  | 0 | 0% |  | 5347.764 | 72.98%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 | Omite as the existing AC is good conditon propose to clean | 0.75 | 1795.5 | 75% | 0 | 0 | 0% | 0.75 | 1795.5 | 75%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.72 | 919.872 | 72% | 0 | 0 | 0% | 0.72 | 919.872 | 72%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.72 | 1218.96 | 72% | 0 | 0 | 0% | 0.72 | 1218.96 | 72%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.72 | 1413.432 | 72% | 0 | 0 | 0% | 0.72 | 1413.432 | 72%
C | Miscellaneous and Common Work | [6 empty] | 1801.4 |  |  | 337.05 | 18.71% |  | 0 | 0% |  | 337.05 | 18.71%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 17 | 44.2 | 19 | 63.2 | 1074.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0.75 | 337.05 | 75% | 0 | 0 | 0% | 0.75 | 337.05 | 75%
3.1.2 | B-TYPE | [6 empty] | 17800.1 |  |  | 8719.055 | 48.98% |  | 0 | 0% |  | 8719.055 | 48.98%
A | Architectural Works | [6 empty] | 4803.4 |  |  | 347.9 | 7.243% |  | 0 | 0% |  | 347.9 | 7.243%
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 65 | 41.8 | 12.9 | 54.7 | 3555.5 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 |  | 7 | 347.9 | 100% | 0 | 0 | 0% | 7 | 347.9 | 100%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 7969.905 | 72.98% |  | 0 | 0% |  | 7969.905 | 72.98%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 | Omite as the existing AC is good conditon propose to clean | 0.75 | 2685.825 | 75% | 0 | 0 | 0% | 0.75 | 2685.825 | 75%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.72 | 1489.032 | 72% | 0 | 0 | 0% | 0.72 | 1489.032 | 72%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.72 | 1694.304 | 72% | 0 | 0 | 0% | 0.72 | 1694.304 | 72%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.72 | 2100.744 | 72% | 0 | 0 | 0% | 0.72 | 2100.744 | 72%
C | Miscellaneous and Common Work | [6 empty] | 2076.6 |  |  | 401.25 | 19.32% |  | 0 | 0% |  | 401.25 | 19.32%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 20 | 44.2 | 19 | 63.2 | 1264 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0.75 | 401.25 | 75% | 0 | 0 | 0% | 0.75 | 401.25 | 75%
4 | Kampong Thom Province | [6 empty] | 31281.4 |  |  | 16371.4 | 52.34% |  | 0 | 0% |  | 16371.4 | 52.34%
4.1 | Polytechnic Institute of Kampong Thom Province (PIKT) | [6 empty] | 31281.4 |  |  | 16371.4 | 52.34% |  | 0 | 0% |  | 16371.4 | 52.34%
4.1.1 | A-TTYPE | [6 empty] | 13718.6 |  |  | 6429.67 | 46.87% |  | 0 | 0% |  | 6429.67 | 46.87%
A | Architectural Works | [6 empty] | 5031.9 |  |  | 198.8 | 3.951% |  | 0 | 0% |  | 198.8 | 3.951%
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 73 | 41.8 | 12.9 | 54.7 | 3993.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 4 | 38.7 | 11 | 49.7 | 198.8 |  | 4 | 198.8 | 100% | 0 | 0 | 0% | 4 | 198.8 | 100%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 6230.87 | 85.03% |  | 0 | 0% |  | 6230.87 | 85.03%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 1 | 2394 | 100% | 0 | 0 | 0% | 1 | 2394 | 100%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 1 | 1277.6 | 100% | 0 | 0 | 0% | 1 | 1277.6 | 100%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.7 | 1185.1 | 70% | 0 | 0 | 0% | 0.7 | 1185.1 | 70%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.7 | 1374.17 | 70% | 0 | 0 | 0% | 0.7 | 1374.17 | 70%
C | Miscellaneous and Common Work | [6 empty] | 1359 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 10 | 44.2 | 19 | 63.2 | 632 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
4.1.2 | B-TYPE | [6 empty] | 17562.8 |  |  | 9941.73 | 56.61% |  | 0 | 0% |  | 9941.73 | 56.61%
A | Architectural Works | [6 empty] | 4566.1 |  |  | 602.9 | 13.2% |  | 0 | 0% |  | 602.9 | 13.2%
Floor Finish
Wall Finish
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 50 | 1.5 | 3.6 | 5.1 | 255 | There are some brick wall and the existing washing basin | 50 | 255 | 100% | 0 | 0 | 0% | 50 | 255 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 56 | 41.8 | 12.9 | 54.7 | 3063.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 |  | 7 | 347.9 | 100% | 0 | 0 | 0% | 7 | 347.9 | 100%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 9338.83 | 85.52% |  | 0 | 0% |  | 9338.83 | 85.52%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 1 | 3581.1 | 100% | 0 | 0 | 0% | 1 | 3581.1 | 100%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 1 | 2068.1 | 100% | 0 | 0 | 0% | 1 | 2068.1 | 100%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.7 | 1647.24 | 70% | 0 | 0 | 0% | 0.7 | 1647.24 | 70%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.7 | 2042.39 | 70% | 0 | 0 | 0% | 0.7 | 2042.39 | 70%
C | Miscellaneous and Common Work | [6 empty] | 2076.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 20 | 44.2 | 19 | 63.2 | 1264 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
5 | Siem Reap Province | [6 empty] | 67880.3 |  |  | 24708.2 | 36.4% |  | 4899.28 | 7.218% |  | 29607.48 | 43.62%
5.1 | National Polytechnic Institute of Angkor (NPIA) | [6 empty] | 40246.7 |  |  | 14302.1 | 35.54% |  | 2381.38 | 5.917% |  | 16683.48 | 41.45%
5.1.1 | A-TYPE | [6 empty] | 16311.1 |  |  | 5516.16 | 33.82% |  | 914.32 | 5.606% |  | 6430.48 | 39.42%
A | Architectural Works | [6 empty] | 7118.8 |  |  | 921.1 | 12.94% |  | 435.52 | 6.118% |  | 1356.62 | 19.06%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 61 | 2.6 | 1.8 | 4.4 | 268.4 |  | 0 | 0 | 0% | 49 | 215.6 | 80.33% | 49 | 215.6 | 80.33%
Wall Finish
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 49 | 5 | 4 | 9 | 441 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 49 | 41.8 | 12.9 | 54.7 | 2680.3 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 23 | 4.3 | 3.6 | 7.9 | 181.7 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 61 | 22.6 | 7.6 | 30.2 | 1842.2 | Revise quantities based on the actual site | 30.5 | 921.1 | 50% | 0 | 0 | 0% | 30.5 | 921.1 | 50%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0 | 0 | 0% | 0.1 | 49.92 | 10% | 0.1 | 49.92 | 10%
Window Works
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 18 | 11.3 | 5.7 | 17 | 306 | Revise quantities based on the actual site | 0 | 0 | 0% | 10 | 170 | 55.56% | 10 | 170 | 55.56%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 4595.06 | 62.71% |  | 478.8 | 6.534% |  | 5073.86 | 69.24%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.2 | 478.8 | 20% | 0.2 | 478.8 | 20% | 0.4 | 957.6 | 40%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.8 | 1022.08 | 80% | 0 | 0 | 0% | 0.8 | 1022.08 | 80%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.9 | 1523.7 | 90% | 0 | 0 | 0% | 0.9 | 1523.7 | 90%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.8 | 1570.48 | 80% | 0 | 0 | 0% | 0.8 | 1570.48 | 80%
C | Miscellaneous and Common Work | [6 empty] | 1864.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 18 | 44.2 | 19 | 63.2 | 1137.6 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
5.1.2 | B-TYPE | [6 empty] | 23935.6 |  |  | 8785.94 | 36.71% |  | 1467.06 | 6.129% |  | 10253 | 42.84%
A | Architectural Works | [6 empty] | 10180.5 |  |  | 1963.2 | 19.28% |  | 750.84 | 7.375% |  | 2714.04 | 26.66%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 113 | 2.6 | 1.8 | 4.4 | 497.2 |  | 0 | 0 | 0% | 90 | 396 | 79.65% | 90 | 396 | 79.65%
Wall Finish
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 66.5 | 5 | 4 | 9 | 598.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 40 | 204 | 100% | 0 | 0 | 0% | 40 | 204 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 47 | 41.8 | 12.9 | 54.7 | 2570.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 46.8228 | 4.3 | 3.6 | 7.9 | 369.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 113 | 22.6 | 7.6 | 30.2 | 3412.6 |  | 56 | 1691.2 | 49.56% | 0 | 0 | 0% | 56 | 1691.2 | 49.56%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 |  | 0 | 0 | 0% | 0.2 | 99.84 | 10% | 0.2 | 99.84 | 10%
Window Works
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 37 | 11.3 | 5.7 | 17 | 629 | Revise quantities based on the actual site | 4 | 68 | 10.81% | 15 | 255 | 40.54% | 19 | 323 | 51.35%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 6822.74 | 62.48% |  | 716.22 | 6.559% |  | 7538.96 | 69.04%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.2 | 716.22 | 20% | 0.2 | 716.22 | 20% | 0.4 | 1432.44 | 40%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.8 | 1654.48 | 80% | 0 | 0 | 0% | 0.8 | 1654.48 | 80%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.9 | 2117.88 | 90% | 0 | 0 | 0% | 0.9 | 2117.88 | 90%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.8 | 2334.16 | 80% | 0 | 0 | 0% | 0.8 | 2334.16 | 80%
C | Miscellaneous and Common Work | [6 empty] | 2835 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 32 | 44.2 | 19 | 63.2 | 2022.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
5.2 | Regional Polytechnic Institute Techo Sen Siem Reap (RPITSSR) | [6 empty] | 27633.6 |  |  | 10406.1 | 37.66% |  | 2517.9 | 9.112% |  | 12924 | 46.77%
5.2.1 | B-TYPE | [6 empty] | 27633.6 |  |  | 10406.1 | 37.66% |  | 2517.9 | 9.112% |  | 12924 | 46.77%
A | Architectural Works | [6 empty] | 14399.1 |  |  | 5069.4 | 35.21% |  | 1784 | 12.39% |  | 6853.4 | 47.6%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 125 | 25.7 | 7.5 | 33.2 | 4150 |  | 75 | 2490 | 60% | 40 | 1328 | 32% | 115 | 3818 | 92%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 101.5 | 1.8 | 2.8 | 4.6 | 466.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 81.9 | 5 | 4 | 9 | 737.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 40 | 204 | 100% | 0 | 0 | 0% | 40 | 204 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 47 | 41.8 | 12.9 | 54.7 | 2570.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 48 | 4.3 | 3.6 | 7.9 | 379.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 20 | 240 | 36.36% | 30 | 360 | 54.55% | 50 | 600 | 90.91%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 125 | 22.6 | 7.6 | 30.2 | 3775 |  | 62 | 1872.4 | 49.6% | 0 | 0 | 0% | 62 | 1872.4 | 49.6%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 2 | 120 | 35 | 155 | 310 |  | 0.6 | 93 | 30% | 0.4 | 62 | 20% | 1 | 155 | 50%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 18 | 11.3 | 5.7 | 17 | 306 | The existing security bars are in good condition, we propose repainting | 10 | 170 | 55.56% | 2 | 34 | 11.11% | 12 | 204 | 66.67%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 5162.1 | 47.27% |  | 733.9 | 6.721% |  | 5896 | 53.99%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.2 | 716.22 | 20% | 0 | 0 | 0% | 0.2 | 716.22 | 20%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.55 | 1137.455 | 55% | 0.1 | 206.81 | 10% | 0.65 | 1344.265 | 65%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.6 | 1411.92 | 60% | 0.1 | 235.32 | 10% | 0.7 | 1647.24 | 70%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.65 | 1896.505 | 65% | 0.1 | 291.77 | 10% | 0.75 | 2188.275 | 75%
C | Miscellaneous and Common Work | [6 empty] | 2314.4 |  |  | 174.6 | 7.544% |  | 0 | 0% |  | 174.6 | 7.544%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 21 | 44.2 | 19 | 63.2 | 1327.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 9 | 12.1 | 7.3 | 19.4 | 174.6 | Revise quantities based on the actual site | 9 | 174.6 | 100% | 0 | 0 | 0% | 9 | 174.6 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6 | Phnom Penh | [6 empty] | 324850.24 |  |  | 96167.4 | 29.6% |  | 11544.815 | 3.554% |  | 107712.215 | 33.16%
6.1 | National Polytechnic Institute of Cambodia (NPIC) | [6 empty] | 42963.12 |  |  | 0 | 0% |  | 268 | 0.6238% |  | 268 | 0.6238%
6.1.1 | A-TYPE | [6 empty] | 12978.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 7317.9 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 122 | 2.6 | 1.8 | 4.4 | 536.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 113 | 41.8 | 12.9 | 54.7 | 6181.1 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 50 | 7.5 | 4.5 | 12 | 600 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 0 | 19.3 | 4.3 | 23.6 | 0 | The existing ceilling is good condition can be reuse
B | Electrical Works | [6 empty] | 4933.7 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 727 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 0 | 44.2 | 19 | 63.2 | 0 | Revise quantities based on the actual site
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 0 | 12.1 | 7.3 | 19.4 | 0 | No ventilation block is exposed within the interior wall
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.1.2 | B-TYPE | [6 empty] | 29984.52 |  |  | 0 | 0% |  | 268 | 0.8938% |  | 268 | 0.8938%
A | Architectural Works | [6 empty] | 16599.22 |  |  | 0 | 0% |  | 268 | 1.615% |  | 268 | 1.615%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 136 | 25.7 | 7.5 | 33.2 | 4515.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 88.2 | 1.8 | 2.8 | 4.6 | 405.72 |  | 0 | 0 | 0% | 25 | 115 | 28.34% | 25 | 115 | 28.34%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 79.1 | 5 | 4 | 9 | 711.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 0 | 0 | 0% | 30 | 153 | 75% | 30 | 153 | 75%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 53 | 41.8 | 12.9 | 54.7 | 2899.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 49 | 4.3 | 3.6 | 7.9 | 387.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 136 | 22.6 | 7.6 | 30.2 | 4107.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 5 | 11.3 | 5.7 | 17 | 85 | The existing security bars are in good condition, we propose repainting | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2465.2 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 24 | 44.2 | 19 | 63.2 | 1516.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 7 | 12.1 | 7.3 | 19.4 | 135.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2 | National Technical Training Institute (NTTI) | [6 empty] | 254498.06 |  |  | 73727.52 | 28.97% |  | 8803.11 | 3.459% |  | 82530.63 | 32.43%
6.2.1 | A-TYPE-1 | [6 empty] | 20828.66 |  |  | 12224.59 | 58.69% |  | 1487.02 | 7.139% |  | 13711.61 | 65.83%
A | Architectural Works | [6 empty] | 11792.16 |  |  | 6514.53 | 55.24% |  | 1359.26 | 11.53% |  | 7873.79 | 66.77%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 72 | 25.7 | 7.5 | 33.2 | 2390.4 |  | 64.8 | 2151.36 | 90% | 0 | 0 | 0% | 64.8 | 2151.36 | 90%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 65.1 | 1.8 | 2.8 | 4.6 | 299.46 |  | 65.1 | 299.46 | 100% | 0 | 0 | 0% | 65.1 | 299.46 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 52.5 | 5 | 4 | 9 | 472.5 |  | 47.25 | 425.25 | 90% | 0 | 0 | 0% | 47.25 | 425.25 | 90%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61 | 41.8 | 12.9 | 54.7 | 3336.7 |  | 0 | 0 | 0% | 18.3 | 1001.01 | 30% | 18.3 | 1001.01 | 30%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 26 | 4.3 | 3.6 | 7.9 | 205.4 |  | 23.4 | 184.86 | 90% | 0 | 0 | 0% | 23.4 | 184.86 | 90%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 45 | 540 | 90% | 0 | 0 | 0% | 45 | 540 | 90%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 19.5 | 234 | 30% | 19.5 | 234 | 30%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 72 | 22.6 | 7.6 | 30.2 | 2174.4 |  | 64.8 | 1956.96 | 90% | 0 | 0 | 0% | 64.8 | 1956.96 | 90%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0.5 | 249.6 | 50% | 0 | 0 | 0% | 0.5 | 249.6 | 50%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 3.6 | 707.04 | 90% | 0 | 0 | 0% | 3.6 | 707.04 | 90%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 2.5 | 124.25 | 50% | 2.5 | 124.25 | 50%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 5622.76 | 76.73% |  | 127.76 | 1.744% |  | 5750.52 | 78.48%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.7 | 1675.8 | 70% | 0 | 0 | 0% | 0.7 | 1675.8 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.8 | 1022.08 | 80% | 0.1 | 127.76 | 10% | 0.9 | 1149.84 | 90%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.8 | 1354.4 | 80% | 0 | 0 | 0% | 0.8 | 1354.4 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.8 | 1570.48 | 80% | 0 | 0 | 0% | 0.8 | 1570.48 | 80%
C | Miscellaneous and Common Work | [6 empty] | 1708.8 |  |  | 87.3 | 5.109% |  | 0 | 0% |  | 87.3 | 5.109%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 5 | 12.1 | 7.3 | 19.4 | 97 |  | 4.5 | 87.3 | 90% | 0 | 0 | 0% | 4.5 | 87.3 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.2 | A-TYPE-2 | [6 empty] | 20842.86 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 11806.36 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 72 | 25.7 | 7.5 | 33.2 | 2390.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 65.1 | 1.8 | 2.8 | 4.6 | 299.46 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 53.2 | 5 | 4 | 9 | 478.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61 | 41.8 | 12.9 | 54.7 | 3336.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 27 | 4.3 | 3.6 | 7.9 | 213.3 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 72 | 22.6 | 7.6 | 30.2 | 2174.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1708.8 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 5 | 12.1 | 7.3 | 19.4 | 97 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.3 | A-TYPE-3 | [6 empty] | 20049.24 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 11367.54 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 75 | 25.7 | 7.5 | 33.2 | 2490 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 71.4 | 1.8 | 2.8 | 4.6 | 328.44 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 56.7 | 5 | 4 | 9 | 510.3 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 66 | 41.8 | 12.9 | 54.7 | 3610.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 36 | 4.3 | 3.6 | 7.9 | 284.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 75 | 22.6 | 7.6 | 30.2 | 2265 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is in good condition and will be retained
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0 | Omitted, as there is no window on the corridor side.
B | Electrical Works | [6 empty] | 7327.7 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1354 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 9 | 44.2 | 19 | 63.2 | 568.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 3 | 12.1 | 7.3 | 19.4 | 58.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.4 | A-TYPE-4 | [6 empty] | 20717.64 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 11681.14 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 72 | 25.7 | 7.5 | 33.2 | 2390.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 64.4 | 1.8 | 2.8 | 4.6 | 296.24 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 51.8 | 5 | 4 | 9 | 466.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 59 | 41.8 | 12.9 | 54.7 | 3227.3 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 27 | 4.3 | 3.6 | 7.9 | 213.3 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 72 | 22.6 | 7.6 | 30.2 | 2174.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1708.8 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 5 | 12.1 | 7.3 | 19.4 | 97 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.5 | A-TYPE-5 | [6 empty] | 20821.36 |  |  | 12267.25 | 58.92% |  | 1470.61 | 7.063% |  | 13737.86 | 65.98%
A | Architectural Works | [6 empty] | 11784.86 |  |  | 6557.19 | 55.64% |  | 1342.85 | 11.39% |  | 7900.04 | 67.04%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 72 | 25.7 | 7.5 | 33.2 | 2390.4 |  | 64.8 | 2151.36 | 90% | 0 | 0 | 0% | 64.8 | 2151.36 | 90%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 65.1 | 1.8 | 2.8 | 4.6 | 299.46 |  | 65.1 | 299.46 | 100% | 0 | 0 | 0% | 65.1 | 299.46 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 52.5 | 5 | 4 | 9 | 472.5 |  | 47.25 | 425.25 | 90% | 0 | 0 | 0% | 47.25 | 425.25 | 90%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 60 | 41.8 | 12.9 | 54.7 | 3282 |  | 0 | 0 | 0% | 18 | 984.6 | 30% | 18 | 984.6 | 30%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 32 | 4.3 | 3.6 | 7.9 | 252.8 |  | 28.8 | 227.52 | 90% | 0 | 0 | 0% | 28.8 | 227.52 | 90%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 45 | 540 | 90% | 0 | 0 | 0% | 45 | 540 | 90%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 19.5 | 234 | 30% | 19.5 | 234 | 30%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 72 | 22.6 | 7.6 | 30.2 | 2174.4 |  | 64.8 | 1956.96 | 90% | 0 | 0 | 0% | 64.8 | 1956.96 | 90%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0.5 | 249.6 | 50% | 0 | 0 | 0% | 0.5 | 249.6 | 50%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 3.6 | 707.04 | 90% | 0 | 0 | 0% | 3.6 | 707.04 | 90%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 2.5 | 124.25 | 50% | 2.5 | 124.25 | 50%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 5622.76 | 76.73% |  | 127.76 | 1.744% |  | 5750.52 | 78.48%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.7 | 1675.8 | 70% | 0 | 0 | 0% | 0.7 | 1675.8 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.8 | 1022.08 | 80% | 0.1 | 127.76 | 10% | 0.9 | 1149.84 | 90%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.8 | 1354.4 | 80% | 0 | 0 | 0% | 0.8 | 1354.4 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.8 | 1570.48 | 80% | 0 | 0 | 0% | 0.8 | 1570.48 | 80%
C | Miscellaneous and Common Work | [6 empty] | 1708.8 |  |  | 87.3 | 5.109% |  | 0 | 0% |  | 87.3 | 5.109%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 5 | 12.1 | 7.3 | 19.4 | 97 |  | 4.5 | 87.3 | 90% | 0 | 0 | 0% | 4.5 | 87.3 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.6 | A-TYPE-6 | [6 empty] | 20842.86 |  |  | 12237.37 | 58.71% |  | 1487.02 | 7.134% |  | 13724.39 | 65.85%
A | Architectural Works | [6 empty] | 11806.36 |  |  | 6527.31 | 55.29% |  | 1359.26 | 11.51% |  | 7886.57 | 66.8%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 72 | 25.7 | 7.5 | 33.2 | 2390.4 |  | 64.8 | 2151.36 | 90% | 0 | 0 | 0% | 64.8 | 2151.36 | 90%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 65.1 | 1.8 | 2.8 | 4.6 | 299.46 |  | 65.1 | 299.46 | 100% | 0 | 0 | 0% | 65.1 | 299.46 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 53.2 | 5 | 4 | 9 | 478.8 |  | 47.88 | 430.92 | 90% | 0 | 0 | 0% | 47.88 | 430.92 | 90%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61 | 41.8 | 12.9 | 54.7 | 3336.7 |  | 0 | 0 | 0% | 18.3 | 1001.01 | 30% | 18.3 | 1001.01 | 30%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 27 | 4.3 | 3.6 | 7.9 | 213.3 |  | 24.3 | 191.97 | 90% | 0 | 0 | 0% | 24.3 | 191.97 | 90%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 45 | 540 | 90% | 0 | 0 | 0% | 45 | 540 | 90%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 19.5 | 234 | 30% | 19.5 | 234 | 30%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 72 | 22.6 | 7.6 | 30.2 | 2174.4 |  | 64.8 | 1956.96 | 90% | 0 | 0 | 0% | 64.8 | 1956.96 | 90%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 |  | 0.5 | 249.6 | 50% | 0 | 0 | 0% | 0.5 | 249.6 | 50%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 3.6 | 707.04 | 90% | 0 | 0 | 0% | 3.6 | 707.04 | 90%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 2.5 | 124.25 | 50% | 2.5 | 124.25 | 50%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 5622.76 | 76.73% |  | 127.76 | 1.744% |  | 5750.52 | 78.48%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.7 | 1675.8 | 70% | 0 | 0 | 0% | 0.7 | 1675.8 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.8 | 1022.08 | 80% | 0.1 | 127.76 | 10% | 0.9 | 1149.84 | 90%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.8 | 1354.4 | 80% | 0 | 0 | 0% | 0.8 | 1354.4 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.8 | 1570.48 | 80% | 0 | 0 | 0% | 0.8 | 1570.48 | 80%
C | Miscellaneous and Common Work | [6 empty] | 1708.8 |  |  | 87.3 | 5.109% |  | 0 | 0% |  | 87.3 | 5.109%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 5 | 12.1 | 7.3 | 19.4 | 97 |  | 4.5 | 87.3 | 90% | 0 | 0 | 0% | 4.5 | 87.3 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.7 | B-TYPE-1 | [6 empty] | 30283.16 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 17004.86 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 140 | 25.7 | 7.5 | 33.2 | 4648 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 100.1 | 1.8 | 2.8 | 4.6 | 460.46 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 80.5 | 5 | 4 | 9 | 724.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 55 | 41.8 | 12.9 | 54.7 | 3008.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 51 | 4.3 | 3.6 | 7.9 | 402.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 140 | 22.6 | 7.6 | 30.2 | 4228 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2358.2 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 22 | 44.2 | 19 | 63.2 | 1390.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 8 | 12.1 | 7.3 | 19.4 | 155.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.8 | B-TYPE-2 | [6 empty] | 30322.66 |  |  | 19816.96 | 65.35% |  | 1485.61 | 4.899% |  | 21302.57 | 70.25%
A | Architectural Works | [6 empty] | 17044.36 |  |  | 11299.31 | 66.29% |  | 1278.8 | 7.503% |  | 12578.11 | 73.8%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 140 | 25.7 | 7.5 | 33.2 | 4648 |  | 126 | 4183.2 | 90% | 0 | 0 | 0% | 126 | 4183.2 | 90%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 100.1 | 1.8 | 2.8 | 4.6 | 460.46 |  | 100.1 | 460.46 | 100% | 0 | 0 | 0% | 100.1 | 460.46 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 80.5 | 5 | 4 | 9 | 724.5 |  | 72.45 | 652.05 | 90% | 0 | 0 | 0% | 72.45 | 652.05 | 90%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 55 | 41.8 | 12.9 | 54.7 | 3008.5 |  | 0 | 0 | 0% | 16.5 | 902.55 | 30% | 16.5 | 902.55 | 30%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 56 | 4.3 | 3.6 | 7.9 | 442.4 |  | 50.4 | 398.16 | 90% | 0 | 0 | 0% | 50.4 | 398.16 | 90%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 49.5 | 594 | 90% | 0 | 0 | 0% | 49.5 | 594 | 90%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 21 | 252 | 30% | 21 | 252 | 30%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 140 | 22.6 | 7.6 | 30.2 | 4228 |  | 126 | 3805.2 | 90% | 0 | 0 | 0% | 126 | 3805.2 | 90%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 |  | 1 | 499.2 | 50% | 0 | 0 | 0% | 1 | 499.2 | 50%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 3.6 | 707.04 | 90% | 0 | 0 | 0% | 3.6 | 707.04 | 90%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 2.5 | 124.25 | 50% | 2.5 | 124.25 | 50%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 8377.97 | 76.72% |  | 206.81 | 1.894% |  | 8584.78 | 78.61%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.7 | 2506.77 | 70% | 0 | 0 | 0% | 0.7 | 2506.77 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.8 | 1654.48 | 80% | 0.1 | 206.81 | 10% | 0.9 | 1861.29 | 90%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.8 | 1882.56 | 80% | 0 | 0 | 0% | 0.8 | 1882.56 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.8 | 2334.16 | 80% | 0 | 0 | 0% | 0.8 | 2334.16 | 80%
C | Miscellaneous and Common Work | [6 empty] | 2358.2 |  |  | 139.68 | 5.923% |  | 0 | 0% |  | 139.68 | 5.923%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 22 | 44.2 | 19 | 63.2 | 1390.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 8 | 12.1 | 7.3 | 19.4 | 155.2 | Revise quantities based on the actual site | 7.2 | 139.68 | 90% | 0 | 0 | 0% | 7.2 | 139.68 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.9 | B-TYPE-3 (Capstone Design Room) | [6 empty] | 35452.66 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 22174.36 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 140 | 25.7 | 7.5 | 33.2 | 4648 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 100.1 | 1.8 | 2.8 | 4.6 | 460.46 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 80.5 | 5 | 4 | 9 | 724.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 51 | 4.3 | 3.6 | 7.9 | 402.9 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W7 | - Glass partition thk. 10 tempered glass / Opaque Non-Adhessive film with aluminum bar (50x100) | Sq.m | 108 | 72.8 | 10.7 | 83.5 | 9018 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 140 | 22.6 | 7.6 | 30.2 | 4228 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2358.2 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 22 | 44.2 | 19 | 63.2 | 1390.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 8 | 12.1 | 7.3 | 19.4 | 155.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.2.10 | B-TYPE-4 (Multimedia Conference Room) | [6 empty] | 34336.96 |  |  | 17181.35 | 50.04% |  | 2872.85 | 8.367% |  | 20054.2 | 58.4%
A | Architectural Works | [6 empty] | 21058.66 |  |  | 8870.51 | 42.12% |  | 2666.04 | 12.66% |  | 11536.55 | 54.78%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 140 | 25.7 | 7.5 | 33.2 | 4648 |  | 126 | 4183.2 | 90% | 0 | 0 | 0% | 126 | 4183.2 | 90%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 100.1 | 1.8 | 2.8 | 4.6 | 460.46 |  | 100.1 | 460.46 | 100% | 0 | 0 | 0% | 100.1 | 460.46 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 80.5 | 5 | 4 | 9 | 724.5 |  | 72.45 | 652.05 | 90% | 0 | 0 | 0% | 72.45 | 652.05 | 90%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 124 | 41.8 | 12.9 | 54.7 | 6782.8 |  | 0 | 0 | 0% | 37.2 | 2034.84 | 30% | 37.2 | 2034.84 | 30%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 56 | 4.3 | 3.6 | 7.9 | 442.4 |  | 50.4 | 398.16 | 90% | 0 | 0 | 0% | 50.4 | 398.16 | 90%
| S1 | - Porcelain tile thk12, H=120mm | m | 65 | 7.5 | 4.5 | 12 | 780 | New skirting in all rooms where the new floor tile (F2) is installed | 58.5 | 702 | 90% | 0 | 0 | 0% | 58.5 | 702 | 90%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 80 | 7.5 | 4.5 | 12 | 960 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 24 | 288 | 30% | 24 | 288 | 30%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 140 | 22.6 | 7.6 | 30.2 | 4228 |  | 42 | 1268.4 | 30% | 7.25 | 218.95 | 5.179% | 49.25 | 1487.35 | 35.18%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 |  | 1 | 499.2 | 50% | 0 | 0 | 0% | 1 | 499.2 | 50%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 4 | 166.4 | 30 | 196.4 | 785.6 | The existing window at the backside is in good condition and will be retained; only the corridor-side window will be changed. | 3.6 | 707.04 | 90% | 0 | 0 | 0% | 3.6 | 707.04 | 90%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 5 | 38.7 | 11 | 49.7 | 248.5 |  | 0 | 0 | 0% | 2.5 | 124.25 | 50% | 2.5 | 124.25 | 50%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 8171.16 | 74.83% |  | 206.81 | 1.894% |  | 8377.97 | 76.72%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.7 | 2506.77 | 70% | 0 | 0 | 0% | 0.7 | 2506.77 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.7 | 1447.67 | 70% | 0.1 | 206.81 | 10% | 0.8 | 1654.48 | 80%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.8 | 1882.56 | 80% | 0 | 0 | 0% | 0.8 | 1882.56 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.8 | 2334.16 | 80% | 0 | 0 | 0% | 0.8 | 2334.16 | 80%
C | Miscellaneous and Common Work | [6 empty] | 2358.2 |  |  | 139.68 | 5.923% |  | 0 | 0% |  | 139.68 | 5.923%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 22 | 44.2 | 19 | 63.2 | 1390.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 8 | 12.1 | 7.3 | 19.4 | 155.2 | Revise quantities based on the actual site | 7.2 | 139.68 | 90% | 0 | 0 | 0% | 7.2 | 139.68 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
6.3 | National Institute of Business (NIB) | [6 empty] | 27389.06 |  |  | 22439.88 | 81.93% |  | 2473.705 | 9.032% |  | 24913.585 | 90.96%
6.3.1 | B-TYPE | [6 empty] | 27389.06 |  |  | 22439.88 | 81.93% |  | 2473.705 | 9.032% |  | 24913.585 | 90.96%
A | Architectural Works | [6 empty] | 14839.76 |  |  | 12153.47 | 81.9% |  | 1927.7 | 12.99% |  | 14081.17 | 94.89%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 0 | 2.6 | 1.8 | 4.4 | 0 | - Based on the site inspection, the teacher requested to change the room from A5.2 to A5.1. - The existing room has a raised floor, which needs to be removed and replaced with F2.
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 95 | 25.7 | 7.5 | 33.2 | 3154 |  | 95 | 3154 | 100% | 0 | 0 | 0% | 95 | 3154 | 100%
| F3 | - Demolish raised cement floor ~ 0.30m | Sq.m | 45 | 0 | 20 | 20 | 900 |  | 45 | 900 | 100% | 0 | 0 | 0% | 45 | 900 | 100%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 79.1 | 1.8 | 2.8 | 4.6 | 363.86 | Revise quantities based on the actual site | 79.1 | 363.86 | 100% | 0 | 0 | 0% | 79.1 | 363.86 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 62.3 | 5 | 4 | 9 | 560.7 |  | 62.3 | 560.7 | 100% | 0 | 0 | 0% | 62.3 | 560.7 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 47 | 41.8 | 12.9 | 54.7 | 2570.9 |  | 23.5 | 1285.45 | 50% | 19 | 1039.3 | 40.43% | 42.5 | 2324.75 | 90.43%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 41 | 4.3 | 3.6 | 7.9 | 323.9 |  | 25 | 197.5 | 60.98% | 6 | 47.4 | 14.63% | 31 | 244.9 | 75.61%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 55 | 660 | 100% | 0 | 0 | 0% | 55 | 660 | 100%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 63 | 756 | 90% | 63 | 756 | 90%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 91 | 22.6 | 7.6 | 30.2 | 2748.2 |  | 91 | 2748.2 | 100% | 0 | 0 | 0% | 91 | 2748.2 | 100%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 1 | 428 | 71.2 | 499.2 | 499.2 | Revise quantities based on the actual site | 0.3 | 149.76 | 30% | 0 | 0 | 0% | 0.3 | 149.76 | 30%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 10 | 166.4 | 30 | 196.4 | 1964 |  | 10 | 1964 | 100% | 0 | 0 | 0% | 10 | 1964 | 100%
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 15 | 11.3 | 5.7 | 17 | 255 | The existing security bars along the corridor are in good condition; replacement is not required. CPM propose to change to WD2 | 10 | 170 | 66.67% | 5 | 85 | 33.33% | 15 | 255 | 100%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 10228.21 | 93.66% |  | 546.005 | 5% |  | 10774.215 | 98.66%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.95 | 3402.045 | 95% | 0.05 | 179.055 | 5% | 1 | 3581.1 | 100%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.95 | 1964.695 | 95% | 0.05 | 103.405 | 5% | 1 | 2068.1 | 100%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.95 | 2235.54 | 95% | 0.05 | 117.66 | 5% | 1 | 2353.2 | 100%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.9 | 2625.93 | 90% | 0.05 | 145.885 | 5% | 0.95 | 2771.815 | 95%
C | Miscellaneous and Common Work | [6 empty] | 1629.2 |  |  | 58.2 | 3.572% |  | 0 | 0% |  | 58.2 | 3.572%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 12 | 44.2 | 19 | 63.2 | 758.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 3 | 12.1 | 7.3 | 19.4 | 58.2 | Revise quantities based on the actual site | 3 | 58.2 | 100% | 0 | 0 | 0% | 3 | 58.2 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
7 | Kandal Province | [6 empty] | 37682.58 |  |  | 9391.65 | 24.92% |  | 2087.72 | 5.54% |  | 11479.37 | 30.46%
7.1 | National Polytechnic Institute of Techo Sen (NPIT) | [6 empty] | 37682.58 |  |  | 9391.65 | 24.92% |  | 2087.72 | 5.54% |  | 11479.37 | 30.46%
7.1.1 | A-TYPE | [6 empty] | 17195.74 |  |  | 3833.87 | 22.3% |  | 844.41 | 4.911% |  | 4678.28 | 27.21%
A | Architectural Works | [6 empty] | 7823.84 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 84 | 2.6 | 1.8 | 4.4 | 369.6 | The existing Floor tile is good condition can be reuse CPM Propose to clean it | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 0 | 25.7 | 7.5 | 33.2 | 0
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 74.9 | 1.8 | 2.8 | 4.6 | 344.54 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 74.9 | 5 | 4 | 9 | 674.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 90 | 41.8 | 12.9 | 54.7 | 4923 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 80 | 7.5 | 4.5 | 12 | 960 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 0 | 19.3 | 4.3 | 23.6 | 0 | The existing ceilling is good condition can be reuse
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 8 | 38.7 | 11 | 49.7 | 397.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 3756.27 | 51.26% |  | 844.41 | 11.52% |  | 4600.68 | 62.78%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.5 | 1197 | 50% | 0.2 | 478.8 | 20% | 0.7 | 1675.8 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.7 | 1185.1 | 70% | 0.1 | 169.3 | 10% | 0.8 | 1354.4 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.7 | 1374.17 | 70% | 0.1 | 196.31 | 10% | 0.8 | 1570.48 | 80%
C | Miscellaneous and Common Work | [6 empty] | 2044.2 |  |  | 77.6 | 3.796% |  | 0 | 0% |  | 77.6 | 3.796%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 19 | 44.2 | 19 | 63.2 | 1200.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 6 | 12.1 | 7.3 | 19.4 | 116.4 | Revise quantities based on the actual site | 4 | 77.6 | 66.67% | 0 | 0 | 0% | 4 | 77.6 | 66.67%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
7.1.2 | B-TYPE | [6 empty] | 20486.84 |  |  | 5557.78 | 27.13% |  | 1243.31 | 6.069% |  | 6801.09 | 33.2%
A | Architectural Works | [6 empty] | 7417.54 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 126 | 2.6 | 1.8 | 4.4 | 554.4 | The existing Floor tile is good condition can be reuse CPM Propose to clean it | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 0 | 25.7 | 7.5 | 33.2 | 0
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 99.4 | 1.8 | 2.8 | 4.6 | 457.24 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 99.4 | 5 | 4 | 9 | 894.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 75 | 41.8 | 12.9 | 54.7 | 4102.5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 0 | 19.3 | 4.3 | 23.6 | 0 | The existing ceilling is good condition can be reuse
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 2 | 120 | 35 | 155 | 310 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 4 | 38.7 | 11 | 49.7 | 198.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 5480.18 | 50.18% |  | 1243.31 | 11.39% |  | 6723.49 | 61.57%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.5 | 1790.55 | 50% | 0.2 | 716.22 | 20% | 0.7 | 2506.77 | 70%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.7 | 1647.24 | 70% | 0.1 | 235.32 | 10% | 0.8 | 1882.56 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.7 | 2042.39 | 70% | 0.1 | 291.77 | 10% | 0.8 | 2334.16 | 80%
C | Miscellaneous and Common Work | [6 empty] | 2149.2 |  |  | 77.6 | 3.611% |  | 0 | 0% |  | 77.6 | 3.611%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 19 | 44.2 | 19 | 63.2 | 1200.8 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 7 | 12.1 | 7.3 | 19.4 | 135.8 |  | 4 | 77.6 | 57.14% | 0 | 0 | 0% | 4 | 77.6 | 57.14%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
8 | Takeo Province | [6 empty] | 25269.8 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
8.1 | Regional Polytechnic Institute Techo Sen Takeo (RPITST) | [6 empty] | 25269.8 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
8.1.1 | A-TYPE | [6 empty] | 11269.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 4976.9 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 74 | 41.8 | 12.9 | 54.7 | 4047.8 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 0 | 19.3 | 4.3 | 23.6 | 0 | The existing ceiling is good condition can be reuse
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 3 | 38.7 | 11 | 49.7 | 149.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 4933.7 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1359 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 10 | 44.2 | 19 | 63.2 | 632 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
8.1.2 | B-TYPE | [6 empty] | 14000.2 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
A | Architectural Works | [6 empty] | 4584.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Floor Finish
Wall Finish
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61 | 41.8 | 12.9 | 54.7 | 3336.7 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 0 | 19.3 | 4.3 | 23.6 | 0 | The existing ceiling is good conditon
Door Works
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 7339 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2076.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 20 | 44.2 | 19 | 63.2 | 1264 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
9 | Svay Rieng Province | [6 empty] | 47348.06 |  |  | 0 | 0% |  | 322 | 0.6801% |  | 322 | 0.6801%
9.1 | Regional Polytechnic Institute Techo Sen Svay Rieng (RPITSSR) | [6 empty] | 47348.06 |  |  | 0 | 0% |  | 322 | 0.6801% |  | 322 | 0.6801%
9.1.1 | A-TYPE | [6 empty] | 19038.14 |  |  | 0 | 0% |  | 138 | 0.7249% |  | 138 | 0.7249%
A | Architectural Works | [6 empty] | 10171.84 |  |  | 0 | 0% |  | 138 | 1.357% |  | 138 | 1.357%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 68 | 25.7 | 7.5 | 33.2 | 2257.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 74.9 | 1.8 | 2.8 | 4.6 | 344.54 |  | 0 | 0 | 0% | 30 | 138 | 40.05% | 30 | 138 | 40.05%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 54.6 | 5 | 4 | 9 | 491.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 61 | 41.8 | 12.9 | 54.7 | 3336.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 68 | 22.6 | 7.6 | 30.2 | 2053.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 9 | 11.3 | 5.7 | 17 | 153 | The existing security bars are in good condition, we propose repainting | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 7327.7 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1538.6 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 11 | 44.2 | 19 | 63.2 | 695.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 6 | 12.1 | 7.3 | 19.4 | 116.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
9.1.2 | B-TYPE | [6 empty] | 28309.92 |  |  | 0 | 0% |  | 184 | 0.6499% |  | 184 | 0.6499%
A | Architectural Works | [6 empty] | 14978.42 |  |  | 0 | 0% |  | 184 | 1.228% |  | 184 | 1.228%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 133 | 25.7 | 7.5 | 33.2 | 4415.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 112.7 | 1.8 | 2.8 | 4.6 | 518.42 |  | 0 | 0 | 0% | 40 | 184 | 35.49% | 40 | 184 | 35.49%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 82.6 | 5 | 4 | 9 | 743.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 52 | 41.8 | 12.9 | 54.7 | 2844.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The external paint is good conditon
| S1 | - Porcelain tile thk12, H=120mm | m | 60 | 7.5 | 4.5 | 12 | 720 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 133 | 22.6 | 7.6 | 30.2 | 4016.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 2 | 120 | 35 | 155 | 310 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 18 | 11.3 | 5.7 | 17 | 306 | The existing security bars are in good condition, we propose repainting | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2411.4 |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 21 | 44.2 | 19 | 63.2 | 1327.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 14 | 12.1 | 7.3 | 19.4 | 271.6 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
10 | Preah Sihanouk | [6 empty] | 88034 |  |  | 45610.493 | 51.81% |  | 0 | 0% |  | 45610.493 | 51.81%
10.1 | Preah Sihanouk Cambodia China Friendship Polytechnic Institute (PCCFPI) | [6 empty] | 42129.7 |  |  | 18619.078 | 44.19% |  | 0 | 0% |  | 18619.078 | 44.19%
10.1.1 | A-TYPE | [6 empty] | 17140.98 |  |  | 7027.163 | 41% |  | 0 | 0% |  | 7027.163 | 41%
A | Architectural Works | [6 empty] | 8201.48 |  |  | 3172.433 | 38.68% |  | 0 | 0% |  | 3172.433 | 38.68%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 61 | 2.6 | 1.8 | 4.4 | 268.4 |  | 54.9 | 241.56 | 90% | 0 | 0 | 0% | 54.9 | 241.56 | 90%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 74.2 | 1.8 | 2.8 | 4.6 | 341.32 |  | 74.2 | 341.32 | 100% | 0 | 0 | 0% | 74.2 | 341.32 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 74.2 | 5 | 4 | 9 | 667.8 |  | 74.2 | 667.8 | 100% | 0 | 0 | 0% | 74.2 | 667.8 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 81.9335 | 41.8 | 12.9 | 54.7 | 4481.76 |  | 8.19 | 447.993 | 9.996% | 0 | 0 | 0% | 8.19 | 447.993 | 9.996%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 50 | 7.5 | 4.5 | 12 | 600 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 0 | 19.3 | 4.3 | 23.6 | 0 | There have no existing ceiling CPM proposes to install C2 instead.
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 61 | 22.6 | 7.6 | 30.2 | 1842.2 |  | 48.8 | 1473.76 | 80% | 0 | 0 | 0% | 48.8 | 1473.76 | 80%
B | Electrical Works | [6 empty] | 7327.7 |  |  | 3722.01 | 50.79% |  | 0 | 0% |  | 3722.01 | 50.79%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.5 | 1197 | 50% | 0 | 0 | 0% | 0.5 | 1197 | 50%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.85 | 1085.96 | 85% | 0 | 0 | 0% | 0.85 | 1085.96 | 85%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.85 | 1439.05 | 85% | 0 | 0 | 0% | 0.85 | 1439.05 | 85%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1611.8 |  |  | 132.72 | 8.234% |  | 0 | 0% |  | 132.72 | 8.234%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 2.1 | 132.72 | 15% | 0 | 0 | 0% | 2.1 | 132.72 | 15%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
10.1.2 | B-TYPE | [6 empty] | 24988.72 |  |  | 11591.915 | 46.39% |  | 0 | 0% |  | 11591.915 | 46.39%
A | Architectural Works | [6 empty] | 11612.82 |  |  | 5632.46 | 48.5% |  | 0 | 0% |  | 5632.46 | 48.5%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 147 | 2.6 | 1.8 | 4.4 | 646.8 | Revise quantities based on the actual site | 124.95 | 549.78 | 85% | 0 | 0 | 0% | 124.95 | 549.78 | 85%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 116.2 | 1.8 | 2.8 | 4.6 | 534.52 | Revise quantities based on the actual site | 116.2 | 534.52 | 100% | 0 | 0 | 0% | 116.2 | 534.52 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 84.7 | 5 | 4 | 9 | 762.3 |  | 84.7 | 762.3 | 100% | 0 | 0 | 0% | 84.7 | 762.3 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 62 | 41.8 | 12.9 | 54.7 | 3391.4 |  | 12.4 | 678.28 | 20% | 0 | 0 | 0% | 12.4 | 678.28 | 20%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 70 | 7.5 | 4.5 | 12 | 840 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 147 | 22.6 | 7.6 | 30.2 | 4439.4 |  | 102.9 | 3107.58 | 70% | 0 | 0 | 0% | 102.9 | 3107.58 | 70%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 2 | 428 | 71.2 | 499.2 | 998.4 | The existing Door is not good condition propose to install new | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
B | Electrical Works | [6 empty] | 10920.1 |  |  | 5548.655 | 50.81% |  | 0 | 0% |  | 5548.655 | 50.81%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.5 | 1790.55 | 50% | 0 | 0 | 0% | 0.5 | 1790.55 | 50%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.85 | 1757.885 | 85% | 0 | 0 | 0% | 0.85 | 1757.885 | 85%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.85 | 2000.22 | 85% | 0 | 0 | 0% | 0.85 | 2000.22 | 85%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2455.8 |  |  | 410.8 | 16.73% |  | 0 | 0% |  | 410.8 | 16.73%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 26 | 44.2 | 19 | 63.2 | 1643.2 | Revise quantities based on the actual site | 6.5 | 410.8 | 25% | 0 | 0 | 0% | 6.5 | 410.8 | 25%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
10.2 | Polytechnic Institute of Preah Sihanouk (PIP) | [6 empty] | 45904.3 |  |  | 26991.415 | 58.8% |  | 0 | 0% |  | 26991.415 | 58.8%
10.2.1 | A-TYPE | [6 empty] | 18343.6 |  |  | 11358.09 | 61.92% |  | 0 | 0% |  | 11358.09 | 61.92%
A | Architectural Works | [6 empty] | 9307.1 |  |  | 7302.07 | 78.46% |  | 0 | 0% |  | 7302.07 | 78.46%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 62 | 25.7 | 7.5 | 33.2 | 2058.4 |  | 58.9 | 1955.48 | 95% | 0 | 0 | 0% | 58.9 | 1955.48 | 95%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 63 | 1.8 | 2.8 | 4.6 | 289.8 |  | 63 | 289.8 | 100% | 0 | 0 | 0% | 63 | 289.8 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 49.7 | 5 | 4 | 9 | 447.3 |  | 49.7 | 447.3 | 100% | 0 | 0 | 0% | 49.7 | 447.3 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 56 | 41.8 | 12.9 | 54.7 | 3063.2 |  | 44.8 | 2450.56 | 80% | 0 | 0 | 0% | 44.8 | 2450.56 | 80%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | External paint is good condition
| S1 | - Porcelain tile thk12, H=120mm | m | 40 | 7.5 | 4.5 | 12 | 480 | New skirting in all rooms where the new floor tile (F2) is installed | 40 | 480 | 100% | 0 | 0 | 0% | 40 | 480 | 100%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 60 | 7.5 | 4.5 | 12 | 720 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 62 | 22.6 | 7.6 | 30.2 | 1872.4 |  | 43.4 | 1310.68 | 70% | 0 | 0 | 0% | 43.4 | 1310.68 | 70%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing door is good condition propose to repaint
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0.95 | 147.25 | 95% | 0 | 0 | 0% | 0.95 | 147.25 | 95%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition propose to reuse
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 13 | 11.3 | 5.7 | 17 | 221 | There are existing security bar propose to repaint | 13 | 221 | 100% | 0 | 0 | 0% | 13 | 221 | 100%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 7327.7 |  |  | 3870.54 | 52.82% |  | 0 | 0% |  | 3870.54 | 52.82%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0.5 | 1197 | 50% | 0 | 0 | 0% | 0.5 | 1197 | 50%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.9 | 1149.84 | 90% | 0 | 0 | 0% | 0.9 | 1149.84 | 90%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.9 | 1523.7 | 90% | 0 | 0 | 0% | 0.9 | 1523.7 | 90%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 1708.8 |  |  | 185.48 | 10.85% |  | 0 | 0% |  | 185.48 | 10.85%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 14 | 44.2 | 19 | 63.2 | 884.8 | Revise quantities based on the actual site | 1.4 | 88.48 | 10% | 0 | 0 | 0% | 1.4 | 88.48 | 10%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 5 | 12.1 | 7.3 | 19.4 | 97 |  | 5 | 97 | 100% | 0 | 0 | 0% | 5 | 97 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
10.2.2 | B-TYPE | [6 empty] | 27560.7 |  |  | 15633.325 | 56.72% |  | 0 | 0% |  | 15633.325 | 56.72%
A | Architectural Works | [6 empty] | 13883.8 |  |  | 9246.605 | 66.6% |  | 0 | 0% |  | 9246.605 | 66.6%
Floor Finish
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 119 | 25.7 | 7.5 | 33.2 | 3950.8 |  | 113.5 | 3768.2 | 95.38% | 0 | 0 | 0% | 113.5 | 3768.2 | 95.38%
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 91 | 1.8 | 2.8 | 4.6 | 418.6 |  | 91 | 418.6 | 100% | 0 | 0 | 0% | 91 | 418.6 | 100%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 72.1 | 5 | 4 | 9 | 648.9 |  | 72.1 | 648.9 | 100% | 0 | 0 | 0% | 72.1 | 648.9 | 100%
| W3 | - Removing the existing wall (brick wall or dry wall) including reparing the floor, wall and ceiling where the existing wall had been | Sq.m | 40 | 1.5 | 3.6 | 5.1 | 204 |  | 40 | 204 | 100% | 0 | 0 | 0% | 40 | 204 | 100%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 51 | 41.8 | 12.9 | 54.7 | 2789.7 |  | 12.75 | 697.425 | 25% | 0 | 0 | 0% | 12.75 | 697.425 | 25%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 0 | 4.3 | 3.6 | 7.9 | 0 | The extenal wall paint is good condition
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 55 | 660 | 100% | 0 | 0 | 0% | 55 | 660 | 100%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 75 | 7.5 | 4.5 | 12 | 900 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 119 | 22.6 | 7.6 | 30.2 | 3593.8 |  | 71.4 | 2156.28 | 60% | 0 | 0 | 0% | 71.4 | 2156.28 | 60%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing door is good condition propose to paint
| D1' | Repaint the existing double door and install a new lock. | Set | 2 | 120 | 35 | 155 | 310 |  | 1.84 | 285.2 | 92% | 0 | 0 | 0% | 1.84 | 285.2 | 92%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition propose to reuse
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 24 | 11.3 | 5.7 | 17 | 408 | There are existing security bar propose to repaint | 24 | 408 | 100% | 0 | 0 | 0% | 24 | 408 | 100%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 5769.72 | 52.84% |  | 0 | 0% |  | 5769.72 | 52.84%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0.5 | 1790.55 | 50% | 0 | 0 | 0% | 0.5 | 1790.55 | 50%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.9 | 1861.29 | 90% | 0 | 0 | 0% | 0.9 | 1861.29 | 90%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.9 | 2117.88 | 90% | 0 | 0 | 0% | 0.9 | 2117.88 | 90%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
C | Miscellaneous and Common Work | [6 empty] | 2756.8 |  |  | 617 | 22.38% |  | 0 | 0% |  | 617 | 22.38%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 28 | 44.2 | 19 | 63.2 | 1769.6 | Revise quantities based on the actual site | 7 | 442.4 | 25% | 0 | 0 | 0% | 7 | 442.4 | 25%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 9 | 12.1 | 7.3 | 19.4 | 174.6 |  | 9 | 174.6 | 100% | 0 | 0 | 0% | 9 | 174.6 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
11 | Kampot Province | [6 empty] | 41266.2 |  |  | 5398.06 | 13.08% |  | 3392.06 | 8.22% |  | 8790.12 | 21.3%
11.1 | Regional Polytechnic Institute Techo Sen Kampot (RPITSK) | [6 empty] | 41266.2 |  |  | 5398.06 | 13.08% |  | 3392.06 | 8.22% |  | 8790.12 | 21.3%
11.1.1 | A-TYPE | [6 empty] | 17210.76 |  |  | 2023.608 | 11.76% |  | 1315.216 | 7.642% |  | 3338.824 | 19.4%
A | Architectural Works | [6 empty] | 8344.46 |  |  | 932.108 | 11.17% |  | 328.476 | 3.936% |  | 1260.584 | 15.11%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 63 | 2.6 | 1.8 | 4.4 | 277.2 | The existing floor tile is good condition can be reuse | 25.2 | 110.88 | 40% | 12.6 | 55.44 | 20% | 37.8 | 166.32 | 60%
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 0 | 25.7 | 7.5 | 33.2 | 0
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 75.6 | 1.8 | 2.8 | 4.6 | 347.76 |  | 60.48 | 278.208 | 80% | 7.56 | 34.776 | 10% | 68.04 | 312.984 | 90%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 54.6 | 5 | 4 | 9 | 491.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 62 | 41.8 | 12.9 | 54.7 | 3391.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 29 | 4.3 | 3.6 | 7.9 | 229.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 50 | 7.5 | 4.5 | 12 | 600 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 63 | 22.6 | 7.6 | 30.2 | 1902.6 |  | 12.6 | 380.52 | 20% | 6.3 | 190.26 | 10% | 18.9 | 570.78 | 30%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0.5 | 77.5 | 50% | 0.2 | 31 | 20% | 0.7 | 108.5 | 70%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 10 | 11.3 | 5.7 | 17 | 170 | The existing security bars are in good condition, we propose repainting | 5 | 85 | 50% | 1 | 17 | 10% | 6 | 102 | 60%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 7327.7 |  |  | 986.74 | 13.47% |  | 986.74 | 13.47% |  | 1973.48 | 26.93%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 2295.5 | 98.5 | 2394 | 2394 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.2 | 255.52 | 20% | 0.2 | 255.52 | 20% | 0.4 | 511.04 | 40%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.2 | 338.6 | 20% | 0.2 | 338.6 | 20% | 0.4 | 677.2 | 40%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.2 | 392.62 | 20% | 0.2 | 392.62 | 20% | 0.4 | 785.24 | 40%
C | Miscellaneous and Common Work | [6 empty] | 1538.6 |  |  | 104.76 | 6.809% |  | 0 | 0% |  | 104.76 | 6.809%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 11 | 44.2 | 19 | 63.2 | 695.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 6 | 12.1 | 7.3 | 19.4 | 116.4 | Revise quantities based on the actual site | 5.4 | 104.76 | 90% | 0 | 0 | 0% | 5.4 | 104.76 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
11.1.2 | B-TYPE | [6 empty] | 24055.44 |  |  | 3374.452 | 14.03% |  | 2076.844 | 8.634% |  | 5451.296 | 22.66%
A | Architectural Works | [6 empty] | 10704.54 |  |  | 1644.752 | 15.36% |  | 609.044 | 5.69% |  | 2253.796 | 21.05%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 119 | 2.6 | 1.8 | 4.4 | 523.6 | The existing floor tile is good condition can be reuse | 47.6 | 209.44 | 40% | 23.8 | 104.72 | 20% | 71.4 | 314.16 | 60%
| F2 | - Replacing the existing tiles with new porcelain tile (600mm x 600mm, THK 12) including the existing base | Sq.m | 0 | 25.7 | 7.5 | 33.2 | 0
Wall Finish
| W1 | - Removing the existing paint and cleaning with repairing the existing mortar finish | Sq.m | 106.4 | 1.8 | 2.8 | 4.6 | 489.44 | Revise quantities based on the actual site | 85.12 | 391.552 | 80% | 10.64 | 48.944 | 10% | 95.76 | 440.496 | 90%
| W2 | - Interior wall paint (Emulsion paint with smooth surface roller paint, stucco paint cream white or designated color, 2 Coat) | Sq.m | 78.4 | 5 | 4 | 9 | 705.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 50 | 41.8 | 12.9 | 54.7 | 2735 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 49 | 4.3 | 3.6 | 7.9 | 387.1 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S1 | - Porcelain tile thk12, H=120mm | m | 55 | 7.5 | 4.5 | 12 | 660 | New skirting in all rooms where the new floor tile (F2) is installed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 80 | 7.5 | 4.5 | 12 | 960 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C2 | - Acoustic tax (300mm x 600mm, THK 6) on gypsum board (THK 9.5, 1 ply) with light-weight steel ceiling frame | Sq.m | 119 | 22.6 | 7.6 | 30.2 | 3593.8 | Revise quantities based on the actual site | 23.8 | 718.76 | 20% | 11.9 | 359.38 | 10% | 35.7 | 1078.14 | 30%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 2 | 120 | 35 | 155 | 310 |  | 1 | 155 | 50% | 0.4 | 62 | 20% | 1.4 | 217 | 70%
Window Works
| WD1 | - Replacing the existing window with new PVC window + THK 5 tempered glass | Sq.m | 0 | 166.4 | 30 | 196.4 | 0 | The existing window is good condition we propose to reuse and repainting
| WD2 | - Paint on window frame and security bar (Cleaning the existing window frame and security bar / Removing the existing paint and re-paint with new paint, oil paint for steel, white or designated color) | Sq.m | 20 | 11.3 | 5.7 | 17 | 340 | The existing security bars are in good condition, we propose repainting | 10 | 170 | 50% | 2 | 34 | 10% | 12 | 204 | 60%
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 0 | 38.7 | 11 | 49.7 | 0
B | Electrical Works | [6 empty] | 10920.1 |  |  | 1467.8 | 13.44% |  | 1467.8 | 13.44% |  | 2935.6 | 26.88%
Air Conditioner
| AC | - Installation wall mounted air conditioner (2.5HP each) with outdoor unit with copper pipe, drain pipe and power cabling including PVC conduit and accessories | LS | 1 | 3433.3 | 147.8 | 3581.1 | 3581.1 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.2 | 413.62 | 20% | 0.2 | 413.62 | 20% | 0.4 | 827.24 | 40%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.2 | 470.64 | 20% | 0.2 | 470.64 | 20% | 0.4 | 941.28 | 40%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.2 | 583.54 | 20% | 0.2 | 583.54 | 20% | 0.4 | 1167.08 | 40%
C | Miscellaneous and Common Work | [6 empty] | 2430.8 |  |  | 261.9 | 10.77% |  | 0 | 0% |  | 261.9 | 10.77%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 21 | 44.2 | 19 | 63.2 | 1327.2 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 15 | 12.1 | 7.3 | 19.4 | 291 | Revise quantities based on the actual site | 13.5 | 261.9 | 90% | 0 | 0 | 0% | 13.5 | 261.9 | 90%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
12 | Kampong Speu Province | [6 empty] | 34066.2 |  |  | 15706.745 | 46.11% |  | 1082.9 | 3.179% |  | 16789.645 | 49.29%
12.1 | Polytechnic Institute of Kampong Speu Province (PIKSP) | [6 empty] | 34066.2 |  |  | 15706.745 | 46.11% |  | 1082.9 | 3.179% |  | 16789.645 | 49.29%
12.1.1 | A-TYPE | [6 empty] | 14304.3 |  |  | 6935.045 | 48.48% |  | 317.3 | 2.218% |  | 7252.345 | 50.7%
A | Architectural Works | [6 empty] | 7807.6 |  |  | 2663.8 | 34.12% |  | 317.3 | 4.064% |  | 2981.1 | 38.18%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 62 | 2.6 | 1.8 | 4.4 | 272.8 | Revise quantities based on the actual site | 62 | 272.8 | 100% | 0 | 0 | 0% | 62 | 272.8 | 100%
Wall Finish
| W4 | - New wall (brick wall or drywall) | Sq.m | 33 | 13.1 | 8.8 | 21.9 | 722.7 | Revise quantities based on the actual site | 32 | 700.8 | 96.97% | 0 | 0 | 0% | 32 | 700.8 | 96.97%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 70 | 41.8 | 12.9 | 54.7 | 3829 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 30 | 4.3 | 3.6 | 7.9 | 237 | Revise quantities based on the actual site | 15 | 118.5 | 50% | 15 | 118.5 | 50% | 30 | 237 | 100%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 65 | 7.5 | 4.5 | 12 | 780 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 62 | 19.3 | 4.3 | 23.6 | 1463.2 | Revise quantities based on the actual site | 62 | 1463.2 | 100% | 0 | 0 | 0% | 62 | 1463.2 | 100%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0.7 | 108.5 | 70% | 0 | 0 | 0% | 0.7 | 108.5 | 70%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 7 | 38.7 | 11 | 49.7 | 347.9 |  | 0 | 0 | 0% | 4 | 198.8 | 57.14% | 4 | 198.8 | 57.14%
B | Electrical Works | [6 empty] | 4933.7 |  |  | 4193.645 | 85% |  | 0 | 0% |  | 4193.645 | 85%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 988.5 | 289.1 | 1277.6 | 1277.6 |  | 0.85 | 1085.96 | 85% | 0 | 0 | 0% | 0.85 | 1085.96 | 85%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1369.8 | 323.2 | 1693 | 1693 |  | 0.85 | 1439.05 | 85% | 0 | 0 | 0% | 0.85 | 1439.05 | 85%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 1612.9 | 350.2 | 1963.1 | 1963.1 |  | 0.85 | 1668.635 | 85% | 0 | 0 | 0% | 0.85 | 1668.635 | 85%
C | Miscellaneous and Common Work | [6 empty] | 1563 |  |  | 77.6 | 4.965% |  | 0 | 0% |  | 77.6 | 4.965%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 12 | 44.2 | 19 | 63.2 | 758.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 4 | 12.1 | 7.3 | 19.4 | 77.6 |  | 4 | 77.6 | 100% | 0 | 0 | 0% | 4 | 77.6 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 374.5 | 74.9 | 449.4 | 449.4 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
12.1.2 | B-TYPE | [6 empty] | 19761.9 |  |  | 8771.7 | 44.39% |  | 765.6 | 3.874% |  | 9537.3 | 48.26%
A | Architectural Works | [6 empty] | 9748.7 |  |  | 2745.3 | 28.16% |  | 765.6 | 7.853% |  | 3510.9 | 36.01%
Floor Finish
| F1 | - Cleaning the existing tiles with repairing joint including the existing base | Sq.m | 116 | 2.6 | 1.8 | 4.4 | 510.4 |  | 116 | 510.4 | 100% | 0 | 0 | 0% | 116 | 510.4 | 100%
Wall Finish
| W4 | - New wall (brick wall or drywall) | Sq.m | 38 | 13.1 | 8.8 | 21.9 | 832.2 |  | 36 | 788.4 | 94.74% | 0 | 0 | 0% | 36 | 788.4 | 94.74%
| W5 | - Acoustic wood panel (on the existing wall) using nail gun and accessories | Sq.m | 60 | 41.8 | 12.9 | 54.7 | 3282 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| W6 | - External wall paint (Emulsion paint with smooth surface roller paint, existing color or designated color, 2 Coat) | Sq.m | 54 | 4.3 | 3.6 | 7.9 | 426.6 |  | 20 | 158 | 37.04% | 34 | 268.6 | 62.96% | 54 | 426.6 | 100%
| S2 | - MC Wood Molding 20x50mm with laminate finishing | m | 80 | 7.5 | 4.5 | 12 | 960 | New items proposes for the top trim of W5 and around WD1 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Ceiling Works
| C1 | - Installation of acoustic tax (300mm x 600mm, THK 6) on the existing gypsum board | Sq.m | 116 | 19.3 | 4.3 | 23.6 | 2737.6 |  | 50 | 1180 | 43.1% | 0 | 0 | 0% | 50 | 1180 | 43.1%
Door Works
| D1 | - Replacing the existing door with new steel door including door frame (W: 1,000 x H: 2,100) certificated KS (Korean Standard) with 1 set of hardware, door lock, door closer and door stopper | Set | 0 | 428 | 71.2 | 499.2 | 0 | The existing Door is good condition can be reuse we propose to repainting on the existing and install new lock
| D1' | Repaint the existing double door and install a new lock. | Set | 1 | 120 | 35 | 155 | 155 |  | 0.7 | 108.5 | 70% | 0 | 0 | 0% | 0.7 | 108.5 | 70%
Window Works
| WD3 | - Steel Security Bar: Size to cover the existing window opening including oil paint (Korean traditional window lattice pattern) | Sq.m | 17 | 38.7 | 11 | 49.7 | 844.9 |  | 0 | 0 | 0% | 10 | 497 | 58.82% | 10 | 497 | 58.82%
B | Electrical Works | [6 empty] | 7339 |  |  | 5871.2 | 80% |  | 0 | 0% |  | 5871.2 | 80%
Electricity & Communication
| E1 | - Replacing the existing lighting fixture with new LED lighting fixtures (300 x 1,200, 50w) including 2 way switch (1.00 pcs) and accessories (cable, conduit, etc.) | LS | 1 | 1548.9 | 519.2 | 2068.1 | 2068.1 |  | 0.8 | 1654.48 | 80% | 0 | 0 | 0% | 0.8 | 1654.48 | 80%
| E2 | - Install DB Panel, Power socket, grounding and accessories (Cable, Conduit, etc,…) | LS | 1 | 1820 | 533.2 | 2353.2 | 2353.2 |  | 0.8 | 1882.56 | 80% | 0 | 0 | 0% | 0.8 | 1882.56 | 80%
| E3 | - Install Rack Cabinet, Data socket, Network switch, Testing and Accessories (Cable, Conduit, etc,…) | LS | 1 | 2330.8 | 586.9 | 2917.7 | 2917.7 |  | 0.8 | 2334.16 | 80% | 0 | 0 | 0% | 0.8 | 2334.16 | 80%
C | Miscellaneous and Common Work | [6 empty] | 2674.2 |  |  | 155.2 | 5.804% |  | 0 | 0% |  | 155.2 | 5.804%
Miscellaneous
| MC1 | - Window Blind : Blackout roll-up blind on each window (larger than the opening size) with wall mount rail and other accessories | Sq.m | 27 | 44.2 | 19 | 63.2 | 1706.4 | Revise quantities based on the actual site | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| MC2 | - Block the ventilation block (3,000mm x 400mm) in the classroom and paint (finish same as wall paint) | Sq.m | 8 | 12.1 | 7.3 | 19.4 | 155.2 |  | 8 | 155.2 | 100% | 0 | 0 | 0% | 8 | 155.2 | 100%
| MC3 | - Signboard: 500mm (W) x 350mm (H) stainless steel panel, hairline finishing including context | Set | 1 | 84 | 18 | 102 | 102 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Common Works
| CM1 | - Multi-Function Glass Board : white glass board (L: 2.400 x H: 1.200, THK 8) with tempered film including clip, steel (or aluminium) frame and pen tray | Set | 1 | 131.7 | 43.9 | 175.6 | 175.6 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
| CM2 | - Smoke Detector with sealed lithium battery, photoelectric sensor and audio alarm (85dB at 10ft) | LS | 1 | 428 | 107 | 535 | 535 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
III | Other Work | [6 empty] | 5000
1 | Shop Drawing |  | LS | 1 |  |  | 2000 | 2000
2 | As-built Drawing Work and Documentation |  | LS | 1 |  |  | 3000 | 3000
Prepared By |  |  | Comment
( Sign here) |  | Signature , name & Position
Name:…………………. Position:…………. |  | Name:…………………. Position:………….

## Cover
KINGDOM OF CAMBODIA
NATION RELIGION KING
WEEKLY PROGRESS REPORT
| 20 |  |  |  | 20
| From 13-Mar-26 ~ 19-Mar-26 |  |  |  | 13-Mar-26 | 19-Mar-26
Renovation Works of The Project for Building Capacity and
Establishing Enabling Environment in ICT Majors of TVET
in Cambodia
|  | Employer | : | KOICA Cambodia Office
|  | Consultant | : | KFS(Korea Forest Service) &
FA(Forestry Administration)
|  | Contractor | : | Cambodian Advanced Construction Project Management (CACPM)Co., Ltd

## Letter
LETTER FOR WEEKLY PROGRESS REPORT No.20 |  |  | 20 | 13-Mar-26 | 19-Mar-26
Ref. No. | : | ICT-CPM-LETTER-20
Date | : | 2026-03-20
To | : | KOICA Cambodia Office 12th Floor, Exchange Square, Building Nos19. And 20, Street 106, Village 2, Sangkat Wat Phnom, Khan Daun Penh, Phnom Penh, Cambodia
Att. | : | Mr. Chang Woo Jin / CM of Korea International Cooperation Agency
CC | : | Ms. Kim Sujin / Deputy Country Director of KOICA
| : | Mr. Sao Dona / Senior Specialist of KOICA
| : | Mr. Hourn Kimhour / Assistant CM of KOICA
Dear Sir,
We are pleased to submit Weekly Progress Report No-20 from 13-Mar-26 to 19-Mar-26 for Renovation Works of The Project for Building Capacity and Establishing Enabling Environment in ICT Majors of TVET in Cambodia. Sincerely Yours,
_________________________________
Mr. Milko Orecchia ¦ Project Manager Cambodian Advanced Construction Project Management (CACPM) 8th Floor, K1 Tower, No.148, Mao Tse Toung Boulevard (245), Sangkat Toul Tumpong II, Khan Chamkarmorn, Phnom Penh, Cambodia T +855 (0) 23 964 417~8 ¦ M +855 (0) 11 693 415 o.milko@cambodiacpm.com www.cambodiacpm.com

## CONTENT
TABLE OF CONTENTS*
1. INTRODUCTION
2. OVERALL PROGRESS OF THIS WEEK AND NEXT WEEK
3. ACTIVITIES OF WORK DONE / NEXT WEEK PLAN
4. QA/QC STATUS
4.1 Non-Conformity Report (NCR)
4.2 Corrective Action Request (CAR)
4.3 Safety Corrective Action Request (SCAR)
4.4 PM Site Instruction (SI)
4.5 Client Site Instruction (SI)
4.6 Inspection Request (IR)
4.7 Material for Approval (MFA)
4.8 Request for Information (RFI)
4.9 Request for Approval (RFA)
4.10 Field Change Request (FCR)
4.11 Variation Order (VO)
4.12 Transmittal (TR)
4.13 Material Inspection Approval (MIR)
5. HEALTH, SAFETY, ENVIRONMENTAL & SECURITY (HSES)
5.1 HSES Training / Introduction / Toolbox Meeting
5.2 HSES Inspection / Audit / Heavy Equipment / Hand&Power Tool Checklist
5.3 Permit to Work
5.4 First Aid / Accident / Incident / Near Miss / Fatalities (if Any)
5.5 Other HSES Actities Concerns
5.6 HSES Photo Reference
6. RESOURCES STATUS
6.1 Manpower Status
6.2 Material Delivery Status
6.3 Machinery / Equipment Status
7. SITE ACTIVITY PHOTOS
8. CONSTRUCTION ISSUE
9. MASTER SCHEDULE

## 1.Intro
1. INTRODUCTION
Project Overview
This project aims to strengthen the ICT education capacity of TVET and to improve the ICT education environment of the existing TVET institutes in Cambodia. ICT Labs will be established and furnished for the TVET. For this Project, 17 institutes have been selected by KOICA and MLVT Cambodia; 2 as Hub Centers and 15 as Leading institutes. Each institute has secured existing classrooms to be renovated into an ICT Lab with the capacity of 30 persons (A-Type: 30 sets of computers with 15 desks / B-Type (or H-Type): 30 sets of computers with 15 desks + 2 working tables). Remodelling Work to renovate the existing classrooms into ICT Labs for a better ICT education environment is one of the Project scopes. This bidding is to select a Contractor to conduct the Remodelling Work.
Design & Construction
Cambodian Advanced Construction Project Management Co., Ltd (CACPM) is a design, engineeing and construction project management company with core services portfolio including Architecture, Urban planning, Civil, Structure, MEP Engineering, Cost Management, Property Management, Owner-team consultation Turnkey Projects and Feasibility Study. CACPM was appointed as Contractor by client for this project to carry out the scope of works as follows:
▪ Architectural Work
▪ Electrical Work
▪ Miscellaneous and Common Work

## 2.OP
2. OVERALL PROGRESS OF THIS WEEK AND NEXT WEEK
No | Scope of Works | % Up to Previous Week | % This Week | % Up to This Week | % Remaining | % Next Week Plan | % Up Next Week Plan
I | INVESTIGATION PHASE | 100% | 0% | 100% | 0% | 0% | 100% | 100%
1 | Site survey | 100% | 0% | 100% | 0% | 0% | 100%
2 | Drawing (Existing & Construction) | 100% | 0% | 100% | 0% | 0% | 100%
3 | BoQ | 100% | 0% | 100% | 0% | 0% | 100%
II | CONSTRUCTION PHASE | 27.89% | 2.76% | 30.65% | 69.35% | 3.456% | 34.11%
1 | Battambang Province | 13.15% | 5.557% | 18.71% | 81.29% | 6.947% | 25.66%
2 | Banteay Meanchey Province | 50.92% | 0% | 50.92% | 49.08% | 0% | 50.92%
3 | Pursat Province Province | 43.82% | 0% | 43.82% | 56.18% | 0% | 43.82%
4 | Kampong Thom Province | 52.34% | 0% | 52.34% | 47.66% | 0% | 52.34%
5 | Siem Reap Province | 34.52% | 1.884% | 36.4% | 63.6% | 7.218% | 43.62%
6 | Phnom Penh | 26.8% | 2.805% | 29.6% | 70.4% | 3.554% | 33.16%
7 | Kandal Province | 18.5% | 6.427% | 24.92% | 75.08% | 5.54% | 30.46%
8 | Takeo Province | 0% | 0% | 0% | 100% | 0% | 0%
9 | Svay Rieng Province | 0% | 0% | 0% | 100% | 0.6801% | 0.6801%
10 | Preah Sihanouk | 51.81% | 0% | 51.81% | 48.19% | 0% | 51.81%
11 | Kampot Province | 2.571% | 10.51% | 13.08% | 86.92% | 8.22% | 21.3%
12 | Kampong Speu Province | 41.78% | 4.327% | 46.11% | 53.89% | 3.179% | 49.29%
Remark: - Banteay Meanchey, Pursat, Kampong Thom and Preah Sihanouk will resume work once the acoustic panels and acoustic ceiling have been delivered from overseas.

## 3.NWDP
3. ACTIVITIES OF WORK DONE / NEXT WEEK PLAN
Activities of Work Done |  | Next Week Plan
I. Investigation Phase | 100% | I. Investigation Phase | 0% | 100%
1. Site survey | 100% | 1. Site survey | 0%
2. Drawing (Existing & Construction) | 100% | 2. Drawing (Existing & Construction) | 0%
3. BoQ | 100% | 3. BoQ | 0%
II. Construction Phase | 30.65% | II. Construction Phase | 3.456%
1. Battambang Province | 18.71% | 1. Battambang Province | 6.947%
1.1. Battambang Institute of Technology (BIT) | 20.11% | 1.1. Battambang Institute of Technology (BIT) | 5.053%
1.1.1. Room A-Type | 17.92% | 1.1.1. Room A-Type | 4.509%
- Architectural work | 14.29% | - Architectural work | 3.234%
- Electrical Works | 24.03% | - Electrical Works | 6.733%
- Miscellaneous and Common work | 7.187% | - Miscellaneous and Common work | 0.3783%
1.1.2. Room B-Type | 21.66% | 1.1.2. Room B-Type | 5.436%
- Architectural work | 23.25% | - Architectural work | 5.213%
- Electrical Works | 22.96% | - Electrical Works | 6.721%
- Miscellaneous and Common work | 8.615% | - Miscellaneous and Common work | 0.4534%
1.2. Regional Polytechnic Institute Techo Sen Battambang (RPITSB) | 17.51% | 1.2. Regional Polytechnic Institute Techo Sen Battambang (RPITSB) | 8.572%
1.2.1. Room A-Type | 15.57% | 1.2.1. Room A-Type | 8.904%
- Architectural work | 12.8% | - Architectural work | 11.52%
- Electrical Works | 22.69% | - Electrical Works | 6.733%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 1.891%
1.2.2. Room B-Type | 18.83% | 1.2.2. Room B-Type | 8.346%
- Architectural work | 21.3% | - Architectural work | 10.47%
- Electrical Works | 19.21% | - Electrical Works | 6.721%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 1.973%
2. Banteay Meanchey Province | 50.92% | 2. Banteay Meanchey Province | 0%
2.1. Polytechnic Institute of Banteay Meanchey Province (PIBMC) | 50.92% | 2.1. Polytechnic Institute of Banteay Meanchey Province (PIBMC) | 0%
2.1.1. Room A-Type | 43.48% | 2.1.1. Room A-Type | 0%
- Architectural work | 5.26% | - Architectural work | 0%
- Electrical Works | 80% | - Electrical Works | 0%
- Miscellaneous and Common work | 30.74% | - Miscellaneous and Common work | 0%
2.1.2. Room B-Type | 57.62% | 2.1.2. Room B-Type | 0%
- Architectural work | 7.49% | - Architectural work | 0%
- Electrical Works | 81.64% | - Electrical Works | 0%
- Miscellaneous and Common work | 34.1% | - Miscellaneous and Common work | 0%
3. Pursat Province | 43.82% | 3. Pursat Province | 0%
3.1. Polytechnic Institute of Pursat Province (PIPP) | 43.82% | 3.1. Polytechnic Institute of Pursat Province (PIPP) | 0%
3.1.1. Room A-Type | 38.02% | 3.1.1. Room A-Type | 0%
- Architectural work | 5.162% | - Architectural work | 0%
- Electrical Works | 72.98% | - Electrical Works | 0%
- Miscellaneous and Common work | 18.71% | - Miscellaneous and Common work | 0%
3.1.2. Room B-Type | 48.98% | 3.1.2. Room B-Type | 0%
- Architectural work | 7.243% | - Architectural work | 0%
- Electrical Works | 72.98% | - Electrical Works | 0%
- Miscellaneous and Common work | 19.32% | - Miscellaneous and Common work | 0%
4. Kampong Thom Province | 52.34% | 4. Kampong Thom Province | 0%
4.1. Polytechnic Institute of Kampong Thom Province (PIKT) | 52.34% | 4.1. Polytechnic Institute of Kampong Thom Province (PIKT) | 0%
4.1.1. Room A-Type | 46.87% | 4.1.1. Room A-Type | 0%
- Architectural work | 3.951% | - Architectural work | 0%
- Electrical Works | 85.03% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
4.1.2. Room B-Type | 56.61% | 4.1.2. Room B-Type | 0%
- Architectural work | 13.2% | - Architectural work | 0%
- Electrical Works | 85.52% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
5. Siem Reap Province | 36.4% | 5. Siem Reap Province | 7.218%
5.1. National Polytechnic Institute of Angkor (NPIA) | 35.54% | 5.1. National Polytechnic Institute of Angkor (NPIA) | 5.917%
5.1.1. Room A-Type | 33.82% | 5.1.1. Room A-Type | 5.606%
- Architectural work | 12.94% | - Architectural work | 6.118%
- Electrical Works | 62.71% | - Electrical Works | 6.534%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
5.1.2. Room B-Type | 36.71% | 5.1.2. Room B-Type | 6.129%
- Architectural work | 19.28% | - Architectural work | 7.375%
- Electrical Works | 62.48% | - Electrical Works | 6.559%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
5.2. Regional Polytechnic Institute Techo Sen Siem Reap (RPITSSR) | 37.66% | 5.2. Regional Polytechnic Institute Techo Sen Siem Reap (RPITSSR) | 9.112%
5.2.1. Room B-Type | 37.66% | 5.2.1. Room B-Type | 9.112%
- Architectural work | 35.21% | - Architectural work | 12.39%
- Electrical Works | 47.27% | - Electrical Works | 6.721%
- Miscellaneous and Common work | 7.544% | - Miscellaneous and Common work | 0%
6. Phnom Penh | 29.6% | 6. Phnom Penh | 3.554%
6.1. National Polytechnic Institute of Cambodia (NPIC) | 0% | 6.1. National Polytechnic Institute of Cambodia (NPIC) | 0.6238%
6.1.1. Room A-Type | 0% | 6.1.1. Room A-Type | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.1.2. Room B-Type | 0% | 6.1.2. Room B-Type | 0.8938%
- Architectural work | 0% | - Architectural work | 1.615%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.2. National Technical Training Institute (NTTI) | 28.97% | 6.2. National Technical Training Institute (NTTI) | 3.459%
6.2.1. Room A-Type-1 | 58.69% | 6.2.1. Room A-Type-1 | 7.139%
- Architectural work | 55.24% | - Architectural work | 11.53%
- Electrical Works | 76.73% | - Electrical Works | 1.744%
- Miscellaneous and Common work | 5.109% | - Miscellaneous and Common work | 0%
6.2.2. Room A-Type-2 | 0% | 6.2.2. Room A-Type-2 | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.2.3. Room A-Type-3 | 0% | 6.2.3. Room A-Type-3 | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.2.4. Room A-Type-4 | 0% | 6.2.4. Room A-Type-4 | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.2.5. Room A-Type-5 | 58.92% | 6.2.5. Room A-Type-5 | 7.063%
- Architectural work | 55.64% | - Architectural work | 11.39%
- Electrical Works | 76.73% | - Electrical Works | 1.744%
- Miscellaneous and Common work | 5.109% | - Miscellaneous and Common work | 0%
6.2.6. Room A-Type-6 | 58.71% | 6.2.6. Room A-Type-6 | 7.134%
- Architectural work | 55.29% | - Architectural work | 11.51%
- Electrical Works | 76.73% | - Electrical Works | 1.744%
- Miscellaneous and Common work | 5.109% | - Miscellaneous and Common work | 0%
6.2.7. Room B-Type-1 | 0% | 6.2.7. Room B-Type-1 | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.2.8. Room B-Type-2 | 65.35% | 6.2.8. Room B-Type-2 | 4.899%
- Architectural work | 66.29% | - Architectural work | 7.503%
- Electrical Works | 76.72% | - Electrical Works | 1.894%
- Miscellaneous and Common work | 5.923% | - Miscellaneous and Common work | 0%
6.2.9. Room B-Type-3 | 0% | 6.2.9. Room B-Type-3 | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
6.2.10. Room B-Type-4 | 50.04% | 6.2.10. Room B-Type-4 | 8.367%
- Architectural work | 42.12% | - Architectural work | 12.66%
- Electrical Works | 74.83% | - Electrical Works | 1.894%
- Miscellaneous and Common work | 5.923% | - Miscellaneous and Common work | 0%
6.3. National Institute of Business (NIB) | 81.93% | 6.3. National Institute of Business (NIB) | 9.032%
6.3.1. Room B-Type | 81.93% | 6.3.1. Room B-Type | 9.032%
- Architectural work | 81.9% | - Architectural work | 12.99%
- Electrical Works | 93.66% | - Electrical Works | 5%
- Miscellaneous and Common work | 3.572% | - Miscellaneous and Common work | 0%
7. Kandal Province | 24.92% | 7. Kandal Province | 5.54%
7.1. National Polytechnic Institute of Techo Sen (NPIT) | 24.92% | 7.1. National Polytechnic Institute of Techo Sen (NPIT) | 5.54%
7.1.1. Room A-Type | 22.3% | 7.1.1. Room A-Type | 4.911%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 51.26% | - Electrical Works | 11.52%
- Miscellaneous and Common work | 3.796% | - Miscellaneous and Common work | 0%
7.1.2. Room B-Type | 27.13% | 7.1.2. Room B-Type | 6.069%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 50.18% | - Electrical Works | 11.39%
- Miscellaneous and Common work | 3.611% | - Miscellaneous and Common work | 0%
8. Takeo Province | 0% | 8. Takeo Province | 0%
8.1. Regional Polytechnic Institute Techo Sen Takeo (RPITST) | 0% | 8.1. Regional Polytechnic Institute Techo Sen Takeo (RPITST) | 0%
8.1.1. Room A-Type | 0% | 8.1.1. Room A-Type | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
8.1.2. Room B-Type | 0% | 8.1.2. Room B-Type | 0%
- Architectural work | 0% | - Architectural work | 0%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
9. Svay Rieng Province | 0% | 9. Svay Rieng Province | 0.6801%
9.1. Regional Polytechnic Institute Techo Sen Svay Rieng (RPITSSR) | 0% | 9.1. Regional Polytechnic Institute Techo Sen Svay Rieng (RPITSSR) | 0.6801%
9.1.1. Room A-Type | 0% | 9.1.1. Room A-Type | 0.7249%
- Architectural work | 0% | - Architectural work | 1.357%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
9.1.2. Room B-Type | 0% | 9.1.2. Room B-Type | 0.6499%
- Architectural work | 0% | - Architectural work | 1.228%
- Electrical Works | 0% | - Electrical Works | 0%
- Miscellaneous and Common work | 0% | - Miscellaneous and Common work | 0%
10. Preah Sihanouk | 51.81% | 10. Preah Sihanouk | 0%
10.1. Preah Sihanouk Cambodia China Friendship Polytechnic Institute (PCCFPI) | 44.19% | 10.1. Preah Sihanouk Cambodia China Friendship Polytechnic Institute (PCCFPI) | 0%
10.1.1. Room A-Type | 41% | 10.1.1. Room A-Type | 0%
- Architectural work | 38.68% | - Architectural work | 0%
- Electrical Works | 50.79% | - Electrical Works | 0%
- Miscellaneous and Common work | 8.234% | - Miscellaneous and Common work | 0%
10.1.2. Room B-Type | 46.39% | 10.1.2. Room B-Type | 0%
- Architectural work | 48.5% | - Architectural work | 0%
- Electrical Works | 50.81% | - Electrical Works | 0%
- Miscellaneous and Common work | 16.73% | - Miscellaneous and Common work | 0%
10.2. Polytechnic Institute of Preah Sihanouk (PIP) | 58.8% | 10.2. Polytechnic Institute of Preah Sihanouk (PIP) | 0%
10.2.1. Room A-Type | 61.92% | 10.2.1. Room A-Type | 0%
- Architectural work | 78.46% | - Architectural work | 0%
- Electrical Works | 52.82% | - Electrical Works | 0%
- Miscellaneous and Common work | 10.85% | - Miscellaneous and Common work | 0%
10.2.2. Room B-Type | 56.72% | 10.2.2. Room B-Type | 0%
- Architectural work | 66.6% | - Architectural work | 0%
- Electrical Works | 52.84% | - Electrical Works | 0%
- Miscellaneous and Common work | 22.38% | - Miscellaneous and Common work | 0%
11. Kampot Province | 13.08% | 11. Kampot Province | 8.22%
11.1. Regional Polytechnic Institute Techo Sen Kampot (RPITSK) | 13.08% | 11.1. Regional Polytechnic Institute Techo Sen Kampot (RPITSK) | 8.22%
11.1.1. Room A-Type | 11.76% | 11.1.1. Room A-Type | 7.642%
- Architectural work | 11.17% | - Architectural work | 3.936%
- Electrical Works | 13.47% | - Electrical Works | 13.47%
- Miscellaneous and Common work | 6.809% | - Miscellaneous and Common work | 0%
11.1.2. Room B-Type | 14.03% | 11.1.2. Room B-Type | 8.634%
- Architectural work | 15.36% | - Architectural work | 5.69%
- Electrical Works | 13.44% | - Electrical Works | 13.44%
- Miscellaneous and Common work | 10.77% | - Miscellaneous and Common work | 0%
12. Kampong Speu Province | 46.11% | 12. Kampong Speu Province | 3.179%
12.1. Polytechnic Institute of Kampong Speu Province (PIKSP) | 46.11% | 12.1. Polytechnic Institute of Kampong Speu Province (PIKSP) | 3.179%
12.1.1. Room A-Type | 48.48% | 12.1.1. Room A-Type | 2.218%
- Architectural work | 34.12% | - Architectural work | 4.064%
- Electrical Works | 85% | - Electrical Works | 0%
- Miscellaneous and Common work | 4.965% | - Miscellaneous and Common work | 0%
12.1.2. Room B-Type | 44.39% | 12.1.2. Room B-Type | 3.874%
- Architectural work | 28.16% | - Architectural work | 7.853%
- Electrical Works | 80% | - Electrical Works | 0%
- Miscellaneous and Common work | 5.804% | - Miscellaneous and Common work | 0%

## 4. QAQC
4. QA/QC STATUS
4.1 Non-Conformity Report (NCR)
Code | Description | Status | Date Responded
Comments
4.2 Corrective Action Request (CAR)
Code | Description | Status | Date Responded
Comments
4.3 Safety Corrective Action Request (SCAR)
Code | Description | Status | Date Responded
Comments
4.4 PM Site Instruction (SI)
Code | Description | Status | Date Responded
Comments
4.5 Client Site Instruction (SI)
Code | Description | Issued By | Issued Date
Comments
4.6 Inspection Request (IR)
Code | Description | Received Date | Inspection Date
Comments
4.7 Material for Approval (MFA)
Code | Description | Status | Date Responded
ICT-CPM-MFA-AR-001-R0 | Material List For Architectural Works | Approved with condition | 2026-01-13
ICT-CPM-MFA-ME-001-R0 | Material List For Electrical and Mechanical Works | Approved with condition | 2026-01-13
ICT-CPM-MFA-AR-001-R1 | Material List For Architectural Works | Resubmit
ICT-CPM-MFA-ME-001-R1 | Material List For Electrical and Mechanical Works | Resubmit
ICT-CPM-MFA-AR-001-R2 | Material List For Architectural Works | Approved | 2026-01-23
ICT-CPM-MFA-ME-001-R2 | Material List For Electrical and Mechanical Works | Approved | 2026-01-23
ICT-CPM-MFA-AR-001-R3 | Material List For Architectural Works | Resubmit
Comments
4.8 Request for Information (RFI)
Code | Description | Status | Date Responded
CKR-CPM-RFI-001 | Request for information regarding Roof Leakage NTTI Institute | Respond | 2025-12-26
CKR-CPM-RFI-002 | Request for Authorization to Begin Work NPIT (Kandal) - PIKSP (Kampon Speu) - RPITSSR (Seam Reap) | Respond | 2025-12-26
Comments
4.9 Request for Approval (RFA)
Code | Description | Status | Date Responded
ICT-CPM-RFA-001-R0 | Scope of work form sample | Submit
ICT-CPM-RFA-002-R0 | Site Investigation Results for all 17 Institutes | Submit
ICT-CPM-RFA-003-R0 | Scope of work form sample for all 17 Institutes | Submit
ICT-CPM-RFA-004-R0 | Submission Final Investigation Report | Submit
ICT-CPM-RFA-004-R1 | Submission Final Investigation Report | Resubmit
ICT-CPM-RFA-004-R2 | Submission Revised Scope of Work, Detailed Architectural Design Drawings, Detailed MEP Design Drawings | Resubmit
ICT-CPM-RFA-004-R3 | Submission Revised Electrical Drawings | Resubmit
ICT-CPM-RFA-005-R0 | Submission Classrooms Signboard Proposal | Approved with condition | 2026-02-04
ICT-CPM-RFA-005-R1 | Submission Revised Classrooms Signboard Proposal | Resubmit
ICT-CPM-RFA-006-R0 | Revised Schedule | Submit
ICT-CPM-RFA-007-R0 | Threshold Options of the classroom entrance doors | Approved | 2026-02-23
ICT-CPM-RFA-005-R2 | Submission Revised Classrooms Signboard Proposal | Resubmit
Comments
4.10 Field Change Request (FCR)
Code | Description | Status | Date Responded
Comments
4.11 Variation Order (VO)
Code | Description | Status | Date Responded
Comments
4.12 Transmittal (TR)
Code | Description | Status | Date Responded
Comments
4.13 Material Inspection Approval (MIR)
Code | Description | Status | Date Responded
ICT-CPM-NIB-MIR-001 | MEP & Floor Work (Cable, Wood Panel, pipe…) | Submit
ICT-CPM-NTTI-MIR-001 | MEP (Cable…) | Submit
ICT-CPM-NTTI-MIR-002 | Floor Finish (Floor Tile…) | Submit
ICT-CPM-NTTI-MIR-003 | Acoustical Ceiling Panels | Submit
ICT-CPM-PIBMC-MIR-001 | Electrical Works (Cable…) | Submit
ICT-CPM-PIBMC-MIR-002 | Electrical Work ( Air conditioner, Cable, PVC flexible) | Submit
ICT-CPM-PIKSP-MIR-001 | MEP (Cable, LED Panel light…) | Submit
ICT-CPM-PIKT-MIR-001 | Architectural and MEP (Air conditioner, Cable, Window Steel…) | Submit
ICT-CPM-PIP-MIR-001 | Architectural and MEP | Submit
ICT-CPM-PPCFPI-MIR-001 | Architectural and MEP | Submit
ICT-CPM-NPIA-MIR-001 | Architectural and MEP (Cable, Bar frame for ceiling…) | Submit
ICT-CPM-NPIT-MIR-001 | MEP Work (CAT6 Cable & pipe…) | Submit
Comments

## 5. HSE
5. HEALTH, SAFETY, ENVIRONMENTAL & SECURITY (HSES)
5.1 HSES Training / Introduction / Toolbox Meeting
Type of Training | Date | Venue | Trainer | Attendee | Remarks
HSE induction training cousre | 2026-01-27 | PIBMC | Vetou | 2 | Banteay Meanchey
HSE induction training cousre | 2026-01-31 | PIBMC | Vetou | 1
HSE induction training cousre | 2026-02-04 | PIBMC | Vetou | 1
HSE induction training cousre | 2026-01-27 | PIKT | Boribo | 2 | Kampong Thom
HSE induction training cousre | 2026-01-28 | PIKT | Boribo | 2
HSE induction training cousre | 2026-01-31 | PIKT | Boribo | 1
HSE induction training cousre | 2026-01-23 | NTTI | Lyheang | 8 | Phnom Penh
HSE induction training cousre | 2026-01-26 | NTTI | Lyheang | 8
HSE induction training cousre | 2026-01-23 | NIB | Ramon | 3
HSE induction training cousre | 2026-01-27 | NIB | Ramon | 3
HSE induction training cousre | 2026-02-24 | NPIT | Ramon | 3 | Kandal
HSE induction training cousre | 2026-01-29 | PIP | Sopheak | 8 | Preah Sihanouk
HSE induction training cousre | 2026-02-02 | PCCFPI | Sopheak | 7
HSE induction training cousre | 2026-01-23 | PIKSP | Phearum | 6 | Kampong Speu
HSE induction training cousre | 2026-02-19 | NPIA | Boribo | 6 | Siem Reap
HSE induction training cousre | 2026-03-03 | RPITSK | Sopheak | 5 | Kampot
5.2 HSES Inspection / Audit / Heavy Equipment / Hand&Power Tool Checklist
Type of Inspection |  |  | Date | Inspector | Remarks
Tool and equipment inspection |  |  | 2026-01-31 | Vetou | Banteay Meanchey
Tool and equipment inspection |  |  | 2026-01-28 | Boribo | Kampong Thom
Tool and equipment inspection |  |  | 2026-01-30 | Ramon | Phnom Penh
Tool and equipment inspection |  |  | 2026-02-04 | Lyheang
Tool and equipment inspection |  |  | 2026-01-29 | Sopheak | Preah Sihanouk
Tool and equipment inspection |  |  | 2026-02-02 | Sopheak
Tool and equipment inspection |  |  | 2026-01-27 | Phearum | Kampong Speu
Material Inspection Approval |  |  | 2026-02-11 | Phearum
Tool and equipment inspection |  |  | 2026-02-10 | Boribo | Siem Reap
Tool and equipment inspection |  |  | 2026-03-11 | Vetou | Battambang
Tool and equipment inspection |  |  | 2026-03-04 | Sopheak | Kampot
5.3 Permit to Work
Type of Permit | Start Date | End Date | Inspector | Approver | Remarks
5.4 First Aid / Accident / Incident / Near Miss / Fatalities (if Any)
…................................................................................................................................................................................
5.5 Other HSES Actities Concerns
…................................................................................................................................................................................
5.6 HSES Photo Reference
HSE Toolbox Meeting
BIT: Toolbox Meeting |  | BIT: Toolbox Meeting
RPITSB: Toolbox Meeting |  | RPITSB: Toolbox Meeting
RPITSSR: Toolbox Meeting |  | RPITSSR: Toolbox Meeting
NTTI: Toolbox Meeting |  | NTTI: Toolbox Meeting
NIB: Toolbox Meeting |  | NIB: Toolbox Meeting
NPIT: Toolbox Meeting |  | NPIT: Toolbox Meeting
RPITSK: Toolbox Meeting |  | RPITSK: Toolbox Meeting
HSE Activity Photo
BIT: Worker wearing PPE |  | BIT: HSE activities
RPITSB: Worker wearing PPE |  | RPITSB: HSE activities
RPITSSR: Site cleaning |  | RPITSSR: Site cleaning
NIB: HSE activities |  | NIB: HSE activities
NPIT: HSE activities |  | NPIT: HSE activities

## 6. Resources
6. RESOURCES STATUS
6.1 Manpower Status
Description | 2026-03-01 | [6 empty] | Previous Week | This Week | Up to This Week
| Fri | Sat | Sun | Mon | Tue | Wed | Thu |  |  |  | Banteay Meanchey (PIBMC) | [6 empty] | Kampot (RPITSK) | [6 empty] | Pursat (PIPP) | [6 empty] | Battambang (BIT) | [6 empty] | Battambang (RPITSB) | [6 empty] | Kampong Thom (PIKT) | [6 empty] | Siem Reap (NPIA) | [6 empty] | Siem Reap (RPITSSR) | [6 empty] | Preah Sihanouk (PIP) | [6 empty] | Preah Sihanouk (PCCFPI) | [6 empty] | Kampong Speu (PIKSP) | [6 empty] | Phnom Penh (NTTI) | [6 empty] | Kandal (NPITI) | [6 empty] | Phnom Penh (NIB)
| 13 | 14 | 15 | 16 | 17 | 18 | 19 |  |  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 13 | 14 | 15 | 16 | 17 | 18 | 19
I. Site Management Team
1. Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Construction Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Architect engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4
4. Site Engineer | 6 | 5 | 0 | 6 | 5 | 6 | 6 | 253 | 34 | 287 | bar: Battambang (BIT) 13; Battambang (BIT) 16 to Battambang (RPITSB) 14; Battambang (RPITSB) 16 to Battambang (RPITSB) 19; Siem Reap (NPIA) 18 to Siem Reap (RPITSSR) 14; Siem Reap (RPITSSR) 16 to Siem Reap (RPITSSR) 19; Kampong Speu (PIKSP) 13 to Kampong Speu (PIKSP) 14; Kampong Speu (PIKSP) 16; Phnom Penh (NTTI) 13 to Phnom Penh (NTTI) 14; Phnom Penh (NTTI) 16 to Kandal (NPITI) 14; Kandal (NPITI) 16 to Kandal (NPITI) 19
5. MEP Engineer | 2 | 2 | 0 | 2 | 1 | 2 | 1 | 91 | 10 | 101 | bar: Kampong Speu (PIKSP) 13 to Kampong Speu (PIKSP) 14; Kampong Speu (PIKSP) 16; Kampong Speu (PIKSP) 18; Phnom Penh (NIB) 13 to Phnom Penh (NIB) 14; Phnom Penh (NIB) 16 to Phnom Penh (NIB) 19
II. Site Working Team (Interior)
1. Site Engineer | 4 | 4 | 1 | 4 | 3 | 3 | 3 | 168 | 22 | 190 | bar: Kampot (RPITSK) 13 to Kampot (RPITSK) 19; Battambang (RPITSB) 13 to Battambang (RPITSB) 14; Battambang (RPITSB) 16 to Battambang (RPITSB) 19; Kampong Speu (PIKSP) 13 to Kampong Speu (PIKSP) 14; Kampong Speu (PIKSP) 16; Phnom Penh (NTTI) 13 to Phnom Penh (NTTI) 14; Phnom Penh (NTTI) 16 to Phnom Penh (NTTI) 19
2. Skilled Worker | 16 | 18 | 4 | 15 | 12 | 15 | 19 | 481 | 99 | 580 | Kampot (RPITSK) 13: 5; Kampot (RPITSK) 14: 4; Kampot (RPITSK) 15: 4; Kampot (RPITSK) 16: 3; Kampot (RPITSK) 17: 2; Kampot (RPITSK) 18: 4; Kampot (RPITSK) 19: 4; Battambang (BIT) 13: 4; Battambang (BIT) 14: 4; Battambang (BIT) 16: 4; Battambang (BIT) 17: 4; Battambang (BIT) 18: 4; Battambang (RPITSB) 13: 2; Battambang (RPITSB) 14: 2; Battambang (RPITSB) 16: 2; Battambang (RPITSB) 17: 2; Battambang (RPITSB) 18: 2; Battambang (RPITSB) 19: 6; Siem Reap (NPIA) 18: 1; Siem Reap (NPIA) 19: 2; Siem Reap (RPITSSR) 13: 3; Siem Reap (RPITSSR) 14: 5; Siem Reap (RPITSSR) 16: 5; Siem Reap (RPITSSR) 17: 3; Siem Reap (RPITSSR) 18: 3; Siem Reap (RPITSSR) 19: 5; Kampong Speu (PIKSP) 14: 2; Phnom Penh (NTTI) 14: 1; Phnom Penh (NTTI) 16: 1; Phnom Penh (NTTI) 17: 1; Phnom Penh (NTTI) 18: 1; Phnom Penh (NTTI) 19: 1; Phnom Penh (NIB) 13: 2; Phnom Penh (NIB) 19: 1
3. General Worker | 5 | 7 | 2 | 8 | 6 | 5 | 4 | 431 | 37 | 468 | Kampot (RPITSK) 13: 2; Kampot (RPITSK) 14: 2; Kampot (RPITSK) 15: 2; Kampot (RPITSK) 16: 2; Kampot (RPITSK) 17: 2; Kampot (RPITSK) 18: 2; Kampot (RPITSK) 19: 2; Kampong Speu (PIKSP) 16: 1; Phnom Penh (NTTI) 13: 3; Phnom Penh (NTTI) 14: 5; Phnom Penh (NTTI) 16: 5; Phnom Penh (NTTI) 17: 4; Phnom Penh (NTTI) 18: 3; Phnom Penh (NTTI) 19: 2
III. Site Working Team (MEP)
1. Site Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 23
2. Skilled Worker | 9 | 8 | 2 | 7 | 8 | 9 | 9 | 361 | 52 | 413 | Kampot (RPITSK) 13: 2; Kampot (RPITSK) 14: 2; Kampot (RPITSK) 15: 2; Kampot (RPITSK) 16: 2; Kampot (RPITSK) 17: 2; Kampot (RPITSK) 18: 2; Kampot (RPITSK) 19: 2; Battambang (BIT) 13: 2; Battambang (BIT) 14: 1; Battambang (BIT) 16: 1; Battambang (BIT) 17: 1; Battambang (BIT) 18: 1; Battambang (RPITSB) 18: 1; Battambang (RPITSB) 19: 1; Phnom Penh (NTTI) 13: 3; Phnom Penh (NTTI) 14: 3; Phnom Penh (NTTI) 16: 2; Phnom Penh (NTTI) 17: 3; Phnom Penh (NTTI) 18: 3; Phnom Penh (NTTI) 19: 5; Kandal (NPITI) 13: 1; Kandal (NPITI) 14: 1; Kandal (NPITI) 16: 1; Kandal (NPITI) 17: 1; Kandal (NPITI) 18: 1; Phnom Penh (NIB) 13: 1; Phnom Penh (NIB) 14: 1; Phnom Penh (NIB) 16: 1; Phnom Penh (NIB) 17: 1; Phnom Penh (NIB) 18: 1; Phnom Penh (NIB) 19: 1
3. General Worker | 4 | 2 | 0 | 5 | 2 | 5 | 2 | 103 | 20 | 123 | Kampong Speu (PIKSP) 13: 2; Kampong Speu (PIKSP) 16: 3; Kampong Speu (PIKSP) 18: 4; Kandal (NPITI) 13: 1; Kandal (NPITI) 14: 1; Kandal (NPITI) 16: 1; Kandal (NPITI) 17: 1; Kandal (NPITI) 18: 1; Kandal (NPITI) 19: 2; Phnom Penh (NIB) 13: 1; Phnom Penh (NIB) 14: 1; Phnom Penh (NIB) 16: 1; Phnom Penh (NIB) 17: 1
Total | [7 empty] | 1915 | 274 | 2189
6.2 Material Delivery Status
Description | [6 empty] | Unit | Previous | This Period | Accumulate
Cement | [6 empty] | bag | 174 | 34 | 208 | Battambang (BIT) 19: 14; Battambang (RPITSB) 19: 10; Siem Reap (RPITSSR) 19: 10
Skim coat | [6 empty] | bag | 64 | 0 | 64
Sand | [6 empty] | m3 | 34.5 | 12 | 46.5 | Battambang (BIT) 19: 2; Battambang (RPITSB) 19: 2; Siem Reap (RPITSSR) 19: 8
Brick | [6 empty] | pcs | 11500 | 0 | 11500
UTP CAT6 cable | [6 empty] | m | 238 | 4 | 242 | Kampot (RPITSK) 19: 4
PVC pipes | [6 empty] | pcs | 201 | 0 | 201
PVC flexible | [6 empty] | roll | 283 | 0 | 283
uPVC Conduit DN25mm | [6 empty] | pcs | 550 | 0 | 550
PVC Trunking 40x20mm | [6 empty] | length | 105 | 0 | 105
PVC Trunking 50x50mm | [6 empty] | length | 14 | 0 | 14
1Cx1.5mm2 Cu/PVC Black | [6 empty] | roll | 13 | 0 | 13
1Cx1.5mm2 Cu/PVC Red | [6 empty] | roll | 14 | 0 | 14
1Cx2.5mm2 Cu/PVC Black | [6 empty] | roll | 23 | 0 | 23
1Cx2.5mm2 Cu/PVC Red | [6 empty] | roll | 23 | 0 | 23
1Cx2.5mm2 Cu/PVC Green/Yellow | [6 empty] | roll | 23 | 0 | 23
HDMI AOC cable 15m | [6 empty] | pcs | 7 | 0 | 7
UTP cat6 cable 305m/roll | [6 empty] | roll | 37 | 0 | 37
uPVC conduit DN 20mm 2.9m | [6 empty] | length | 253 | 0 | 253
uPVC conduit DN 25mm 2.9m | [6 empty] | length | 260 | 0 | 260
uPVC flexible DN 20mm 50m/roll | [6 empty] | roll | 39 | 0 | 39
uPVC flexible DN 25mm 50m/roll | [6 empty] | roll | 86 | 0 | 86
Electrical back box 85x85x40mm | [6 empty] | pcs | 204 | 0 | 204
Electrical double back box 141x80x50mm | [6 empty] | pcs | 25 | 0 | 25
Electrical Wire 1Cx1.5mm² | [6 empty] | roll | 18 | 0 | 18
Electrical Wire 1Cx2.5mm² | [6 empty] | roll | 73 | 0 | 73
Electrical Conduit 20mm | [6 empty] | pcs | 267 | 0 | 267
Electrical Conduit 25mm | [6 empty] | pcs | 230 | 0 | 230
Flexible Conduit 20mm | [6 empty] | roll | 15 | 0 | 15
Flexible Conduit 25mm | [6 empty] | roll | 9 | 0 | 9
PVC drain pipe | [6 empty] | pcs | 10 | 0 | 10
Copper pipe | [6 empty] | m | 80 | 0 | 80
Insulation | [6 empty] | m | 200 | 0 | 200
Floor tile | [6 empty] | box | 958 | 0 | 958
PVC trunking | [6 empty] | pcs | 31 | 0 | 31
Socket | [6 empty] | pcs | 104 | 41 | 145 | Phnom Penh (NIB) 19: 41
Ceiling support | [6 empty] | set | 2 | 2 | 4 | Kampot (RPITSK) 19: 2
Conduit pvc | [6 empty] | set | 8 | 0 | 8
Air conditioner | [6 empty] | pcs | 6 | 0 | 6
Copper Pipe ϕ6.35, thk 0.7mm | [6 empty] | roll | 1.5 | 0 | 1.5
Copper Pipe ϕ15.88, thk 0.7mm | [6 empty] | roll | 1.5 | 0 | 1.5
PVC drain pipe DN 18mm (Class 8.5) | [6 empty] | m | 19 | 0 | 19
Copper pipe (15.88mmx0.72mmx15m) | [6 empty] | roll | 10 | 0 | 10
Copper pipe (6.35mmx0.72mmx15m) | [6 empty] | roll | 10 | 0 | 10
Insulation (6mmx13mm) | [6 empty] | m | 49 | 0 | 49
Insulation (16mmx13mm) | [6 empty] | m | 49 | 0 | 49
Cable CU/PVC 1Cx2.5mm2-Black | [6 empty] | roll | 8 | 0 | 8
Cable CU/PVC 1Cx2.5mm2-Red | [6 empty] | roll | 8 | 0 | 8
Cable CU/PVC 1Cx2.5mm2-Blue | [6 empty] | roll | 4 | 0 | 4
Cable CU/PVC 1Cx2.5mm2-G/Y | [6 empty] | roll | 5 | 0 | 5
AC White Tape | [6 empty] | kg | 2 | 0 | 2
Acoustic Wood Panel | [6 empty] | sheet | 56 | 0 | 56
PVC Drain pipe DN 18mm (Class 8.5) | [6 empty] | m | 55 | 0 | 55
Electric cable | [6 empty] | pcs | 20 | 2 | 22 | Kampot (RPITSK) 19: 2
Fiber Optic HDMI | [6 empty] | roll | 8 | 0 | 8
HDMI Socket | [6 empty] | pcs | 12 | 0 | 12
Painting | [6 empty] | pcs | 40 | 0 | 40
Drywall | [6 empty] | pcs | 8 | 0 | 8
Acoustic ceiling panels | [6 empty] | pcs | 8 | 0 | 8
Aluminum frames | [6 empty] | pcs | 4 | 0 | 4
T Bar Frame for Ceiling | [6 empty] | m | 100 | 0 | 100
Air-Con wall mound type 2.5Hp | [6 empty] | set | 11 | 3 | 14 | Phnom Penh (NTTI) 19: 3
Support Outdoor Unit | [6 empty] | set | 14 | 0 | 14
Audio Cable | [6 empty] | roll | 2 | 0 | 2
Double data socket | [6 empty] | pcs | 18 | 0 | 18
Double socket | [6 empty] | pcs | 94 | 0 | 94
1gang 1way switch | [6 empty] | pcs | 32 | 0 | 32
2gang 2way switch | [6 empty] | pcs | 2 | 0 | 2
3gang 2way switch | [6 empty] | pcs | 2 | 0 | 2
Surface Electrical box | [6 empty] | pcs | 5 | 0 | 5
LED Panel light 300x600mm 40W 6500K | [6 empty] | pcs | 84 | 24 | 108 | Phnom Penh (NIB) 19: 24
Distribution Board | [6 empty] | set | 24 | 1 | 25 | bar: Phnom Penh (NIB) 19
Switches | [6 empty] | pcs | 1 | 1 | 2 | bar: Phnom Penh (NIB) 19
Circuit Breaker | [6 empty] | pcs | 11 | 11 | 22 | Phnom Penh (NIB) 19: 11
Window Glass | [6 empty] | EA | 0 | 5 | 5 | Phnom Penh (NTTI) 19: 5
MCB 2P 63A 6ka | [6 empty] | pcs | 0 | 2 | 2 | Phnom Penh (NTTI) 19: 2
MCB 2P 50A 6ka | [6 empty] | pcs | 0 | 3 | 3 | Phnom Penh (NTTI) 19: 3
MCB 1P 20A 6ka | [6 empty] | pcs | 0 | 14 | 14 | Phnom Penh (NTTI) 19: 14
MCB 1P 10A 6ka | [6 empty] | pcs | 0 | 5 | 5 | Phnom Penh (NTTI) 19: 5
RCBO 1P+N 20A 30mA 4.5ka | [6 empty] | pcs | 0 | 25 | 25 | Phnom Penh (NTTI) 19: 25
6.3 Machinery / Equipment Status
Description | 2026-03-01 | [6 empty] | Previous Week | This Week | Up to This Week
| Fri | Sat | Sun | Mon | Tue | Wed | Thu
| 13 | 14 | 15 | 16 | 17 | 18 | 19
Scaffolding | 4 | 1 | 0 | 1 | 0 | 2 | 1 | 153 | 9 | 162 | Siem Reap (NPIA) 18: 1; Siem Reap (NPIA) 19: 1; Siem Reap (RPITSSR) 13: 3; Kampong Speu (PIKSP) 13: 1; Kampong Speu (PIKSP) 14: 1; Kampong Speu (PIKSP) 16: 1; Kampong Speu (PIKSP) 18: 1
Hand cutting machine | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 7 | 15 | bar: Kampot (RPITSK) 13 to Kampot (RPITSK) 19
Chipping hammer machine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7
Mobile stair | 2 | 3 | 0 | 3 | 4 | 4 | 2 | 103 | 18 | 121 | Battambang (BIT) 14: 1; Battambang (BIT) 16: 1; Battambang (BIT) 17: 2; Battambang (BIT) 18: 2; Battambang (RPITSB) 13: 1; Battambang (RPITSB) 14: 1; Battambang (RPITSB) 16: 1; Battambang (RPITSB) 17: 1; Battambang (RPITSB) 18: 1; Battambang (RPITSB) 19: 1; Siem Reap (RPITSSR) 13: 1; Siem Reap (RPITSSR) 14: 1; Siem Reap (RPITSSR) 16: 1; Siem Reap (RPITSSR) 17: 1; Siem Reap (RPITSSR) 18: 1; Siem Reap (RPITSSR) 19: 1
Eletric cable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4
Hand drill machine | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 2 | 6 | bar: Kampot (RPITSK) 15 to Kampot (RPITSK) 16
Mixer machine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Angle grinder | 8 | 8 | 0 | 9 | 8 | 7 | 4 | 181 | 44 | 225 | Battambang (BIT) 13: 3; Battambang (BIT) 14: 3; Battambang (BIT) 16: 3; Battambang (BIT) 17: 3; Battambang (BIT) 18: 3; Battambang (RPITSB) 13: 3; Battambang (RPITSB) 14: 3; Battambang (RPITSB) 16: 3; Battambang (RPITSB) 17: 3; Battambang (RPITSB) 18: 3; Battambang (RPITSB) 19: 3; Siem Reap (RPITSSR) 13: 1; Siem Reap (RPITSSR) 14: 1; Siem Reap (RPITSSR) 16: 1; Siem Reap (RPITSSR) 17: 1; Siem Reap (RPITSSR) 18: 1; Siem Reap (RPITSSR) 19: 1; Phnom Penh (NTTI) 13: 1; Phnom Penh (NTTI) 14: 1; Phnom Penh (NTTI) 16: 2; Phnom Penh (NTTI) 17: 1
Electric hammer | 8 | 8 | 0 | 8 | 7 | 7 | 4 | 199 | 42 | 241 | Battambang (BIT) 13: 3; Battambang (BIT) 14: 3; Battambang (BIT) 16: 3; Battambang (BIT) 17: 3; Battambang (BIT) 18: 3; Battambang (RPITSB) 13: 3; Battambang (RPITSB) 14: 3; Battambang (RPITSB) 16: 3; Battambang (RPITSB) 17: 3; Battambang (RPITSB) 18: 3; Battambang (RPITSB) 19: 3; Siem Reap (RPITSSR) 13: 1; Siem Reap (RPITSSR) 14: 1; Siem Reap (RPITSSR) 16: 1; Siem Reap (RPITSSR) 17: 1; Siem Reap (RPITSSR) 18: 1; Siem Reap (RPITSSR) 19: 1; Phnom Penh (NTTI) 13: 1; Phnom Penh (NTTI) 14: 1; Phnom Penh (NTTI) 16: 1
Power cable | 5 | 8 | 0 | 9 | 8 | 7 | 4 | 120 | 41 | 161 | Battambang (BIT) 14: 3; Battambang (BIT) 16: 3; Battambang (BIT) 17: 3; Battambang (BIT) 18: 3; Battambang (RPITSB) 13: 3; Battambang (RPITSB) 14: 3; Battambang (RPITSB) 16: 3; Battambang (RPITSB) 17: 3; Battambang (RPITSB) 18: 3; Battambang (RPITSB) 19: 3; Phnom Penh (NTTI) 13: 2; Phnom Penh (NTTI) 14: 2; Phnom Penh (NTTI) 16: 3; Phnom Penh (NTTI) 17: 2; Phnom Penh (NTTI) 18: 1; Phnom Penh (NTTI) 19: 1
Electric drill | 4 | 5 | 0 | 5 | 5 | 5 | 3 | 136 | 27 | 163 | Battambang (BIT) 13: 1; Battambang (BIT) 14: 1; Battambang (BIT) 16: 1; Battambang (BIT) 17: 2; Battambang (BIT) 18: 2; Battambang (RPITSB) 13: 1; Battambang (RPITSB) 14: 1; Battambang (RPITSB) 16: 1; Battambang (RPITSB) 17: 1; Battambang (RPITSB) 18: 1; Battambang (RPITSB) 19: 1; Siem Reap (RPITSSR) 13: 1; Siem Reap (RPITSSR) 14: 1; Siem Reap (RPITSSR) 16: 1; Siem Reap (RPITSSR) 17: 1; Siem Reap (RPITSSR) 18: 1; Siem Reap (RPITSSR) 19: 1; Phnom Penh (NTTI) 13: 1; Phnom Penh (NTTI) 14: 2; Phnom Penh (NTTI) 16: 2; Phnom Penh (NTTI) 17: 1; Phnom Penh (NTTI) 18: 1; Phnom Penh (NTTI) 19: 1
Cut-off machine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Welding machine | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 8 | 6 | 14 | bar: Battambang (RPITSB) 13 to Battambang (RPITSB) 14; Battambang (RPITSB) 16 to Battambang (RPITSB) 19
Air compressor | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 8 | 6 | 14 | bar: Battambang (RPITSB) 13 to Battambang (RPITSB) 14; Battambang (RPITSB) 16 to Battambang (RPITSB) 19
Total | [7 empty] | 932 | 202 | 1134

## 6. Workdone (hidden)
SUMMERY WEEKLY WORK DONE PROGRESS
Project: Strengthening Maternal and Child Health In North-Eastern of Cambodia | [38 empty] | CACPM CO.,LTD
ITEM NO |  | SCOPE OF WORK/ DESCRIPTION | CONTRACT AMOUNT
|  |  | QTY | UNIT | UNIT | AMOUNT |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | REMARK
[9 empty] | 14/1-21/1 | 22/1-28/1 | 29/1-4/2 | 5/2-11/2 | 12/2-18/2 | 19/2-25/2 | 26/2-4/3 | 5/3-11/3 | 12/3-18/3 | 19/3-25/3 | 26/3-1/4 | 2/4-8/4 | 9/4-15/4 | 16/4-22/4 | 23/4-29/4 | 30/4-6/5 | 7/5-13/5 | 14/5-20/5 | 21/5-27/5 | 28/5-3/6 | 4/6-10/6 | 11/6-17/6 | 18/6-24/6 | 25/6-1/7 | 2/7-8/7 | 9/7-15/7 | 16/7-22/7 | 23/7-29/7 | 30/7-6/8 | 7/8-13/8
SMCH |  |  |  |  | lot | 964340.51 | 100% | S
A
RH HOSPITAL | A | STRUCTURAL WORK |  |  | lot | 35294.21 | 3.66% | S |  | 0.0366% | 0.0366% | 0.0366% | 0.3294% | 0.0732% | 0.0366% | 0.2562% | 0.2562% | 0.6954% | 0.3294% | 0.0732% | 0.1098% |  |  | 0.183% | 0.183% | 0.0732% | 0.1098% | 0.0366% | 0.0366% | 0.3294% | 0.3294% | 0.1098%
[8 empty] | A |  | 0.0366% | 0.1464% | 0.366% | 0.1098% | 0.4392% | 1.208% | 0.366% | [7 empty] | 0.183% | 0.2562% | 0.183% | 0.0366% | 0.2928%
| B | ARCHITECTURE WORKS |  |  | lot | 52161.59 | 5.409% | S | [13 empty] | 0.2705% | 0.2705% | 0.2164% | [5 empty] | 0.1623% | 0.1623% | 0.595% | 0.6491% | 0.5409% | 0.4868% | 1.082% | 0.6491% | 0.3245%
[8 empty] | A | [7 empty] | 0.05409% | 0.3786% |  | 0.05409% | 0.05409% |  | 0.2164% | 0.05409% | [7 empty] | 0.05409% | 0.05409% |  | 0.3786%
| C | MEP |  |  | lot | 41072.35 | 4.259% | S | [6 empty] | 0.3549% | 0.3549% |  |  |  | 0.3549% | [7 empty] | 0.3549% | 0.3549% | 0.3549% | 0.3549% | 0.3549% | 0.3549% | 0.3549% | 0.3549% | 0.3549%
[8 empty] | A | [5 empty] | 0.3549% | 0.3549% |  |  |  | 0.3549% | [8 empty] | 0.3549%
| D | CIVIL WORK |  |  | lot | 35341.4749 | 3.665% | S | [8 empty] | 0.02281% | 0.2851% | 0.3308% | 0.07984% | 0.07984% | 0.1027% | 0.01141% | 0.2851% | 0.2512% | 0.2094% | 0.1256% | 0.2931% | 0.4187% | 0.4815% | 0.02483% | 0.3298% | 0.3331%
[8 empty] | A | [9 empty] | 0.01141% | 0.1939% |  |  | 0.4562% |  |  | 0.07984% |  |  | 0.2512% |  | 0.1141% |  | 0.04562% | 0.1141%
KHOH NHEK | A | STRUCTURAL WORK |  |  | lot | 70021.4791 | 7.261% | S |  | 0.07261% | 0.1452% | 0.1452% | 0.4357% | 0.7987% | 0.2904% | 0.2178% | 1.017% | 0.7987% | 0.1452% | 0.07261% | 0.07261% |  |  | 0.3631% | 0.3631% | 0.1452% | 0.2904% | 0.07261% | 0.5809% | 0.5809% | 0.5809% | 0.07261%
[8 empty] | A |  | 0.2178% | 0.3631% | 0.5809% | 0.5809% | 0.2904% | 1.162% | 0.8713% | 0.2178% | [6 empty] | 0.2904% | 0.2904% | 0.5809% | 0.1452% | 0.2904% | 0.07261% |  |  |  |  | 1.307%
| A | ARCHITECTURE WORKS |  |  | lot | 94613.6544 | 9.811% | S | [13 empty] | 0.4906% | 0.4906% | 0.4906% | [5 empty] | 0.3924% | 0.3924% | 1.079% | 1.374% | 0.883% | 0.9811% | 1.079% | 1.472% | 0.6868%
[8 empty] | A | [9 empty] | 0.5887% | 0.5887% | 0.09811% |  | 0% | 0.1962% |  |  | 0.09811% |  | 0.4906% |  | 0.3924% | 0.2943% | 0.2943% | 0.09811% | 0.2943%
| A | MEP |  |  | lot | 38901.5375 | 4.034% | S | [6 empty] | 0.3362% | 0.3362% | [10 empty] | 0.3362% | 0.3362% | 0.3362% | 0.3362% | 0.3362% | 0.3362% | 0.3362% | 0.3362% | 0.3362% | 0.3362%
[8 empty] | A | [5 empty] | 0.3362% | 0.3362%
| A | CIVIL WORK |  |  | lot | 6107.5536 | 0.6333% | S | [15 empty] | 0.04898% | 0.04898% | 0.04898% | 0.04898% | 0.04898% | 0.09709% | 0.09709% | 0.09709% | 0.09709%
A
TAVENG | A | STRUCTURAL WORK |  |  | lot | 59711.0462 | 6.192% | S |  | 0.06192% | 0.1238% | 0.1238% | 0.3715% | 0.6811% | 0.2477% | 0.1858% | 0.8669% | 0.6811% | 0.1238% | 0.06192% | 0.06192% |  |  | 0.3096% | 0.3096% | 0.1238% | 0.2477% | 0.06192% | 0.4954% | 0.4954% | 0.4954% | 0.06192%
[8 empty] | A |  | 0.06192% | 0.3715% | 0.4954% | 0.8669% | 0.3096% | 0.1858% | 0.4334% | 1.3% | 0.4334% | 0.3096% | [5 empty] | 0.06192% | 0.2477% | 0.2477% | 0.3715% |  |  |  |  | 0.1238% | 0.6192%
| B | ARCHITECTURE WORKS |  |  | lot | 59711.0462 | 6.192% | S | [13 empty] | 0.3096% | 0.3096% | 0.2477% | [5 empty] | 0.1858% | 0.1858% | 0.6811% | 0.743% | 0.6192% | 0.5573% | 1.238% | 0.743% | 0.3715%
[8 empty] | A | [11 empty] | 0.3715% |  | 0.1858% | 0.06192% | [5 empty] | 0.1858% | 0.1238% | 0.1238% | 0.3715%
| C | MEP |  |  | lot | 34479.0908 | 3.575% | S | [6 empty] | 0.298% | 0.298% | [10 empty] | 0.298% | 0.298% | 0.298% | 0.298% | 0.298% | 0.298% | 0.298% | 0.298% | 0.298% | 0.298%
[8 empty] | A | [5 empty] | 0.298% | 0.298% |  |  |  | 0.298%
| D | CIVIL WORK |  |  | lot | 13756.6432 | 1.427% | S | [8 empty] | 0.008803% | 0.11% | 0.1276% | 0.03081% | 0.1034% | 0.03961% | 0.004401% | 0.11% | 0.06961% | 0.05801% | 0.03481% | 0.08121% | 0.116% | 0.1334% | 0.01714% | 0.2278% | 0.1538%
[8 empty] | A | [14 empty] | 0.1496% | 0.09683%
OCHUM | A | STRUCTURAL WORK |  |  | lot | 36033.1227 | 3.737% | S |  | 0.07473% | 0.1868% | 0.1868% | 0.1121% | 0.3363% | 0.5231% | 0.3363% | 0.4484% | 0.07473% | 0.07473% | 0.07473% |  |  |  | 0.2616% | 0.2616% | 0.03737% | 0.2242% | 0.03737% | 0.1495% | 0.1495% | 0.1495% | 0.03737%
[8 empty] | A |  | 0% | 0.03737% | 0.1121% | 0.2989% | 0.411% | 0.3363% | 1.046% | 0.1868% | [6 empty] | 0.2616% | 0.2989% | 0.2242% |  | 0.2989% |  |  |  |  | 0.2616%
| B | ARCHITECTURE WORKS |  |  | lot | 50998.54 | 5.288% | S | [12 empty] | 0.1587% | 0.1587% | 0.1587% | [6 empty] | 0.5288% | 0.5288% | 0.2644% | 0.2644% | 0.05288% | 0.476% | 0.3702% | 0.6875% | 1.639%
[8 empty] | A | [9 empty] | 0.4231% | 0.05288% | 0.3173% |  | 0.2115% | 0% | [6 empty] | 0.1587% |  | 0.05288% | 0.1058% | 0.5288%
| C | MEP |  |  | lot | 32875.9043 | 3.409% | S | [6 empty] | 0.2841% | 0.2841% | [10 empty] | 0.2841% | 0.2841% | 0.2841% | 0.2841% | 0.2841% | 0.2841% | 0.2841% | 0.2841% | 0.2841% | 0.2841%
[8 empty] | A | [5 empty] | 0.2841% | 0.2841% |  |  |  | 0.2841% | [8 empty] | 0.2841% |  |  | 0.2841% |  |  | 0.2841%
| D | CIVIL WORK |  |  | lot | 14688.8804 | 1.523% | S | [15 empty] | 0.07345% | 0.07345% | 0.07345% | 0.09591% | 0.09591% | 0.1133% | 0.2659% | 0.2659% | 0.1631% | 0.1223% | 0.1804%
A
ANDONG MEAS | A | STRUCTURAL WORK |  |  | lot | 33750.775 | 3.5% | S |  | 0.07% | 0.175% | 0.175% | 0.105% | 0.315% | 0.49% | 0.315% | 0.42% | 0.07% | 0.07% | 0.07% |  |  |  | 0.245% | 0.245% | 0.035% | 0.21% | 0.035% | 0.14% | 0.14% | 0.14% | 0.035%
[8 empty] | A |  | 0% | 0% | 0% | 0.035% | 0.385% | 0.14% | 0.21% | 1.015% | 0.49% | 0.14% |  |  |  |  | 0% | 0.035% | 0.14% | 0.14% | 0.175% |  |  |  |  | 0.035% | 0.28%
| B | ARCHITECTURE WORKS |  |  | lot | 49022.2444 | 5.083% | S | [12 empty] | 0.1525% | 0.1525% | 0.1525% | [6 empty] | 0.5083% | 0.5083% | 0.2542% | 0.2542% | 0.05083% | 0.4575% | 0.3558% | 0.6609% | 1.576%
[8 empty] | A | [10 empty] | 0.3558% | 0.1017% |  | 0% | 0.05083% | [5 empty] | 0.1017% | 0.305% | 0.1525% | 0.1525% |  | 0.2033%
| C | MEP |  |  | lot | 32051.2825 | 3.324% | S | [6 empty] | 0.277% | 0.277% | [10 empty] | 0.277% | 0.277% | 0.277% | 0.277% | 0.277% | 0.277% | 0.277% | 0.277% | 0.277% | 0.277%
[8 empty] | A | [5 empty] | 0.277% | 0.277% |  |  |  | 0.277% | [12 empty] | 0.277% | 0.277% | 0.277%
| D | CIVIL WORK |  |  | lot | 5955.2195 | 0.6175% | S | [15 empty] | 0.054% | 0.054% | 0.054% | 0.054% | 0.054% | 0.09093% | 0.09093% | 0.09093% | 0.07474%
A
OTHERS | A | SAFETY MANAGEMENT |  |  | lot | 7965.4765 | 0.826% | S |  | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059%
[8 empty] | A |  | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059%
| B | INDIRECT COST |  |  | lot | 120000 | 12.44% | S |  | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609%
[8 empty] | A |  | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609%
| C | PROFIT & OVER HEAD COST |  |  | lot | 39827.3826 | 4.13% | S |  | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153%
[8 empty] | A |  | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153%
TOTAL | [5 empty] | 964340.5037 | 100%
[5 empty] | Schedule Weekly Progress (%) |  |  | S | 0% | 0.9603% | 1.312% | 1.312% | 1.998% | 2.849% | 3.782% | 3.506% | 3.684% | 3.36% | 1.846% | 1.462% | 1.383% | 2.168% | 2.042% | 3.533% | 2.504% | 1.503% | 3.281% | 3.011% | 4.433% | 6.736% | 6.163% | 6.278% | 6.088% | 4.522% | 5.153% | 6.32% | 4.212% | 4.598%
[5 empty] | Actual Weekly Progress (%) |  |  | A | 0% | 0.9608% | 1.312% | 1.312% | 2.536% | 4.03% | 5.226% | 3.626% | 3.743% | 2.591% | 3.553% | 1.587% | 0.6444% | 1.714% | 1.157% | 1.476% | 1.667% | 2.118% | 1.214% | 3.454% | 1.004% | 1.738% | 1.553% | 1.892% | 1.66% | 4.817%
[5 empty] | Accumulative Schedule Progress (%) |  |  | Sc | 0% | 0.9603% | 2.272% | 3.584% | 5.582% | 8.431% | 12.21% | 15.72% | 19.4% | 22.76% | 24.61% | 26.07% | 27.45% | 29.62% | 31.66% | 35.2% | 37.7% | 39.2% | 42.49% | 45.5% | 49.93% | 56.67% | 62.83% | 69.11% | 75.19% | 79.72% | 84.87% | 91.19% | 95.4% | 100%
[5 empty] | Accumulative Actual Progress (%) |  |  | Ac | 0% | 0.9608% | 2.273% | 3.585% | 6.121% | 10.15% | 15.38% | 19% | 22.74% | 25.34% | 28.89% | 30.48% | 31.12% | 32.84% | 33.99% | 35.47% | 37.14% | 39.25% | 40.47% | 43.92% | 44.93% | 46.66% | 48.22% | 50.11% | 51.77% | 56.59%
[5 empty] | Ahead/Delay (%) |  |  |  | 0% | 0.0004927% | 0.0004927% | 0.0004927% | 0.5383% | 1.719% | 3.163% | 3.283% | 3.342% | 2.573% | 4.281% | 4.405% | 3.667% | 3.213% | 2.328% | 0.2711% | -0.566% | 0.0494% | -2.018% | -1.575% | -5.003% | -10% | -14.61% | -19% | -23.42% | -23.13%
[5 empty] | Ahead/Delay (days) |  |  |  | 0 | 1 | 1 | 1 | 2 | 5 | 9 | 9 | 9 | 7 | 12 | 12 | 10 | 9 | 7 | 1 | -2 | 1 | -6 | -5 | -14 | -27 | -38 | -50 | -61 | -61
|  |  | 4 | 310.9556
|  |  | 4 | 1075.9316
|  |  | 27.8 | 3658.2576
|  |  | 70 | 3070.48
|  |  | 13 | 349.44 | [35 empty] | 2022-01-14 | 2022-09-30 | 260
|  |  | 85 | 533.7048
|  |  | 900 | 189.7489
|  |  | 85 | 98.4937 |  |  |  |  | 2022-01-14 | [30 empty] | 37 weeks
|  |  | 900 | 328.2267
|  |  | 13 | 195
21566.2102
|  |  | 12 | 900.06
|  |  | 85 | 1351.585
|  |  | 900 | 1016.1482
|  |  | 13 | 2067.13
|  |  | 85 | 11092.5
|  |  | 900 | 4786.287
|  |  | 1.5 | 352.5
30878.1936
|  |  | 1150 | 10651.5472
|  |  | 1150 | 10672
|  |  | 1150 | 5577.5
|  |  | 1150 | 3977.1464
24200
|  |  | 22 | 24200
6695
|  |  | 11 | 6545
|  |  | 12.5 | 150
260
|  |  | 13 | 260
23050.5
|  |  | 22 | 18590
|  |  | 5.5 | 1072.5
|  |  | 7 | 3388
5610
|  |  | 620 | 620
|  |  | 375 | 750
|  |  | 200 | 200
|  |  | 200 | 400
|  |  | 550 | 1100
|  |  | 650 | 1950
|  |  | 120 | 240
|  |  | 50 | 350
1570
|  |  | 225 | 675
|  |  | 25 | 75
|  |  | 175 | 350
|  |  | 175 | 350
|  |  | 60 | 120
|  |  | 0 | Ecluded
332.7784
8208.0487
|  |  | 27.8 | 1501.2
|  |  | 1.5 | 540
|  |  | 85 | 3672
|  |  | 13 | 226.2
|  |  | 900 | 2268.6487
|  |  | 30 | 157.5
597.5302
|  |  | 4 | 8.8
|  |  | 85 | 280.2476
|  |  | 13 | 32.916
|  |  | 900 | 275.5667
|  |  | 18 | 1314
|  |  | 90 | 6750

## 6. Workdone-Rev01 (hidden)
SUMMERY WEEKLY WORK DONE PROGRESS
Project: Strengthening Maternal and Child Health In North-Eastern of Cambodia | [45 empty] | CACPM CO.,LTD
ITEM NO |  | SCOPE OF WORK/ DESCRIPTION | CONTRACT AMOUNT
|  |  | QTY | UNIT | UNIT | AMOUNT |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | REMARK
[9 empty] | 14/1-21/1 | 22/1-28/1 | 29/1-4/2 | 5/2-11/2 | 12/2-18/2 | 19/2-25/2 | 26/2-4/3 | 5/3-11/3 | 12/3-18/3 | 19/3-25/3 | 26/3-1/4 | 2/4-8/4 | 9/4-15/4 | 16/4-22/4 | 23/4-29/4 | 30/4-6/5 | 7/5-13/5 | 14/5-20/5 | 21/5-27/5 | 28/5-3/6 | 4/6-10/6 | 11/6-17/6 | 18/6-24/6 | 25/6-1/7 | 2/7-8/7 | 9/7-15/7 | 16/7-22/7 | 23/7-29/7 | 30/7-6/8 | 7/8-13/8 | 14/8-20/8 | 21/8-27/8 | 28/8-3/9 | 4/9-10/9 | 11/9-17/9 | 18/9-24/9 | 25/9-1/10
SMCH |  |  |  |  | lot | 964340.51 | 100% | S
A
RH HOSPITAL | A | STRUCTURAL WORK |  |  | lot | 35294.21 | 3.66% | S |  | 0.0366% | 0.1464% | 0.366% | 0.1098% | 0.4392% | 1.208% | 0.366% | [7 empty] | 0.183% | 0.2562% | 0.183% | 0.0366% | 0.2928% | [7 empty] | 0.02% | 0.01% | 0.006599%
[8 empty] | A |  | 0.0366% | 0.1464% | 0.366% | 0.1098% | 0.4392% | 1.208% | 0.366% | [7 empty] | 0.183% | 0.2562% | 0.183% | 0.0366% | 0.2928% | [18 empty] | 0.0366%
| B | ARCHITECTURE WORKS |  |  | lot | 52161.59 | 5.409% | S | [7 empty] | 0.05409% | 0.3786% |  | 0.05409% | 0.05409% |  | 0.2164% | 0.05409% | [7 empty] | 0.05409% | 0.05409% |  | 0.3786% | 0.05% | 0.1% | 0.05% | 0.7% | 1.5% | 1.5% | 0.15% | 0.06087%
[8 empty] | A | [7 empty] | 0.05409% | 0.3786% |  | 0.05409% | 0.05409% |  | 0.2164% | 0.05409% | [7 empty] | 0.05409% | 0.05409% |  | 0.3786% | [12 empty] | 4.111%
| C | MEP |  |  | lot | 41072.35 | 4.259% | S | [5 empty] | 0.2242% | 0.2242% |  |  |  | 0.2242% | [8 empty] | 0.2242% | [7 empty] | 0.22% | 0.22% | 0.22% | 0.22% | 0.4% | 1% | 0.5% | 0.5% | 0.08246%
[8 empty] | A | [5 empty] | 0.2242% | 0.2242% |  |  |  | 0.2242% | [8 empty] | 0.2242% | [18 empty] | 3.362%
| D | CIVIL WORK |  |  | lot | 35341.4749 | 3.665% | S | [9 empty] | 0.01141% | 0.1939% |  |  | 0.4562% |  |  | 0.07984% |  |  | 0.2512% |  | 0.1141% |  | 0.04562% | 0.1141% |  | 0.11% |  |  |  | 0.5% | 0.5% | 0.5% | 0.3% | 0.3% | 0.1885%
[8 empty] | A | [9 empty] | 0.01141% | 0.1939% |  |  | 0.4562% |  |  | 0.07984% |  |  | 0.2512% |  | 0.1141% |  | 0.04562% | 0.1141% | [13 empty] | 2.398%
KHOH NHEK | A | STRUCTURAL WORK |  |  | lot | 70021.4791 | 7.261% | S |  | 0.2178% | 0.3631% | 0.5809% | 0.5809% | 0.2904% | 1.162% | 0.8713% | 0.2178% | [6 empty] | 0.2904% | 0.2904% | 0.5809% | 0.1452% | 0.2904% | 0.07261% |  |  |  |  | 0.5% |  |  |  | 0.01% | 0.01% |  | 0.4% | 0.39%
[8 empty] | A |  | 0.2178% | 0.3631% | 0.5809% | 0.5809% | 0.2904% | 1.162% | 0.8713% | 0.2178% | [6 empty] | 0.2904% | 0.2904% | 0.5809% | 0.1452% | 0.2904% | 0.07261% |  |  |  |  | 0.5% | [12 empty] | 0.81%
| A | ARCHITECTURE WORKS |  |  | lot | 94613.6544 | 9.811% | S | [9 empty] | 0.5887% | 0.5887% | 0.09811% |  | 0% | 0.1962% |  |  | 0.09811% |  | 0.4906% |  | 0.3924% | 0.2943% | 0.2943% | 0.09811% | 0.2943% |  | 0.15% | 0.15% |  | 1% |  | 3% | 2% |  | 0.0773%
[8 empty] | A | [9 empty] | 0.5887% | 0.5887% | 0.09811% |  | 0% | 0.1962% |  |  | 0.09811% |  | 0.4906% |  | 0.3924% | 0.2943% | 0.2943% | 0.09811% | 0.2943% | [12 empty] | 6.377%
| A | MEP |  |  | lot | 38901.5375 | 4.034% | S | [5 empty] | 0.3362% | 0.3362% | [19 empty] | 0.11% |  | 0.33% | 0.22% | 0.22% | 0.4% | 1% | 0.5% | 0.5% | 0.08167%
[8 empty] | A | [5 empty] | 0.3362% | 0.3362% | [31 empty] | 3.362%
| A | CIVIL WORK |  |  | lot | 6107.5536 | 0.6333% | S | [27 empty] | 0.04898% | 0.04898% | 0.04898% | 0.04898% | 0.04898% | 0.09709% | 0.09709% | 0.09709% | 0.09709%
[8 empty] | A | [38 empty] | 0.6333%
TAVENG | A | STRUCTURAL WORK |  |  | lot | 59711.0462 | 6.192% | S |  | 0.06192% | 0.3715% | 0.4954% | 0.8669% | 0.3096% | 0.1858% | 0.4334% | 1.3% | 0.4334% | 0.3096% | [5 empty] | 0.06192% | 0.2477% | 0.2477% | 0.3715% |  |  |  |  | 0.1238% | 0.12% |  |  |  |  | 0.03% | 0.21% |  | 0.01151%
[8 empty] | A |  | 0.06192% | 0.3715% | 0.4954% | 0.8669% | 0.3096% | 0.1858% | 0.4334% | 1.3% | 0.4334% | 0.3096% | [5 empty] | 0.06192% | 0.2477% | 0.2477% | 0.3715% |  |  |  |  | 0.1238% | 0.1238% | [12 empty] | 0.2477%
| B | ARCHITECTURE WORKS |  |  | lot | 59711.0462 | 6.192% | S | [11 empty] | 0.3715% |  | 0.1858% | 0.06192% | [5 empty] | 0.1858% | 0.1238% | 0.1238% | 0.3715% |  |  |  | 0.6% | 0.6% | 0.8% | 0.22% | 0.5% | 1% | 0.5% | 0.5% | 0.04777%
[8 empty] | A | [11 empty] | 0.3715% |  | 0.1858% | 0.06192% | [5 empty] | 0.1858% | 0.1238% | 0.1238% | 0.3715% | [14 empty] | 4.768%
| C | MEP |  |  | lot | 34479.0908 | 3.575% | S | [5 empty] | 0.298% | 0.298% |  |  |  | 0.298% | [15 empty] | 0.11% | 0.22% |  | 0.5% |  | 0.3% | 1% | 0.5% |  | 0.05155%
[8 empty] | A | [5 empty] | 0.298% | 0.298% |  |  |  | 0.298% | [27 empty] | 2.682%
| D | CIVIL WORK |  |  | lot | 13756.6432 | 1.427% | S | [14 empty] | 0.1496% | 0.09683% | [11 empty] | 0.04898% | 0.04898% | 0.35% | 0.2% | 0.2% | 0.09709% | 0.09709% | 0.09709% | 0.04083%
[8 empty] | A | [14 empty] | 0.1496% | 0.09683% | [22 empty] | 1.18%
OCHUM | A | STRUCTURAL WORK |  |  | lot | 36033.1227 | 3.737% | S |  | 0% | 0.03737% | 0.1121% | 0.2989% | 0.411% | 0.3363% | 1.046% | 0.1868% | [6 empty] | 0.2616% | 0.2989% | 0.2242% |  | 0.2989% | [7 empty] | 0.2242%
[8 empty] | A |  | 0% | 0.03737% | 0.1121% | 0.2989% | 0.411% | 0.3363% | 1.046% | 0.1868% | [6 empty] | 0.2616% | 0.2989% | 0.2242% |  | 0.2989% |  |  |  |  | 0.2242% | [13 empty] | 0%
| B | ARCHITECTURE WORKS |  |  | lot | 50998.54 | 5.288% | S | [9 empty] | 0.4231% | 0.05288% | 0.3173% |  | 0.2115% | 0% | [6 empty] | 0.1587% |  | 0.05288% | 0.1058% | 0.5288% | [5 empty] | 0.4% | 2% | 1% |  | 0.03748%
[8 empty] | A | [9 empty] | 0.4231% | 0.05288% | 0.3173% |  | 0.2115% | 0% | [6 empty] | 0.1587% |  | 0.05288% | 0.1058% | 0.5288% | [12 empty] | 3.437%
| C | MEP |  |  | lot | 32875.9043 | 3.409% | S | [5 empty] | 0.2841% | 0.2841% |  |  |  | 0.2841% | [8 empty] | 0.2841% |  |  | 0.2841% |  |  | 0.2841% | 0.11% | 0.11% | 0.11% |  |  |  | 1.1% | 0.25% |  | 0.02458%
[8 empty] | A | [5 empty] | 0.2841% | 0% |  |  |  | 0.2841% | [8 empty] | 0.2841% |  |  | 0.2841% |  |  | 0.2841% | [12 empty] | 1.989%
| D | CIVIL WORK |  |  | lot | 14688.8804 | 1.523% | S | [26 empty] | 0.07345% | 0.07345% | 0.07345% | 0.09591% | 0.09591% | 0.1133% | 0.3% | 0.3% | 0.1631% | 0.2% | 0.03459%
[8 empty] | A | [38 empty] | 1.523%
ANDONG MEAS | A | STRUCTURAL WORK |  |  | lot | 33750.775 | 3.5% | S |  | 0% | 0% | 0% | 0.035% | 0.385% | 0.14% | 0.21% | 1.015% | 0.49% | 0.14% |  |  |  |  | 0% | 0.035% | 0.14% | 0.14% | 0.175% |  |  |  |  | 0.035% | 0.28% |  | 0.01% | 0.01% | 0.06% |  | 0.15% |  | 0.04999%
[8 empty] | A |  | 0% | 0% | 0% | 0.035% | 0.385% | 0.14% | 0.21% | 1.015% | 0.49% | 0.14% |  |  |  |  | 0% | 0.035% | 0.14% | 0.14% | 0.175% |  |  |  |  | 0.035% | 0.28% | [12 empty] | 0.28%
| B | ARCHITECTURE WORKS |  |  | lot | 49022.2444 | 5.083% | S | [10 empty] | 0.3558% | 0.1017% |  | 0% | 0.05083% | [5 empty] | 0.1017% | 0.305% | 0.1525% | 0.1525% |  | 0.2033% |  | 0.2% | 0.25% | 0.15% | 0.15% | 1.5% | 1% | 0.2% | 0.15% | 0.06012%
[8 empty] | A | [10 empty] | 0.3558% | 0.1017% |  | 0% | 0.05083% | [5 empty] | 0.1017% | 0.305% | 0.1525% | 0.1525% |  | 0.2033% | [12 empty] | 3.66%
| C | MEP |  |  | lot | 32051.2825 | 3.324% | S | [5 empty] | 0.277% | 0.277% |  |  |  | 0.277% | [12 empty] | 0.277% | 0.277% | 0.277% |  | 0.1% | 0.1% |  | 0.1% |  | 1.2% | 0.1% |  | 0.06182%
[8 empty] | A | [5 empty] | 0.277% | 0.277% |  |  |  | 0.277% | [12 empty] | 0.277% | 0.277% | 0.277% | [12 empty] | 1.662%
| D | CIVIL WORK |  |  | lot | 5955.2195 | 0.6175% | S | [26 empty] | 0.054% | 0.054% | 0.054% | 0.054% | 0.054% | 0.09093% | 0.09093% | 0.09093% | 0.07474%
[8 empty] | A | [38 empty] | 0.6175%
OTHERS | A | SAFETY MANAGEMENT |  |  | lot | 7965.4765 | 0.826% | S |  | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294%
[8 empty] | A |  | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | [12 empty] | 0.2065%
| B | INDIRECT COST |  |  | lot | 120000 | 12.44% | S |  | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366%
[8 empty] | A |  | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | [12 empty] | 3.294%
| C | PROFIT & OVER HEAD COST |  |  | lot | 39827.3826 | 4.13% | S |  | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215%
[8 empty] | A |  | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | [12 empty] | 1.093%
TOTAL | [5 empty] | 964340.5037 | 100%
[5 empty] | Schedule Weekly Progress (%) |  |  | S | 0% | 0.8268% | 1.429% | 2.065% | 2.402% | 3.765% | 4.961% | 3.491% | 3.609% | 2.457% | 3.289% | 1.453% | 0.5104% | 1.58% | 1.023% | 1.342% | 1.533% | 1.984% | 1.08% | 3.189% | 0.8704% | 1.604% | 1.419% | 1.758% | 1.264% | 3.377% | 1.128% | 2.69% | 2.566% | 3.726% | 4.859% | 6.824% | 14.45% | 7.458% | 2.892% | 1.051% | 0.03459%
[5 empty] | Actual Weekly Progress (%) |  |  | A | 0% | 0.8268% | 1.429% | 2.065% | 2.402% | 3.765% | 4.677% | 3.491% | 3.609% | 2.457% | 3.289% | 1.453% | 0.5104% | 1.58% | 1.023% | 1.342% | 1.533% | 1.984% | 1.08% | 3.189% | 0.8704% | 1.604% | 1.419% | 1.758% | 1.488% | 3.38%
[5 empty] | Accumulative Schedule Progress (%) |  |  | Sc | 0% | 0.8268% | 2.255% | 4.32% | 6.722% | 10.49% | 15.45% | 18.94% | 22.55% | 25.01% | 28.29% | 29.75% | 30.26% | 31.84% | 32.86% | 34.2% | 35.74% | 37.72% | 38.8% | 41.99% | 42.86% | 44.46% | 45.88% | 47.64% | 48.91% | 52.28% | 53.41% | 56.1% | 58.67% | 62.39% | 67.25% | 74.08% | 88.52% | 95.98% | 98.87% | 99.92%
[5 empty] | Accumulative Actual Progress (%) |  |  | Ac | 0% | 0.8268% | 2.255% | 4.32% | 6.722% | 10.49% | 15.16% | 18.66% | 22.26% | 24.72% | 28.01% | 29.46% | 29.97% | 31.55% | 32.58% | 33.92% | 35.45% | 37.44% | 38.52% | 41.71% | 42.58% | 44.18% | 45.6% | 47.36% | 48.85% | 52.23%
[5 empty] | Ahead/Delay (%) |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.0599% | -0.05607%
[5 empty] | Ahead/Delay (days) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4 | 310.9556
|  |  | 4 | 1075.9316
|  |  | 27.8 | 3658.2576
|  |  | 70 | 3070.48
|  |  | 13 | 349.44 | [43 empty] | 2022-01-14 | 2022-09-30 | 260
|  |  | 85 | 533.7048
|  |  | 900 | 189.7489
|  |  | 85 | 98.4937 |  |  |  |  | 2022-01-14 | [38 empty] | 37 weeks | 36
|  |  | 900 | 328.2267
|  |  | 13 | 195
21566.2102
|  |  | 12 | 900.06
|  |  | 85 | 1351.585
|  |  | 900 | 1016.1482
|  |  | 13 | 2067.13
|  |  | 85 | 11092.5
|  |  | 900 | 4786.287
|  |  | 1.5 | 352.5
30878.1936
|  |  | 1150 | 10651.5472
|  |  | 1150 | 10672
|  |  | 1150 | 5577.5
|  |  | 1150 | 3977.1464
24200
|  |  | 22 | 24200
6695
|  |  | 11 | 6545
|  |  | 12.5 | 150
260
|  |  | 13 | 260
23050.5
|  |  | 22 | 18590
|  |  | 5.5 | 1072.5
|  |  | 7 | 3388
5610
|  |  | 620 | 620
|  |  | 375 | 750
|  |  | 200 | 200
|  |  | 200 | 400
|  |  | 550 | 1100
|  |  | 650 | 1950
|  |  | 120 | 240
|  |  | 50 | 350
1570
|  |  | 225 | 675
|  |  | 25 | 75
|  |  | 175 | 350
|  |  | 175 | 350
|  |  | 60 | 120
|  |  | 0 | Ecluded
332.7784
8208.0487
|  |  | 27.8 | 1501.2
|  |  | 1.5 | 540
|  |  | 85 | 3672
|  |  | 13 | 226.2
|  |  | 900 | 2268.6487
|  |  | 30 | 157.5
597.5302
|  |  | 4 | 8.8
|  |  | 85 | 280.2476
|  |  | 13 | 32.916
|  |  | 900 | 275.5667
|  |  | 18 | 1314
|  |  | 90 | 6750

## 7. Site Activity Photos
7. SITE ACTIVITY PHOTOS
SITE ACTIVITY PHOTOS
Banteay Meanchey (PIBMC)
Battambang (BIT)
Type-A: Installing ceiling frame | Type-A: Blocking the ventilation
Type-A: Installing PVC pipe for cable work | Type-A: Removing painting of door and security bar
Type-B: Installing ceiling frame | Type-B: Blocking the ventilation
Type-B: Installing PVC pipe for cable work | Type-B: Removing painting of door and security bar
Battambang (RPITSB)
Type-A: Installing PVC pipe for cable work | Type-A: Installing PVC pipe for cable work
Type-A: Painting door and security bar | Type-A: Installing ceiling frame
Type-B: Demolition wall | Type-B: Installing PVC pipe for cable work
Type-B: Painting door and security bar | Type-B: Preparing for flooring tile
Siem Reap (NPIA)
Type-B: Remove existing paint on window frame | Type-B: Remove existing paint on window frame
Type-B: Remove existing paint on window frame | Type-B: Remove existing paint on window frame
Type-B: Remove existing paint on window frame | Type-B: Remove existing paint on window frame
Type-B: Clean the floor tile and joint | Type-B: Clean the floor tile and joint
Siem Reap (RPITSSR)
Type-B: Prepare material for floor tile laying | Type-B: Prepare material for floor tile laying
Type-B: Floor tile laying | Type-B: Remove existing paint on window and door
Type-B: Remove existing paint on window and door | Type-B: Remove existing paint on window and door
Type-B: Remove existing paint on window and door | Type-B: Remove existing paint on window and door
Phnom Penh (NTTI)
A-Type-1 Install window glass | A-Type-1 Install acoustic ceiling panel
A-Type-1 Apply skim coat and sealer | A-Type-1 Install AC drain pipe
A-Type-1 Install electrical conduit and cement backfill | A-Type-5 Install window glass
A-Type-5 Apply finish wall painting external wall | A-Type-6 Install window glass
Phnom Penh (NTTI)
A-Type-6 Apply finish wall painting external wall | B-Type-2 Install window glass
B-Type-2 Apply finish wall painting external wall | B-Type-4 Install window glass
B-Type-4 Apply skim coat existing louver | B-Type-4 Install power cable for AC
B-Type-4 Install wire cable for Data system | B-Type-4 Apply skim coat and sealer painting
Phnom Penh (NIB)
Type B: External wall painting work | Type B: External wall painting work
Type B: LED Lighting Panel work | Type B: Acoustic wood panel work
Type B: AC outdoor unit work | Type B: AC outdoor unit work
Type B: AC indoor unit work | Type B: AC indoor unit work
Phnom Penh (NPIT)
Type B: Conduit pipe install and Wall mortar repaired | Type B: Conduit pipe install and Wall mortar repaired
Type A: Conduit pipe install and Wall mortar repaired | Type A: Conduit pipe install and Wall mortar repaired
Type A: Conduit pipe installation | Type A: Conduit pipe install and Wall mortar repaired
Type A: Conduit pipe installation | Type A: Wall cutting to install conduit pipe for consumer unit
Kampot (RPITSK)
Type A : Skimcoat work | Type A : Ceiling work
Type A : MEP work | Type A : Skimcoat work
Type B : Remove Existing Painting | Type B : Spray painting work
Type B : Ceiling work | Type B : Repairing tile joint
Kampong Speu (PIKSP)
Type-A:Installation ceiling | Type-A:Installation ceiling
Type-A:Installation ceiling | Type-A:Installing breaker
Type-B:Installation cable trunking | Type-B:Installation cable trunking
Type-B:Installing breaker | Type-B:Installing breaker

## 8. Construction Issues
8. CONSTRUCTION ISSUE
Establishing Enabling Environment in ICT Majors of TVET |  | CACPM Co.,Ltd
Construction Issue
1
Site Location: | Photo Reference
Problems / Descriptions:
Action by:
2
Site Location: | Photo Reference
Problems / Descriptions:
Action by:
3
Site Location: | Photo Reference
Problems / Descriptions:
Action by:
4
Site Location: | Photo Reference
Problems / Descriptions:
Action by: