## Cover
KINGDOM OF CAMBODIA
NATION RELIGION KING
WEEKLY PROGRESS REPORT
| 14 |  |  |  | 14
| From 30-Jan-26 ~ 5-Feb-26 |  |  |  | 30-Jan-26 | 5-Feb-26
Renovation Works of The Project for Building Capacity and
Establishing Enabling Environment in ICT Majors of TVET
in Cambodia
|  | Employer | : | KOICA Cambodia Office
|  | Consultant | : | KFS(Korea Forest Service) &
FA(Forestry Administration)
|  | Contractor | : | Cambodian Advanced Construction Project Management (CACPM)Co., Ltd

## 6. Workdone (hidden)
SUMMERY WEEKLY WORK DONE PROGRESS
Project: Strengthening Maternal and Child Health In North-Eastern of Cambodia | [38 empty] | CACPM CO.,LTD
ITEM NO |  | SCOPE OF WORK/ DESCRIPTION | CONTRACT AMOUNT
|  |  | QTY | UNIT | UNIT | AMOUNT |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | REMARK
[9 empty] | 14/1-21/1 | 22/1-28/1 | 29/1-4/2 | 5/2-11/2 | 12/2-18/2 | 19/2-25/2 | 26/2-4/3 | 5/3-11/3 | 12/3-18/3 | 19/3-25/3 | 26/3-1/4 | 2/4-8/4 | 9/4-15/4 | 16/4-22/4 | 23/4-29/4 | 30/4-6/5 | 7/5-13/5 | 14/5-20/5 | 21/5-27/5 | 28/5-3/6 | 4/6-10/6 | 11/6-17/6 | 18/6-24/6 | 25/6-1/7 | 2/7-8/7 | 9/7-15/7 | 16/7-22/7 | 23/7-29/7 | 30/7-6/8 | 7/8-13/8
SMCH |  |  |  |  | lot | 964340.51 | 100% | S
A
RH HOSPITAL | A | STRUCTURAL WORK |  |  | lot | 35294.21 | 3.66% | S |  | 0.0366% | 0.0366% | 0.0366% | 0.3294% | 0.0732% | 0.0366% | 0.2562% | 0.2562% | 0.6954% | 0.3294% | 0.0732% | 0.1098% |  |  | 0.183% | 0.183% | 0.0732% | 0.1098% | 0.0366% | 0.0366% | 0.3294% | 0.3294% | 0.1098%
[8 empty] | A | W2: 0.0366%; W3: 0.1464%; W4: 0.366%; W5: 0.1098%; W6: 0.4392%; W7: 1.208%; W8: 0.366%; W16: 0.183%; W17: 0.2562%; W18: 0.183%; W19: 0.0366%; W20: 0.2928%
| B | ARCHITECTURE WORKS |  |  | lot | 52161.59 | 5.409% | S | W14: 0.2705%; W15: 0.2705%; W16: 0.2164%; W22: 0.1623%; W23: 0.1623%; W24: 0.595%; W25: 0.6491%; W26: 0.5409%; W27: 0.4868%; W28: 1.082%; W29: 0.6491%; W30: 0.3245%
[8 empty] | A | W8: 0.05409%; W9: 0.3786%; W11: 0.05409%; W12: 0.05409%; W14: 0.2164%; W15: 0.05409%; W23: 0.05409%; W24: 0.05409%; W26: 0.3786%
| C | MEP |  |  | lot | 41072.35 | 4.259% | S | W7: 0.3549%; W8: 0.3549%; W12: 0.3549%; W20: 0.3549%; W21: 0.3549%; W22: 0.3549%; W23: 0.3549%; W24: 0.3549%; W25: 0.3549%; W26: 0.3549%; W27: 0.3549%; W28: 0.3549%
[8 empty] | A | W6: 0.3549%; W7: 0.3549%; W11: 0.3549%; W20: 0.3549%
| D | CIVIL WORK |  |  | lot | 35341.4749 | 3.665% | S | W9: 0.02281%; W10: 0.2851%; W11: 0.3308%; W12: 0.07984%; W13: 0.07984%; W14: 0.1027%; W15: 0.01141%; W16: 0.2851%; W17: 0.2512%; W18: 0.2094%; W19: 0.1256%; W20: 0.2931%; W21: 0.4187%; W22: 0.4815%; W23: 0.02483%; W24: 0.3298%; W25: 0.3331%
[8 empty] | A | W10: 0.01141%; W11: 0.1939%; W14: 0.4562%; W17: 0.07984%; W20: 0.2512%; W22: 0.1141%; W24: 0.04562%; W25: 0.1141%
KHOH NHEK | A | STRUCTURAL WORK |  |  | lot | 70021.4791 | 7.261% | S |  | 0.07261% | 0.1452% | 0.1452% | 0.4357% | 0.7987% | 0.2904% | 0.2178% | 1.017% | 0.7987% | 0.1452% | 0.07261% | 0.07261% |  |  | 0.3631% | 0.3631% | 0.1452% | 0.2904% | 0.07261% | 0.5809% | 0.5809% | 0.5809% | 0.07261%
[8 empty] | A | W2: 0.2178%; W3: 0.3631%; W4: 0.5809%; W5: 0.5809%; W6: 0.2904%; W7: 1.162%; W8: 0.8713%; W9: 0.2178%; W16: 0.2904%; W17: 0.2904%; W18: 0.5809%; W19: 0.1452%; W20: 0.2904%; W21: 0.07261%; W26: 1.307%
| A | ARCHITECTURE WORKS |  |  | lot | 94613.6544 | 9.811% | S | W14: 0.4906%; W15: 0.4906%; W16: 0.4906%; W22: 0.3924%; W23: 0.3924%; W24: 1.079%; W25: 1.374%; W26: 0.883%; W27: 0.9811%; W28: 1.079%; W29: 1.472%; W30: 0.6868%
[8 empty] | A | W10: 0.5887%; W11: 0.5887%; W12: 0.09811%; W14: 0%; W15: 0.1962%; W18: 0.09811%; W20: 0.4906%; W22: 0.3924%; W23: 0.2943%; W24: 0.2943%; W25: 0.09811%; W26: 0.2943%
| A | MEP |  |  | lot | 38901.5375 | 4.034% | S | W7: 0.3362%; W8: 0.3362%; W19: 0.3362%; W20: 0.3362%; W21: 0.3362%; W22: 0.3362%; W23: 0.3362%; W24: 0.3362%; W25: 0.3362%; W26: 0.3362%; W27: 0.3362%; W28: 0.3362%
[8 empty] | A | W6: 0.3362%; W7: 0.3362%
| A | CIVIL WORK |  |  | lot | 6107.5536 | 0.6333% | S | W16: 0.04898%; W17: 0.04898%; W18: 0.04898%; W19: 0.04898%; W20: 0.04898%; W21: 0.09709%; W22: 0.09709%; W23: 0.09709%; W24: 0.09709%
A
TAVENG | A | STRUCTURAL WORK |  |  | lot | 59711.0462 | 6.192% | S |  | 0.06192% | 0.1238% | 0.1238% | 0.3715% | 0.6811% | 0.2477% | 0.1858% | 0.8669% | 0.6811% | 0.1238% | 0.06192% | 0.06192% |  |  | 0.3096% | 0.3096% | 0.1238% | 0.2477% | 0.06192% | 0.4954% | 0.4954% | 0.4954% | 0.06192%
[8 empty] | A | W2: 0.06192%; W3: 0.3715%; W4: 0.4954%; W5: 0.8669%; W6: 0.3096%; W7: 0.1858%; W8: 0.4334%; W9: 1.3%; W10: 0.4334%; W11: 0.3096%; W17: 0.06192%; W18: 0.2477%; W19: 0.2477%; W20: 0.3715%; W25: 0.1238%; W26: 0.6192%
| B | ARCHITECTURE WORKS |  |  | lot | 59711.0462 | 6.192% | S | W14: 0.3096%; W15: 0.3096%; W16: 0.2477%; W22: 0.1858%; W23: 0.1858%; W24: 0.6811%; W25: 0.743%; W26: 0.6192%; W27: 0.5573%; W28: 1.238%; W29: 0.743%; W30: 0.3715%
[8 empty] | A | W12: 0.3715%; W14: 0.1858%; W15: 0.06192%; W21: 0.1858%; W22: 0.1238%; W23: 0.1238%; W24: 0.3715%
| C | MEP |  |  | lot | 34479.0908 | 3.575% | S | W7: 0.298%; W8: 0.298%; W19: 0.298%; W20: 0.298%; W21: 0.298%; W22: 0.298%; W23: 0.298%; W24: 0.298%; W25: 0.298%; W26: 0.298%; W27: 0.298%; W28: 0.298%
[8 empty] | A | W6: 0.298%; W7: 0.298%; W11: 0.298%
| D | CIVIL WORK |  |  | lot | 13756.6432 | 1.427% | S | W9: 0.008803%; W10: 0.11%; W11: 0.1276%; W12: 0.03081%; W13: 0.1034%; W14: 0.03961%; W15: 0.004401%; W16: 0.11%; W17: 0.06961%; W18: 0.05801%; W19: 0.03481%; W20: 0.08121%; W21: 0.116%; W22: 0.1334%; W23: 0.01714%; W24: 0.2278%; W25: 0.1538%
[8 empty] | A | W15: 0.1496%; W16: 0.09683%
OCHUM | A | STRUCTURAL WORK |  |  | lot | 36033.1227 | 3.737% | S |  | 0.07473% | 0.1868% | 0.1868% | 0.1121% | 0.3363% | 0.5231% | 0.3363% | 0.4484% | 0.07473% | 0.07473% | 0.07473% |  |  |  | 0.2616% | 0.2616% | 0.03737% | 0.2242% | 0.03737% | 0.1495% | 0.1495% | 0.1495% | 0.03737%
[8 empty] | A | W2: 0%; W3: 0.03737%; W4: 0.1121%; W5: 0.2989%; W6: 0.411%; W7: 0.3363%; W8: 1.046%; W9: 0.1868%; W16: 0.2616%; W17: 0.2989%; W18: 0.2242%; W20: 0.2989%; W25: 0.2616%
| B | ARCHITECTURE WORKS |  |  | lot | 50998.54 | 5.288% | S | W13: 0.1587%; W14: 0.1587%; W15: 0.1587%; W22: 0.5288%; W23: 0.5288%; W24: 0.2644%; W25: 0.2644%; W26: 0.05288%; W27: 0.476%; W28: 0.3702%; W29: 0.6875%; W30: 1.639%
[8 empty] | A | W10: 0.4231%; W11: 0.05288%; W12: 0.3173%; W14: 0.2115%; W15: 0%; W22: 0.1587%; W24: 0.05288%; W25: 0.1058%; W26: 0.5288%
| C | MEP |  |  | lot | 32875.9043 | 3.409% | S | W7: 0.2841%; W8: 0.2841%; W19: 0.2841%; W20: 0.2841%; W21: 0.2841%; W22: 0.2841%; W23: 0.2841%; W24: 0.2841%; W25: 0.2841%; W26: 0.2841%; W27: 0.2841%; W28: 0.2841%
[8 empty] | A | W6: 0.2841%; W7: 0.2841%; W11: 0.2841%; W20: 0.2841%; W23: 0.2841%; W26: 0.2841%
| D | CIVIL WORK |  |  | lot | 14688.8804 | 1.523% | S | W16: 0.07345%; W17: 0.07345%; W18: 0.07345%; W19: 0.09591%; W20: 0.09591%; W21: 0.1133%; W22: 0.2659%; W23: 0.2659%; W24: 0.1631%; W25: 0.1223%; W26: 0.1804%
A
ANDONG MEAS | A | STRUCTURAL WORK |  |  | lot | 33750.775 | 3.5% | S |  | 0.07% | 0.175% | 0.175% | 0.105% | 0.315% | 0.49% | 0.315% | 0.42% | 0.07% | 0.07% | 0.07% |  |  |  | 0.245% | 0.245% | 0.035% | 0.21% | 0.035% | 0.14% | 0.14% | 0.14% | 0.035%
[8 empty] | A | W2: 0%; W3: 0%; W4: 0%; W5: 0.035%; W6: 0.385%; W7: 0.14%; W8: 0.21%; W9: 1.015%; W10: 0.49%; W11: 0.14%; W16: 0%; W17: 0.035%; W18: 0.14%; W19: 0.14%; W20: 0.175%; W25: 0.035%; W26: 0.28%
| B | ARCHITECTURE WORKS |  |  | lot | 49022.2444 | 5.083% | S | W13: 0.1525%; W14: 0.1525%; W15: 0.1525%; W22: 0.5083%; W23: 0.5083%; W24: 0.2542%; W25: 0.2542%; W26: 0.05083%; W27: 0.4575%; W28: 0.3558%; W29: 0.6609%; W30: 1.576%
[8 empty] | A | W11: 0.3558%; W12: 0.1017%; W14: 0%; W15: 0.05083%; W21: 0.1017%; W22: 0.305%; W23: 0.1525%; W24: 0.1525%; W26: 0.2033%
| C | MEP |  |  | lot | 32051.2825 | 3.324% | S | W7: 0.277%; W8: 0.277%; W19: 0.277%; W20: 0.277%; W21: 0.277%; W22: 0.277%; W23: 0.277%; W24: 0.277%; W25: 0.277%; W26: 0.277%; W27: 0.277%; W28: 0.277%
[8 empty] | A | W6: 0.277%; W7: 0.277%; W11: 0.277%; W24: 0.277%; W25: 0.277%; W26: 0.277%
| D | CIVIL WORK |  |  | lot | 5955.2195 | 0.6175% | S | W16: 0.054%; W17: 0.054%; W18: 0.054%; W19: 0.054%; W20: 0.054%; W21: 0.09093%; W22: 0.09093%; W23: 0.09093%; W24: 0.07474%
A
OTHERS | A | SAFETY MANAGEMENT |  |  | lot | 7965.4765 | 0.826% | S |  | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059%
[8 empty] | A |  | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059% | 0.03059%
| B | INDIRECT COST |  |  | lot | 120000 | 12.44% | S |  | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609%
[8 empty] | A |  | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609% | 0.4609%
| C | PROFIT & OVER HEAD COST |  |  | lot | 39827.3826 | 4.13% | S |  | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153%
[8 empty] | A |  | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153% | 0.153%
TOTAL | [5 empty] | 964340.5037 | 100%
[5 empty] | Schedule Weekly Progress (%) |  |  | S | 0% | 0.9603% | 1.312% | 1.312% | 1.998% | 2.849% | 3.782% | 3.506% | 3.684% | 3.36% | 1.846% | 1.462% | 1.383% | 2.168% | 2.042% | 3.533% | 2.504% | 1.503% | 3.281% | 3.011% | 4.433% | 6.736% | 6.163% | 6.278% | 6.088% | 4.522% | 5.153% | 6.32% | 4.212% | 4.598%
[5 empty] | Actual Weekly Progress (%) |  |  | A | 0% | 0.9608% | 1.312% | 1.312% | 2.536% | 4.03% | 5.226% | 3.626% | 3.743% | 2.591% | 3.553% | 1.587% | 0.6444% | 1.714% | 1.157% | 1.476% | 1.667% | 2.118% | 1.214% | 3.454% | 1.004% | 1.738% | 1.553% | 1.892% | 1.66% | 4.817%
[5 empty] | Accumulative Schedule Progress (%) |  |  | Sc | 0% | 0.9603% | 2.272% | 3.584% | 5.582% | 8.431% | 12.21% | 15.72% | 19.4% | 22.76% | 24.61% | 26.07% | 27.45% | 29.62% | 31.66% | 35.2% | 37.7% | 39.2% | 42.49% | 45.5% | 49.93% | 56.67% | 62.83% | 69.11% | 75.19% | 79.72% | 84.87% | 91.19% | 95.4% | 100%
[5 empty] | Accumulative Actual Progress (%) |  |  | Ac | 0% | 0.9608% | 2.273% | 3.585% | 6.121% | 10.15% | 15.38% | 19% | 22.74% | 25.34% | 28.89% | 30.48% | 31.12% | 32.84% | 33.99% | 35.47% | 37.14% | 39.25% | 40.47% | 43.92% | 44.93% | 46.66% | 48.22% | 50.11% | 51.77% | 56.59%
[5 empty] | Ahead/Delay (%) |  |  |  | 0% | 0.0004927% | 0.0004927% | 0.0004927% | 0.5383% | 1.719% | 3.163% | 3.283% | 3.342% | 2.573% | 4.281% | 4.405% | 3.667% | 3.213% | 2.328% | 0.2711% | -0.566% | 0.0494% | -2.018% | -1.575% | -5.003% | -10% | -14.61% | -19% | -23.42% | -23.13%
[5 empty] | Ahead/Delay (days) |  |  |  | 0 | 1 | 1 | 1 | 2 | 5 | 9 | 9 | 9 | 7 | 12 | 12 | 10 | 9 | 7 | 1 | -2 | 1 | -6 | -5 | -14 | -27 | -38 | -50 | -61 | -61
|  |  | 4 | 310.9556
|  |  | 4 | 1075.9316
|  |  | 27.8 | 3658.2576
|  |  | 70 | 3070.48
|  |  | 13 | 349.44 | [35 empty] | 2022-01-14 | 2022-09-30 | 260
|  |  | 85 | 533.7048
|  |  | 900 | 189.7489
|  |  | 85 | 98.4937 |  |  |  |  | W1: 2022-01-14 |  | 37 weeks
|  |  | 900 | 328.2267
|  |  | 13 | 195
21566.2102
|  |  | 12 | 900.06
|  |  | 85 | 1351.585
|  |  | 900 | 1016.1482
|  |  | 13 | 2067.13
|  |  | 85 | 11092.5
|  |  | 900 | 4786.287
|  |  | 1.5 | 352.5
30878.1936
|  |  | 1150 | 10651.5472
|  |  | 1150 | 10672
|  |  | 1150 | 5577.5
|  |  | 1150 | 3977.1464
24200
|  |  | 22 | 24200
6695
|  |  | 11 | 6545
|  |  | 12.5 | 150
260
|  |  | 13 | 260
23050.5
|  |  | 22 | 18590
|  |  | 5.5 | 1072.5
|  |  | 7 | 3388
5610
|  |  | 620 | 620
|  |  | 375 | 750
|  |  | 200 | 200
|  |  | 200 | 400
|  |  | 550 | 1100
|  |  | 650 | 1950
|  |  | 120 | 240
|  |  | 50 | 350
1570
|  |  | 225 | 675
|  |  | 25 | 75
|  |  | 175 | 350
|  |  | 175 | 350
|  |  | 60 | 120
|  |  | 0 | Ecluded
332.7784
8208.0487
|  |  | 27.8 | 1501.2
|  |  | 1.5 | 540
|  |  | 85 | 3672
|  |  | 13 | 226.2
|  |  | 900 | 2268.6487
|  |  | 30 | 157.5
597.5302
|  |  | 4 | 8.8
|  |  | 85 | 280.2476
|  |  | 13 | 32.916
|  |  | 900 | 275.5667
|  |  | 18 | 1314
|  |  | 90 | 6750

## 6. Workdone-Rev01 (hidden)
SUMMERY WEEKLY WORK DONE PROGRESS
Project: Strengthening Maternal and Child Health In North-Eastern of Cambodia | [45 empty] | CACPM CO.,LTD
ITEM NO |  | SCOPE OF WORK/ DESCRIPTION | CONTRACT AMOUNT
|  |  | QTY | UNIT | UNIT | AMOUNT |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | REMARK
[9 empty] | 14/1-21/1 | 22/1-28/1 | 29/1-4/2 | 5/2-11/2 | 12/2-18/2 | 19/2-25/2 | 26/2-4/3 | 5/3-11/3 | 12/3-18/3 | 19/3-25/3 | 26/3-1/4 | 2/4-8/4 | 9/4-15/4 | 16/4-22/4 | 23/4-29/4 | 30/4-6/5 | 7/5-13/5 | 14/5-20/5 | 21/5-27/5 | 28/5-3/6 | 4/6-10/6 | 11/6-17/6 | 18/6-24/6 | 25/6-1/7 | 2/7-8/7 | 9/7-15/7 | 16/7-22/7 | 23/7-29/7 | 30/7-6/8 | 7/8-13/8 | 14/8-20/8 | 21/8-27/8 | 28/8-3/9 | 4/9-10/9 | 11/9-17/9 | 18/9-24/9 | 25/9-1/10
SMCH |  |  |  |  | lot | 964340.51 | 100% | S
A
RH HOSPITAL | A | STRUCTURAL WORK |  |  | lot | 35294.21 | 3.66% | S | W2: 0.0366%; W3: 0.1464%; W4: 0.366%; W5: 0.1098%; W6: 0.4392%; W7: 1.208%; W8: 0.366%; W16: 0.183%; W17: 0.2562%; W18: 0.183%; W19: 0.0366%; W20: 0.2928%; W28: 0.02%; W29: 0.01%; W30: 0.006599%
[8 empty] | A | W2: 0.0366%; W3: 0.1464%; W4: 0.366%; W5: 0.1098%; W6: 0.4392%; W7: 1.208%; W8: 0.366%; W16: 0.183%; W17: 0.2562%; W18: 0.183%; W19: 0.0366%; W20: 0.2928% |  | 0.0366%
| B | ARCHITECTURE WORKS |  |  | lot | 52161.59 | 5.409% | S | W8: 0.05409%; W9: 0.3786%; W11: 0.05409%; W12: 0.05409%; W14: 0.2164%; W15: 0.05409%; W23: 0.05409%; W24: 0.05409%; W26: 0.3786%; W27: 0.05%; W28: 0.1%; W29: 0.05%; W30: 0.7%; W31: 1.5%; W32: 1.5%; W33: 0.15%; W34: 0.06087%
[8 empty] | A | W8: 0.05409%; W9: 0.3786%; W11: 0.05409%; W12: 0.05409%; W14: 0.2164%; W15: 0.05409%; W23: 0.05409%; W24: 0.05409%; W26: 0.3786% |  | 4.111%
| C | MEP |  |  | lot | 41072.35 | 4.259% | S | W6: 0.2242%; W7: 0.2242%; W11: 0.2242%; W20: 0.2242%; W28: 0.22%; W29: 0.22%; W30: 0.22%; W31: 0.22%; W32: 0.4%; W33: 1%; W34: 0.5%; W35: 0.5%; W36: 0.08246%
[8 empty] | A | W6: 0.2242%; W7: 0.2242%; W11: 0.2242%; W20: 0.2242% |  | 3.362%
| D | CIVIL WORK |  |  | lot | 35341.4749 | 3.665% | S | W10: 0.01141%; W11: 0.1939%; W14: 0.4562%; W17: 0.07984%; W20: 0.2512%; W22: 0.1141%; W24: 0.04562%; W25: 0.1141%; W27: 0.11%; W31: 0.5%; W32: 0.5%; W33: 0.5%; W34: 0.3%; W35: 0.3%; W36: 0.1885%
[8 empty] | A | W10: 0.01141%; W11: 0.1939%; W14: 0.4562%; W17: 0.07984%; W20: 0.2512%; W22: 0.1141%; W24: 0.04562%; W25: 0.1141% |  | 2.398%
KHOH NHEK | A | STRUCTURAL WORK |  |  | lot | 70021.4791 | 7.261% | S | W2: 0.2178%; W3: 0.3631%; W4: 0.5809%; W5: 0.5809%; W6: 0.2904%; W7: 1.162%; W8: 0.8713%; W9: 0.2178%; W16: 0.2904%; W17: 0.2904%; W18: 0.5809%; W19: 0.1452%; W20: 0.2904%; W21: 0.07261%; W26: 0.5%; W30: 0.01%; W31: 0.01%; W33: 0.4%; W34: 0.39%
[8 empty] | A | W2: 0.2178%; W3: 0.3631%; W4: 0.5809%; W5: 0.5809%; W6: 0.2904%; W7: 1.162%; W8: 0.8713%; W9: 0.2178%; W16: 0.2904%; W17: 0.2904%; W18: 0.5809%; W19: 0.1452%; W20: 0.2904%; W21: 0.07261%; W26: 0.5% |  | 0.81%
| A | ARCHITECTURE WORKS |  |  | lot | 94613.6544 | 9.811% | S | W10: 0.5887%; W11: 0.5887%; W12: 0.09811%; W14: 0%; W15: 0.1962%; W18: 0.09811%; W20: 0.4906%; W22: 0.3924%; W23: 0.2943%; W24: 0.2943%; W25: 0.09811%; W26: 0.2943%; W28: 0.15%; W29: 0.15%; W31: 1%; W33: 3%; W34: 2%; W36: 0.0773%
[8 empty] | A | W10: 0.5887%; W11: 0.5887%; W12: 0.09811%; W14: 0%; W15: 0.1962%; W18: 0.09811%; W20: 0.4906%; W22: 0.3924%; W23: 0.2943%; W24: 0.2943%; W25: 0.09811%; W26: 0.2943% |  | 6.377%
| A | MEP |  |  | lot | 38901.5375 | 4.034% | S | W6: 0.3362%; W7: 0.3362%; W27: 0.11%; W29: 0.33%; W30: 0.22%; W31: 0.22%; W32: 0.4%; W33: 1%; W34: 0.5%; W35: 0.5%; W36: 0.08167%
[8 empty] | A | W6: 0.3362%; W7: 0.3362% |  | 3.362%
| A | CIVIL WORK |  |  | lot | 6107.5536 | 0.6333% | S | W28: 0.04898%; W29: 0.04898%; W30: 0.04898%; W31: 0.04898%; W32: 0.04898%; W33: 0.09709%; W34: 0.09709%; W35: 0.09709%; W36: 0.09709%
[8 empty] | A | [38 empty] | 0.6333%
TAVENG | A | STRUCTURAL WORK |  |  | lot | 59711.0462 | 6.192% | S | W2: 0.06192%; W3: 0.3715%; W4: 0.4954%; W5: 0.8669%; W6: 0.3096%; W7: 0.1858%; W8: 0.4334%; W9: 1.3%; W10: 0.4334%; W11: 0.3096%; W17: 0.06192%; W18: 0.2477%; W19: 0.2477%; W20: 0.3715%; W25: 0.1238%; W26: 0.12%; W31: 0.03%; W32: 0.21%; W34: 0.01151%
[8 empty] | A | W2: 0.06192%; W3: 0.3715%; W4: 0.4954%; W5: 0.8669%; W6: 0.3096%; W7: 0.1858%; W8: 0.4334%; W9: 1.3%; W10: 0.4334%; W11: 0.3096%; W17: 0.06192%; W18: 0.2477%; W19: 0.2477%; W20: 0.3715%; W25: 0.1238%; W26: 0.1238% |  | 0.2477%
| B | ARCHITECTURE WORKS |  |  | lot | 59711.0462 | 6.192% | S | W12: 0.3715%; W14: 0.1858%; W15: 0.06192%; W21: 0.1858%; W22: 0.1238%; W23: 0.1238%; W24: 0.3715%; W28: 0.6%; W29: 0.6%; W30: 0.8%; W31: 0.22%; W32: 0.5%; W33: 1%; W34: 0.5%; W35: 0.5%; W36: 0.04777%
[8 empty] | A | W12: 0.3715%; W14: 0.1858%; W15: 0.06192%; W21: 0.1858%; W22: 0.1238%; W23: 0.1238%; W24: 0.3715% |  | 4.768%
| C | MEP |  |  | lot | 34479.0908 | 3.575% | S | W6: 0.298%; W7: 0.298%; W11: 0.298%; W27: 0.11%; W28: 0.22%; W30: 0.5%; W32: 0.3%; W33: 1%; W34: 0.5%; W36: 0.05155%
[8 empty] | A | W6: 0.298%; W7: 0.298%; W11: 0.298% |  | 2.682%
| D | CIVIL WORK |  |  | lot | 13756.6432 | 1.427% | S | W15: 0.1496%; W16: 0.09683%; W28: 0.04898%; W29: 0.04898%; W30: 0.35%; W31: 0.2%; W32: 0.2%; W33: 0.09709%; W34: 0.09709%; W35: 0.09709%; W36: 0.04083%
[8 empty] | A | W15: 0.1496%; W16: 0.09683% |  | 1.18%
OCHUM | A | STRUCTURAL WORK |  |  | lot | 36033.1227 | 3.737% | S | W2: 0%; W3: 0.03737%; W4: 0.1121%; W5: 0.2989%; W6: 0.411%; W7: 0.3363%; W8: 1.046%; W9: 0.1868%; W16: 0.2616%; W17: 0.2989%; W18: 0.2242%; W20: 0.2989%; W28: 0.2242%
[8 empty] | A | W2: 0%; W3: 0.03737%; W4: 0.1121%; W5: 0.2989%; W6: 0.411%; W7: 0.3363%; W8: 1.046%; W9: 0.1868%; W16: 0.2616%; W17: 0.2989%; W18: 0.2242%; W20: 0.2989%; W25: 0.2242% |  | 0%
| B | ARCHITECTURE WORKS |  |  | lot | 50998.54 | 5.288% | S | W10: 0.4231%; W11: 0.05288%; W12: 0.3173%; W14: 0.2115%; W15: 0%; W22: 0.1587%; W24: 0.05288%; W25: 0.1058%; W26: 0.5288%; W32: 0.4%; W33: 2%; W34: 1%; W36: 0.03748%
[8 empty] | A | W10: 0.4231%; W11: 0.05288%; W12: 0.3173%; W14: 0.2115%; W15: 0%; W22: 0.1587%; W24: 0.05288%; W25: 0.1058%; W26: 0.5288% |  | 3.437%
| C | MEP |  |  | lot | 32875.9043 | 3.409% | S | W6: 0.2841%; W7: 0.2841%; W11: 0.2841%; W20: 0.2841%; W23: 0.2841%; W26: 0.2841%; W27: 0.11%; W28: 0.11%; W29: 0.11%; W33: 1.1%; W34: 0.25%; W36: 0.02458%
[8 empty] | A | W6: 0.2841%; W7: 0%; W11: 0.2841%; W20: 0.2841%; W23: 0.2841%; W26: 0.2841% |  | 1.989%
| D | CIVIL WORK |  |  | lot | 14688.8804 | 1.523% | S | W27: 0.07345%; W28: 0.07345%; W29: 0.07345%; W30: 0.09591%; W31: 0.09591%; W32: 0.1133%; W33: 0.3%; W34: 0.3%; W35: 0.1631%; W36: 0.2%; W37: 0.03459%
[8 empty] | A | [38 empty] | 1.523%
ANDONG MEAS | A | STRUCTURAL WORK |  |  | lot | 33750.775 | 3.5% | S | W2: 0%; W3: 0%; W4: 0%; W5: 0.035%; W6: 0.385%; W7: 0.14%; W8: 0.21%; W9: 1.015%; W10: 0.49%; W11: 0.14%; W16: 0%; W17: 0.035%; W18: 0.14%; W19: 0.14%; W20: 0.175%; W25: 0.035%; W26: 0.28%; W28: 0.01%; W29: 0.01%; W30: 0.06%; W32: 0.15%; W34: 0.04999%
[8 empty] | A | W2: 0%; W3: 0%; W4: 0%; W5: 0.035%; W6: 0.385%; W7: 0.14%; W8: 0.21%; W9: 1.015%; W10: 0.49%; W11: 0.14%; W16: 0%; W17: 0.035%; W18: 0.14%; W19: 0.14%; W20: 0.175%; W25: 0.035%; W26: 0.28% |  | 0.28%
| B | ARCHITECTURE WORKS |  |  | lot | 49022.2444 | 5.083% | S | W11: 0.3558%; W12: 0.1017%; W14: 0%; W15: 0.05083%; W21: 0.1017%; W22: 0.305%; W23: 0.1525%; W24: 0.1525%; W26: 0.2033%; W28: 0.2%; W29: 0.25%; W30: 0.15%; W31: 0.15%; W32: 1.5%; W33: 1%; W34: 0.2%; W35: 0.15%; W36: 0.06012%
[8 empty] | A | W11: 0.3558%; W12: 0.1017%; W14: 0%; W15: 0.05083%; W21: 0.1017%; W22: 0.305%; W23: 0.1525%; W24: 0.1525%; W26: 0.2033% |  | 3.66%
| C | MEP |  |  | lot | 32051.2825 | 3.324% | S | W6: 0.277%; W7: 0.277%; W11: 0.277%; W24: 0.277%; W25: 0.277%; W26: 0.277%; W28: 0.1%; W29: 0.1%; W31: 0.1%; W33: 1.2%; W34: 0.1%; W36: 0.06182%
[8 empty] | A | W6: 0.277%; W7: 0.277%; W11: 0.277%; W24: 0.277%; W25: 0.277%; W26: 0.277% |  | 1.662%
| D | CIVIL WORK |  |  | lot | 5955.2195 | 0.6175% | S | W27: 0.054%; W28: 0.054%; W29: 0.054%; W30: 0.054%; W31: 0.054%; W32: 0.09093%; W33: 0.09093%; W34: 0.09093%; W35: 0.07474%
[8 empty] | A | [38 empty] | 0.6175%
OTHERS | A | SAFETY MANAGEMENT |  |  | lot | 7965.4765 | 0.826% | S |  | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294%
[8 empty] | A |  | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | 0.02294% | [12 empty] | 0.2065%
| B | INDIRECT COST |  |  | lot | 120000 | 12.44% | S |  | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366%
[8 empty] | A |  | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | 0.366% | [12 empty] | 3.294%
| C | PROFIT & OVER HEAD COST |  |  | lot | 39827.3826 | 4.13% | S |  | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215%
[8 empty] | A |  | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | 0.1215% | [12 empty] | 1.093%
TOTAL | [5 empty] | 964340.5037 | 100%
[5 empty] | Schedule Weekly Progress (%) |  |  | S | 0% | 0.8268% | 1.429% | 2.065% | 2.402% | 3.765% | 4.961% | 3.491% | 3.609% | 2.457% | 3.289% | 1.453% | 0.5104% | 1.58% | 1.023% | 1.342% | 1.533% | 1.984% | 1.08% | 3.189% | 0.8704% | 1.604% | 1.419% | 1.758% | 1.264% | 3.377% | 1.128% | 2.69% | 2.566% | 3.726% | 4.859% | 6.824% | 14.45% | 7.458% | 2.892% | 1.051% | 0.03459%
[5 empty] | Actual Weekly Progress (%) |  |  | A | 0% | 0.8268% | 1.429% | 2.065% | 2.402% | 3.765% | 4.677% | 3.491% | 3.609% | 2.457% | 3.289% | 1.453% | 0.5104% | 1.58% | 1.023% | 1.342% | 1.533% | 1.984% | 1.08% | 3.189% | 0.8704% | 1.604% | 1.419% | 1.758% | 1.488% | 3.38%
[5 empty] | Accumulative Schedule Progress (%) |  |  | Sc | 0% | 0.8268% | 2.255% | 4.32% | 6.722% | 10.49% | 15.45% | 18.94% | 22.55% | 25.01% | 28.29% | 29.75% | 30.26% | 31.84% | 32.86% | 34.2% | 35.74% | 37.72% | 38.8% | 41.99% | 42.86% | 44.46% | 45.88% | 47.64% | 48.91% | 52.28% | 53.41% | 56.1% | 58.67% | 62.39% | 67.25% | 74.08% | 88.52% | 95.98% | 98.87% | 99.92%
[5 empty] | Accumulative Actual Progress (%) |  |  | Ac | 0% | 0.8268% | 2.255% | 4.32% | 6.722% | 10.49% | 15.16% | 18.66% | 22.26% | 24.72% | 28.01% | 29.46% | 29.97% | 31.55% | 32.58% | 33.92% | 35.45% | 37.44% | 38.52% | 41.71% | 42.58% | 44.18% | 45.6% | 47.36% | 48.85% | 52.23%
[5 empty] | Ahead/Delay (%) |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.2841% | -0.0599% | -0.05607%
[5 empty] | Ahead/Delay (days) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4 | 310.9556
|  |  | 4 | 1075.9316
|  |  | 27.8 | 3658.2576
|  |  | 70 | 3070.48
|  |  | 13 | 349.44 | [43 empty] | 2022-01-14 | 2022-09-30 | 260
|  |  | 85 | 533.7048
|  |  | 900 | 189.7489
|  |  | 85 | 98.4937 |  |  |  |  | W1: 2022-01-14 |  |  | 37 weeks | 36
|  |  | 900 | 328.2267
|  |  | 13 | 195
21566.2102
|  |  | 12 | 900.06
|  |  | 85 | 1351.585
|  |  | 900 | 1016.1482
|  |  | 13 | 2067.13
|  |  | 85 | 11092.5
|  |  | 900 | 4786.287
|  |  | 1.5 | 352.5
30878.1936
|  |  | 1150 | 10651.5472
|  |  | 1150 | 10672
|  |  | 1150 | 5577.5
|  |  | 1150 | 3977.1464
24200
|  |  | 22 | 24200
6695
|  |  | 11 | 6545
|  |  | 12.5 | 150
260
|  |  | 13 | 260
23050.5
|  |  | 22 | 18590
|  |  | 5.5 | 1072.5
|  |  | 7 | 3388
5610
|  |  | 620 | 620
|  |  | 375 | 750
|  |  | 200 | 200
|  |  | 200 | 400
|  |  | 550 | 1100
|  |  | 650 | 1950
|  |  | 120 | 240
|  |  | 50 | 350
1570
|  |  | 225 | 675
|  |  | 25 | 75
|  |  | 175 | 350
|  |  | 175 | 350
|  |  | 60 | 120
|  |  | 0 | Ecluded
332.7784
8208.0487
|  |  | 27.8 | 1501.2
|  |  | 1.5 | 540
|  |  | 85 | 3672
|  |  | 13 | 226.2
|  |  | 900 | 2268.6487
|  |  | 30 | 157.5
597.5302
|  |  | 4 | 8.8
|  |  | 85 | 280.2476
|  |  | 13 | 32.916
|  |  | 900 | 275.5667
|  |  | 18 | 1314
|  |  | 90 | 6750